## Sheet1
| DBSA ASIDI: | SCHOOL BY SCHOOL REPORT as at end Feb 2015
| Project Name | Start Date (Construction) | % Progress to Date | Notes on Progress | School Location (educational District) | School Enrolment (Actual/Planned) | Outputs (Total)
[7 empty] | Classrooms | Grade R | Admin Block | Media Centre | Computer lab | Multi-purpose Class | Social Science Lab | Science Lab | Nutrition | Tuckshop / Change rooms | Educator VIP | Learner VIP | Grade R VIP
FREE STATE | Dorrington Matsepe P/S | 2014-03-18 | 90% | Making good progress but slightly behind target. Contractor is being closely monitored. | Fezile Dabi | 1109 | 27 | 3 | 1 | 0 |  | 2 |  | 1 | 1 | 1 | 15 | 52 | 15
| Phephetso S/S | 2014-03-18 | 90% | Slightly behind target but being monitored. | Fezile Dabi | 1055 | 27 | 0 | 1 | 1 |  | 2 |  | 2 | 1 | 1 | 13 | 65 | 0
| Vredefort P/S | 2014-03-19 | 100% | The project has reached practical completion and scheduled for works completion on 11/03/2015. | Fezile Dabi | 556 | 14 | 3 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 12 | 22 | 20
| Lehutso P/S | 2014-03-20 | 96% | Slightly behind target but being monitored. | Fezile Dabi | 1706 | 40 | 3 | 1 | 0 |  | 2 |  | 1 | 1 | 1 | 5 | 23 | 9
| Metsimatle S/S | Delayed | N/A | Environmental Impact Assessment approved. Contractor in the process of being mobilised. | Fezile Dabi | 366 | 10 | 0 | 1 | 0 |  | 1 |  | 1 | 1 | 1 | 5 | 16 | 0
| Pele-ya-pele S/S | 2014-03-20 | 62% | Delayed due to contractor repairing and relocating unknown underground services, and rejection of backfill material. Variation Order approved and EoT claim is being evaluated by PSP. Electrical connection a problem and being discussed with ESKOM. | Fezile Dabi | 733 | 25 | 0 | 1 | 0 |  | 1 |  | 0 | 1 | 0 | 7 | 20 | 0
| Qalabotjha S/S | 2014-03-25 | 54% | Delayed due to scope change related to rising water table. VO approved and EoT claim is being evaluated by PSP. | Fezile Dabi | 636 | 24 | 0 | 1 | 0 |  | 1 |  | 1 | 1 | 1 | 7 | 20 | 0
| Tjhebelopele P/S | 2014-03-26 | 88% | Slightly behind target but being monitored. | Metro FS | 1240 | 28 | 3 | 1 | 0 |  | 1 |  | 1 | 1 | 1 | 7 | 18 | 9
| Bethlehem C/S | 2014-04-16 | 60% | Behind target due to: * Excavation of unknown septic tanks and additional excavation work to remove unsuitable founding material. * Steel strike resulted in delay in obtaining base plates. EoT claim is being evaluated by the PSP. | Bethlehem | 1150 | 27 | 3 | 1 | 0 |  | 2 |  | 2 | 1 | 1 | 27 | 66 | 32
| Ntsu S/S | 2014-04-16 | 64% | Behind target due to: * Municipality closing access road to repair waterline. * Change in design specs. VO approved. EoT claim is being evaluated by the PSP. | Bethlehem | 1291 | 33 | 0 | 1 | 0 |  | 2 |  | 2 | 1 | 0 | 37 | 66 | 0
| Clarens P/S | 2014-08-29 | 50% | On track however there is interference from the local community which may hinder progress. | Clarens | 387 | 14 | 2 | 1 | 0 |  | 1 |  | 1 | 1 | 0 | 15 | 44 | 12
NORTH WEST | Motaung Primary School | 2014-03-15 | 90% | Bulk Earthworks 100%, Platform Construction 100%, Foundation Concrete 100%, Brickwork 100% (21 Structures), Roofwork 100%, Finishes 95%, Site Works 80% | Ventersdorp LM | 950 | 24 | 3 | 1 | 1 |  | 2 |  | 1 | 1 | 1 | 4 | 14 | 3
| Toevlug Primary School | 2014-03-15 | 96% | Bulk Earthworks 100%, Platform Construction 100%, Foundation Concrete 100%, Brickwork 100% (19 Structures), Roofwork 100% Finishes 80%, Site Works 30% | Ventersdorp LM | 920 | 21 | 3 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 4 | 14 | 3
LIMPOPO | Molepo Primary School | 2014-03-18 | 100% | Bulk Earthworks 100%, Platform Construction 100%, Foundation Concrete 100%, Brickwork 100% (10 Structures), Roofwork 100%, Finishes 100%, Site Works 100% | Polokwane LM | 190 | 10 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 2 | 12 | 1
| Sedibeng Special School | 2014-03-18 | 100% | Bulk Earthworks 100%, Platform Construction 100%, Foundation Concrete 100%, Brickwork 100% (15 Structures), Roofwork 100%, Finishes 100%, Site Works 100% | Lephalale LM | 100 | 12 | 0 | 1 | 1 |  | 5 |  | 0 | 1 | 0 | 2 | 12 | 0
| Honoko Primary School | 2014-04-18 | 75% | Bulk Earthworks 100%, Platform Excavations 100%, Retaining Walls 100%, Foundations Concrete 100%, Brickwork 100% (7 Structures), Roofwork 100%, Finishes 35%,Site Works 50% | Makhuduthamaga LM | 142 | 7 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 2 | 8 | 1
MPUMALANGA | Ngema Primary School | 2013-12-06 | 100% | Approaching FC which is scheduled for 03/15 | Gert Sibande - Mkhondo LM | 696 | 21 | 3 | 1 | 0 |  | 1 |  | 1 | 1 | 0 | 0 | 1 | 1
| Wesselton Primary School | 2014-01-14 | 97% | Final Stages of Construction - Finishes, External Works and Security. PC date move from 09-Jan-15 to 18-Mar-15. The contractor will however reach PC by mid-Mar. | Gert Sibande - Msukalingwa LM | 1214 | 31 | 3 | 1 | 0 |  | 2 |  | 1 | 1 | 1 | 1 | 1 | 1
| Goba Primary School | 2013-12-10 | 100% | WC scheduled for 25/03/15. | Ehlanzeni - Nkomazi LM | 349 | 14 | 2 | 1 | 1 |  | 0 |  | 1 | 1 | 0 | 1 | 1 | 1
| Tiyimeleni Primary School | 2013-12-11 | 93% | Final Stages of Construction - Finishes, External Works and Security. PC date move from 08-Jan-15 to 31-Mar-15 as Contractor is behind schedule. Currently incurring penalties R3500/day. | Ehlanzeni - Bushbuckridge LM | 305 | 9 | 2 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 1 | 1 | 1
| Loding Primary School | 2013-12-11 | 100% | FC achieved on 16/02/15. | NkangalaThembisile Hani LM | 554 | 14 | 2 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 1 | 1 | 1
NORTHERN CAPE | Sternham Intermediary School | 2013-03-26 | 99% | PC Scheduled for 09/03/15. | Siyanda (Groblershoop) | 897 | 9 | 1 | 1 | 0 |  | 1 |  | 1 | 1 | 0 | 1 | 1 | 1
EASTERN CAPE BATCH 2 | BEKISIZWE JSS | 2014-08-27 | 1% | Contractor handed ove site on 27 August 2014. | Mqanduli | 521 | 11 | 2 | 1 | 1 |  | 0 | 1 |  | 1 | 0 | 4 | 11 | 6
| Bhekizulu SSS | 2014-06-27 | 11% | Delays from the contractor. Contractor behind schedule though is recovering. Time of commencement was late. Progress of Contractor is monitored | Libode | 1363 | 34 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | - | 1 | 4 | 0
| Bukazi JSS | 2014-06-24 | 5% | Project behind schedule by 3 weeks. Contractor issued with a notice of default. Will be monitored according to recovery plan. | Lusikisiki | 650 actual ,1000 ( Planned) | 22 | 0 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 5 | 25 | 0
| Bungu JSS | 2014-05-20 | 26% | Contractor on schedule. | Libode | 432 | 9 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 4 | 12 | 6
| Chief H Boklein SSS | 2014-06-27 | 12% | Delays from the contractor. Contractor behind schedule though is recovering. Time of commencement was late. Progress of Contractor is monitored | Libode | 1451 | 36 | 0 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | - | 1 | 4 | 0
| Dalibango JPS | 2014-07-24 | 3% | Contractor behind schedule and being monitored. | Libode | 116 | 4 | 1 | 1 | 1 |  | 0 |  | 1 | 0 | 0 | 2 | 18 | 4
| Dalibunga SSS | 2014-05-05 | 28% | Contractor behind schedule and being monitored. | Libode | 455/1094 | 27 | 0 | 1 | 1 |  | 2 |  | 2 | 1 |  | 4 | 22 | 0
| Dokodela JSS | 2014-06-26 | 10% | Contractor behind schedule and being monitored. | Libode | 252 | 7 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | - | 1 | 1 | 1
| Dweba SSS | 2014-05-26 | 8% | Progress on site is very slow. Contractor took longer on the earthworks, the excavations have been completed but they are still awaiting steel reinforcement to pour concrete strip footings. | Qumbu | 544/909 | 20 | 0 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 4 | 22 | 0
| Gcinilifu JSS | 2014-05-22 | 14% | Terminated contractor. Contractor forwarded letter indicating there inability to implement the works. | Flagstaff | 234 | 6 | 1 | 1 | 1 | - | 1 | - | 1 | 1 | 1 | 1 | 1 | 1
| GOBIDOLO JSS | 2014-05-22 | 0% | Contractor terminated. Await appointment of replacement contractor | Mqanduli | 334 | 3 | 1 | 1 | 1 |  | 1 | 0 |  | 1 | 0 | 4 | 11 | 3
| Gobinamba SSS | 2014-04-30 | 7% | EIA sorted but resulted in 1,5 month delay. Contractor put on terms and action plan requested due on Thursday, 12 Sept 2014. | Libode | 1104 | 25 | 0 | 1 | 1 |  | 2 |  | 2 | 1 | 0 | 4 | 61 | 0
| HLABATSHANE SSS | 2014-04-29 | 23% | Electrical pole in construction area, talks with Eskom underway, but delaying the completion of platforms. Steel backlog (long lead time) due to steel strike. Delays on the foundation and retaining walls. | Mqanduli | 449 | 20 | 0 | 1 | 1 |  | 2 | 2 |  | 1 | 0 | 5 | 18 | 0
| Jenca JSS | 2014-05-19 | 32% | On schedule | Tsolo | Actual=185, Planned=650 | 21 | 1 | 1 | 1 |  | 0 |  | 1 | 1 | 1 | 4 | 20 | 7
| Kwandumiso SPS | 2014-04-30 | 37% | Project on schedule | Lusikisiki | 270 actual | 7 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 3 | 6 | 6
| Langeni SPS | 2014-04-29 | 60% | Ahead of schedule by half a month | Libode | Actual=153, Planned=174 | 7 | 1 | 1 | 1 |  | 0 |  | 1 | 1 | 0 | 4 | 10 | 7
| LOWER NGCOLOKENI JSS | 2014-05-21 | 27% | Contractor ahead of schedule. | Qumbu | 152 | 6 | 2 | 1 | 1 |  | 1 | 1 |  | 1 | 0 | 4 | 6 | 6
| LOWER TYIRA JSS | 2014-06-24 | 13% | Contractor on schedule. | Qumbu | 300 | 3 | 2 | 1 | 1 |  | 1 | 1 |  | 1 | 0 | 4 | 11 | 6
| Lubala SPS | 2014-04-30 | 18% | Project behind scheduel, contractor issued with a notice of default | Lusikisiki | 232 actual | 7 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 4 | 4 | 3
| Lucingweni JSS | 2014-05-19 | 52% | Contractor ahead of schedule. | Mthatha | Actual=335, Planned=515 | 12 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | - | 4 | 10 | 7
| LUXENI JSS | 2014-05-27 | 17% | Contractor replaced his full team to ensure better perfromance. The contractror is monitored to ensure they keep to milestone dates. | Qumbu | 160 | 5 | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 0 | 4 | 6 | 6
| Mali SPS | 2014-08-28 | 7% | Contractor on target with site handove done on 28 August 2014. | Flagstaff | 557 | 14 | 1 | 1 | 1 | - | 1 | - | 1 | 1 | 1 | 1 | 1 | 1
| Mangala SSS | In Procurement | 0% | Still to appoint Contractor | Libode | Actual=630, Planned=636 | 25 | 0 | 1 | 0 |  | 1 |  | 2 | 1 | 1 | 4 | 20 | 0
| Mangena SPS | 2014-05-22 | 17% | Project behind schedule | Lusikisiki | 297 actual | 9 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 3 | 10 | 4
| Mfundweni JPS | 2014-05-14 | 31% | Contractor is accelerating the works but their platforms were cut & filled incorrectly and they had to redo them hence the delay. | Libode | 182/309 | 9 | 1 | 1 | 1 |  | 1 |  | 1 | 1 |  | 4 | 10 | 6
| Mkumbi JSS | 2014-06-22 | 31% | On schedule | Flagstaff | 160 | 6 | 1 | 1 | 1 | - | 1 | - | 1 | 1 | - | 1 | 1 | 1
| Mkumeni JSS | 2014-05-27 | 16% | Contractor behind schedule. Contractor progress being monitored. | Flagstaff | 192 | 6 | 1 | 1 | 1 | - | 1 | - | 1 | 1 | 1 | 1 | 1 | 1
| Mvume Springs SPS | 2014-04-29 | 20% | Contractor started late on site. Contractor delayed on earthworks awaiting imported filling material lab results and industrial strike. Contractor put on terms and action plan due on Thursday, 11 Sept 2014 | Port St Johns | 146 | 9 | 1 | 1 | 1 |  | 0 |  | 1 | 1 | 0 | 3 | 13 | 2
| Mxhume JSS | 2014-06-25 | 8% | Project behind schedule due to Eskom line deviation , 7 blocks are affected | Lusikisiki | 357 actual ,1000 (Planned) | 25 | 0 | 1 | 2 |  | 2 |  | 2 | 1 | 1 | 5 | 20 | 0
| Mzuzile | 2014-05-27 | 25% | Contractor on target | Qumbu | 161/183 | 3 | 0 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 4 | 12 | 0
| Ndakana | 2014-07-14 | 4% | Contractor put on terms. Progress poor. Vehicles/trucks/ mechanical plant experiencing difficulties to access the site, suppliers refuse to do deliveries to the site. | Qumbu | 127/127 | 7 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 4 | 12 | 6
| Ndimbaneni SPS | 2014-05-21 | 29% | Project ahead of schedule | Lusikisiki | 357 actual | 14 | 2 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 4 | 10 | 3
| NGCENDUNA JSS | 2014-07-23 | 5% | Access to site very bad -Batching concrete on site, Procure more labour, more plant, extra working hours. | Mqanduli | 661 | 11 | 2 | 1 | 1 |  | 0 | 1 |  | 1 | 1 | 4 | 21 | 6
| Nkozo JSS | 2014-06-24 | 8% | Project on schedule | Lusikisiki | 470 actual | 16 | 2 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 4 | 12 ( existing) | 3
| NXANXADI JSS | 2014-05-27 | 17% | Contractor is 3 weeks behind the scheduled time. Contractor is put on terms and monitored closely. | Qumbu | 220 | 6 | 2 | 1 | 1 |  | 1 | 1 |  | 1 | 0 | 4 | 8 | 6
| Pondolwendlovu SSS | 2014-05-05 | 14% | Contractor’s pace is improving after being put on terms but all efforts are being put in place to increase pace of works. | Libode | 358/880 | 25 | 0 | 1 | 1 |  | 1 |  | 1 | 1 |  | 4 | 13 | 0
| Sinolwazi SSS | 2014-07-29 | 6% | Contractor 3 weeks behind schedule and recovery schedule received. Performance being closely monitored. | Mthatha | Actual=701, Planned=1000 | 26 | 0 | 1 | 1 |  | 2 |  | 2 | 1 | 1 | 4 | 30 | 0
| Sizwe | 2014-05-26 | 7% | Contractor put on terms. Progress poor | Qumbu | 154/158 | 7 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 4 | 17 | 6
| Smuts Ndamase SSS | 2014-06-24 | 11% | On Schedule. | Libode | 1079 | 27 | 0 | 1 | 1 |  | 2 |  | 1 | 1 | 0 | 5 | 11 | 0
| Taleni SPS | 2014-07-23 | 8% | Project on schedule with one month in construction | Libode | 326 actual | 9 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 4 | 10 | 6
| THWALUPHAHLA JSS | 2014-06-24 | 9% | Contractor is behind schedule – Employed a new site agent to improve site supervision. Contractor is closely monitored. | Mqanduli | 329 | 5 | 1 | 1 | 1 |  | 0 | 1 |  | 1 | 0 | 4 | 11 | 3
| Tobintetho SPS | 2014-05-13 | 16% | Terminated contractor. Contractor forwarded letter indicating there inability to implement the works. | Flagstaff | 218 | 6 | 1 | 1 | 1 | - | 1 | - | 1 | 1 | - | 1 | 1 | 1
| Tyityane SPS | 2014-04-29 | 30% | Contractor delayed due to relocation of grave and industrial strike. Contractor brought extra resources on the project and progressing well. | Port St Johns | 377 | 9 | 2 | 1 | 1 |  | 0 |  | 1 | 1 | 0 | 4 | 7 | 6
| Victor Poto SSS | 2014-04-30 | 7% | Contractor started late on site. Contractor delayed on earthworks awaiting imported filling material lab results and industrial strike. Contractor progressing slow. Contractor put on terms and action plan expected on Thursday 11 Sept 2014. | Libode | 731 | 27 | 0 | 1 | 1 |  | 2 |  | 2 | 1 | 0 | 5 | 16 | 0
| Waban SSS | 2014-06-25 | 9% | Contractor experience delays in earthworks due to relocation of existing Eskom line crossing the school. Escalate to DBE to engage with Eskom at their higher level. | Libode | 771 | 25 | 0 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 4 | 44 | 0
| Zamekile JPS | 2014-05-22 | 20% | Delays from the contractor. The contractor put on terms and action plan to be submitted by Thursday, 11 Sept 2014. | Flagstaff | 234 | 7 | 1 | 1 | 1 | - | 1 | - | 1 | 1 | - | 1 | 1 | 1
| Zamilizwe | 2014-05-27 | 15% | Contractor progress behind target. Delayed by imported material laboratory test results. | Qumbu | 214/208 | 7 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 4 | 17 | 6
| Zamukulungisa | In Procurement |  |  | Qumbu | 177/172 | 7 | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 0 | 17 | 6
| Zanokhanyo SSS | 2014-06-26 | 10% | Contractor behind schedule though is recovering. Issues of logistics of plant and materials problematic to contractor. | Libode | 525 | 15 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | - | 1 | 1 | 1
| Zibungu SSS | 2014-07-01 | 15% | Contractor experience delays in earthworks due to relocation of existing Eskom line crossing the school. Escalate to DBE to engage with Eskom at their higher level. | Libode | 608 | 24 | 0 | 1 | 1 |  | 1 |  | 1 | 1 | 0 | 5 | 16 | 0
| Dakhile | 2012-01-20 | 100% FC | Final Completion achieved on 18 October 2013 | Lusikisiki | 142
| Dikiso | 2012-01-20 | 100% PC | At Works Completion stage |  | 190
| Dumakude | 2012-01-20 | 100% FC | Final Completion achieved on 7 February 2014 | Lusikisiki | 260
| Dumile | 2012-01-20 | 100% FC | Final Completion achieved on 23 June 2014 |  | 175
| Eludikidi | 2012-01-20 | 100% WC | In Defects liabilty period with due date for completion on 18 August 2014 |  | 460
| Gcinizizwe SPS | 2012-01-20 | 100% FC | Final Completion achieved on 21 January 2014
| Goso | 2012-01-20 | 100% WC | In Defects liabilty period with due date for completion on 21 August 2014 |  | 190
| Gqweza SPS | 2012-01-20 | 100% FC | Final Completion achieved on 4 June 2014
| Gungubele SPS | 2012-01-20 | 100% FC | Final Completion achieved on 21 January 2014 |  | 691
| Jonguxolo JSS | 2012-01-20 | 100% FC | Final Completion achieved on 30 April 2014 |  | 348
| Kwenxura | 2012-01-20 | 100% WC | In defect liability period with snags to be completed before final completion achieved
| Kwezilethu | 2012-01-20 | 100% FC | Final Completion achieved on 1 April 2014 | Mthatha | 163
| Lower Mpako | 2012-01-20 | 100% PC | At Works Completion stage | Mthatha | 414
| Ludeke SPS | 2012-01-20 | 100% FC | Final Completion achieved on 27 Feb 2014 |  | 161
| Madwaleni SP | 2012-01-20 | 100% FC | Final Completion achieved on 11 March 2014 |  | 322
| Mahahane SP | 2012-01-20 | 100% FC | Final Completion achieved on 5 May 2014 |  | 300
| Mandlobe | 2012-01-20 | 100% WC | In defects liability stage with Final Completion due now. | Lusikisiki | 260
| Manzabila SPS | 2012-01-20 | 100% FC | Final Completion achieved on 4 June 2014
| Maphindela SPS | 2012-01-20 | 100% FC | Final Completion achieved on 23 May 2014 |  | 331
| Maqolo SPS | 2012-01-20 | 100% FC | Final Completion achieved on 21 January 2014 |  | 160
| Mazama | 2012-01-20 | 100% WC | In defects liability stage with Final Completion due now.
| Mceteni SPS | 2012-01-20 | 100% FC | Final Completion achieved on 21 May 2014
| Mdavuza | 2012-01-20 | 100% FC | Final Completion achieved on 23 June 2014 |  | 188
| Mpatiswa | 2012-01-20 | 100% FC | Final Completion achieved on 11 March 2014 |  | 213
| Mqokelweni | 2012-01-20 | 100% FC | Final Completion achieved on 3 June 2014 |  | 130
| Mseleni SPS | 2012-01-20 | 100% FC | Final Completion achieved on 23 May 2014
| Ndlovayiphatwa | 2012-01-20 | 100% FC | Final Completion achieved on 23 June 2014
| Ndluzula JPS | 2012-01-20 | 100% FC | Final Completion achieved on 30 April 2014
| Ngidini SPS | 2012-01-20 | 100% FC | Final Completion achieved on 21 January 2014
| Nginza | 2012-01-20 | 100% PC | At Works Completion stage | Mthatha | 147
| Nkonkoni SPS | 2012-01-20 | 100% FC | Final Completion achieved on 9 May 2014 |  | 242
| Nobantu | 2012-01-20 | 100% WC | In defects liability period with Final Completion due now. | Mthatha | 211
| Nogaya | 2012-01-20 | 100% WC | In defects liability period with Final Completion due now. |  | 190
| Nomandla SPS | 2012-01-20 | 100% FC | Final Completion achieved on 30 April 2014
| Notsolo | 2012-01-20 | 100% FC | Final Completion achieved on 23 June 2014
| Ntsonyini JSS | 2012-01-20 | 100% FC | Final Completion achieved on 30 April 2014 |  | 566
| Qaka JPS | 2012-01-20 | 100% FC | Final Completion achieved on 30 April 2014
| Sidanda SPS | 2012-01-20 | 100% FC | Final Completion achieved on 27 June 2014 |  | 436
| Sizane | 2012-01-20 | 100% WC | In defects liability period with Final Completion due now. |  | 286
| Sizwe JPS | 2012-01-20 | 100% FC | Final Completion achieved on 27 June 2014
| Sompa SPS | 2012-01-20 | 100% PC | At Works Completion stage |  | 119
| Tembeni SP | 2012-01-20 | 100% FC | Final Completion achieved on 25 February 2014 |  | 221
| Thabatha | 2012-01-20 | 100% FC | Final Completion achieved on 18 October 2013 | Lusikisiki | 195
| Tshantshala SP | 2012-01-20 | 100% FC | Final Completion achieved on 21 May 2014 |  | 121
| Upper Mbange | 2012-01-20 | 100% WC | In defects liability period with Final Completion due now. |  | 206
| Vulindlela | 2012-01-20 | 100% FC | Final Completion achieved on 21 January 2013 | Mthatha | 271
| Vuyani SPS | 2012-01-20 | 100% FC | Final Completion achieved on 9 April 2014
| Welese | 2012-01-20 | 100% WC | In defects liability period with Final Completion due now. |  | 465
| Zingisile | 2012-01-20 | 100% WC | In defects liability period with Final Completion due now. |  | 150