## PROJECT LIST 2015-16 rev 00
[9 empty] | Directorate : Physical Resources and Facilities Planning | [7 empty] | GRAND TOTAL |  | 7695414817.7551 |  |  | 561870754.2237 | 1105968400.8083 | 1323305249.7739 | 1433203965.1132 | 1506704600.563 | 1185113057.3451 | 814080427.9084 | 433599322.2056 | 453322576.8023 | 323525649.1132 | 371074433.9053
[18 empty] | Substitution of Unsafe Structures |  |  |  | 160667163 | 197535950.2423 | 196129730.5494 | 164717461.4987 | 577201286.9757 | 323702098.4232 | 209940609.213 | 67850440.2495 | 36312086.5657 | 25333946.0774 | 26833615.724
[9 empty] | PROJECT LIST FOR 2015/2016 - Rev 00 | [8 empty] | New Schools |  |  |  | 97443580 | 131784707.921 | 303405482.9581 | 418706069.2922 | 195605191.7245 | 153971872.6225 | 148141240.7142 | 54534893.1677 | 40248659.3168 | 9926660.6392 | 9178328.9666
[18 empty] | Special Schools |  |  |  | 40078000 | 135930610 | 65777390 | 55380373.9837 | 0 | 2469950.4065 | 0 | 2840442.9675 | 0 | 3266509.4126 | 0
[18 empty] | Special Projects |  |  |  | 75882446.66 | 69849921.3826 | 76347434.5326 | 50114896.5602 | 54722192.7379 | 59797389.8801 | 66026254.5801 | 72172690.599 | 79676867.2605 | 87120378.0767 | 96162832.5077
[18 empty] | Boarding Schools |  |  |  | 13464000 | 146342918 | 111046150 | 13219100 | 0 | 2011137.5 | 0 | 2312808.125 | 0 | 2659729.3437 | 0
[18 empty] | Dinaledi Schools |  |  |  | 1832203 | 3000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | Technical Schools |  |  |  | 25600000 | 31870460 | 25100000 | 23386751.7073 | 116000 | 446764.4634 | 133400 | 513779.1329 | 153410 | 590846.0029 | 176421.5
[18 empty] | Storm Damaged Schools |  |  |  | 19596108.912 | 10987629.5964 | 21709254.4459 | 185134.4 | 193214.4125 | 212904.56 | 222196.5744 | 244840.244 | 255526.0606 | 281566.2806 | 293854.9697
[18 empty] | Grade R Schools |  |  |  | 2400092.604 | 27805471.8906 | 0 | 338413.0572 | 5815424.3795 | 17753484.9918 | 4749783.2633 | 168006.4823 | 120004.6302 | 51601.991 | 138005.3247
[18 empty] | Upgrades & Additions |  |  |  | 11700000 | 78052802.7666 | 190953669.2493 | 543159173.5263 | 486367616.6491 | 388866636.3278 | 152936331.6564 | 81976151.9725 | 102932415.6309 | 22266993.7048 | 57425056.168
[18 empty] | Water & Sanitation |  |  |  | 1856729.0477 | 25972047.5275 | 303187.5 | 318346.875 | 334264.2188 | 350977.4297 | 368526.3012 | 386952.6162 | 406300.247 | 426615.2594 | 447946.0224
[18 empty] | Maintenance |  |  |  | 36415715 | 110408355 | 86420000 | 91951600 | 98158200 | 105450160 | 112571949 | 120941275.09 | 129114281.6523 | 138721342.0966 | 148102036.3268
[18 empty] | Refurbishment and Renovations | Refurbishment and Renovations |  |  | 3999998 | 136427526.4812 | 243112950.5384 | 71726644.2126 | 88191209.4651 | 130079680.7401 | 118990136.6058 | 29657041.5588 | 64103025.4382 | 32879460.2283 | 32316336.3955
[18 empty] | Old Final Accounts |  |  |  | 70934718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 561870754.2237 | 1105968400.8083 | 1323305249.7739 | 1433203965.1132 | 1506704600.563 | 1185113057.3451 | 814080427.9084 | 433599322.2056 | 453322576.8023 | 323525649.1132 | 371074433.9053
No. | MDoE PROJECT ID No. | PROJECT NAME | TYPE | EMIS | FUNDING SOURCE | ECONOMIC CLASSIFICATION | DISTRICT | CIRCUIT | MUNICIPALITY | COMPREHENSIVE RURAL DEVELOPMENT PROGRAMME | PROGRAMMES | SUB-PROGRAMME |  | TENDER PROJECT NUMBER | PROJECT DESCRIPTION | START DATE | END DATE | COMMITMENT CATEGORY | EST PROJECT VALUE |  |  | MTEF ESTIMATE 2014 / 2015 | MTEF ESTIMATE 2015 / 2016 | MTEF ESTIMATE 2016 / 2017 | MTEF ESTIMATE 2017 / 2018 | MTEF ESTIMATE 2018 / 2019 | MTEF ESTIMATE 2019 / 2020 | MTEF ESTIMATE 2020 / 2021 | MTEF ESTIMATE 2021 / 2022 | MTEF ESTIMATE 2022 / 2023 | MTEF ESTIMATE 2023 / 2024 | MTEF ESTIMATE 2024/ 2025
[12 empty] | PROJECT CLASSIFICATION | PAYMENT CLASSIFICATION | [6 empty] | R0LL OVER BUDGET | Prev Expenditure
1 | ALL/00/001/11-12-ES | Temporary Accomodation (Mobile Classrooms) ex Abacus | All | All | Equitable Share (ES) | Capital Assets | All | All | All |  | New & Replacement Schools | Special Projects | Public Ordinary Schools |  | Movable Classrooms | 2011-09-01 | 2014-08-30 | A | TBA |  | 8000000 | 4212000 | 20000000 | 22000000 | 24000000 | 26400000 | 29040000 | 31944000 | 35138400 | 38652240 | 42517464 | 46769210.4
2 | GSD/18/001/13-14-EIG | Ezakheni Boarding Phase 2 | BS | 800035528 | Equitable Share (ES) | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | CRDP | Upgrades & Additions | Boarding Schools | Public Ordinary Schools |  | CRDP: Construction of Grade R Centres and Phase 2 Scope | 2014-04-01 | 2015-12-31 | A | 69237168 |  | 4000000 | 13464000 | 55773168 | 0 | 350000 | 0 | 402500 | 0 | 462875 | 0 | 532306.25 | 0
3 | EHL/09/001/14-15-EIG | Fish Mahlalela | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of a Grade R Centre, 16 Classrooms, Administration Block, Library, Computer Centre, School Hall, 24 Toilets ,Fence, Electricity, Water, Kitchen, Ramps and Rails, 3 sports grounds and car park. | 2016-04-01 | 2017-06-30 | C | 38000000 |  | 0 | 0 | 0 | 0 | 1900000 | 20000000 | 16100000 | 0 | 308943.0894 | 0 | 355284.5528 | 0
4 |  | Huttington | S | New | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela |  | Bushbuckridge | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 15 classrooms, administration block, laboratory, library, computer centre, school hall. 22 toilets, fence, electricity, water, kitchen, ramps ans rails, 3 sports grounds, and car park. | 2016-04-01 | 2017-06-30 | B | 36000000 |  | 0 | 0 | 1800000 | 20200000 | 14000000 |  | 292682.9268 |  | 336585.3659 |  | 387073.1707
5 |  | Nduma | P | 800035483 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of a Grade R Centre, 10 Classrooms, Administration Block, Library, Computer Centre, School Hall, 14 Toilets ,Fence, Electricity, Water, Kitchen, Ramps and Rails, 2 sports grounds and car park. |  |  | C | 27450501.4974 |  |  | 0 | 0 | 0 | 1935260.3556 | 24142716.067 | 1372525.0749 | 0 | 274505.015 | 0 | 315680.7672 | 0
6 |  | Lehlogonolo | P | 80003527 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Maviljan | Bushbuckridge | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of a Grade R Centre, 12 Classrooms |  |  | C | 11092397.89 |  |  | 0 | 0 | 0 | 782014.0512 | 10310383.8388 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Moriting | P | 800035497 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Casteel | Bushbuckridge | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of a Grade R Centre |  |  | C | 2400092.604 |  |  | 0 | 0 | 0 | 169206.5286 | 2230886.0754 | 0 | 0 | 0 | 0 | 0 | 0
8 | BOH/05/001/16-17-EIG | JB Khoza | P | 800035484 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | CRDP - Construct 14 Classrooms, Administartion block, library, computer centre, school hall, 22 toilets, kitchen, ramps and rails, fence, electricity, water, 3 sports grounds and car park. | 2016-04-01 | 2017-03-30 | B | 34000000 |  | 0 | 0 | 1700000 | 32300000 | 0 | 276422.7642 |  | 317886.1789 |  | 365569.1057 |  | 420404.4715
9 | EHL/02/001/12-13-EIG | Ebuhleni (Phase 2) | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Insikazi | Mbombela |  | New & Replacement Schools | New Schools | Public Ordinary Schools | PW/508/07/MP | Construct 16 Classrooms, Administration block, Library, Computer Centre, School Hall, 24Toilets, Fence, Electricity,Water, Kitchen, Ramps and Rails | 2014-01-20 | 2015-06-30 | A | 39463000 |  | 12000000 | 0 | 28348000 | 11115000 | 0 | 394630 | 0 | 453824.5 | 0 | 521898.175 | 0 | 600182.9012
10 | EHL/03/001/14-16-EIG | Langeloop | S | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construct 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | 2016-04-01 | 2017-06-30 | C | 46000000 |  | 0 | 0 | 0 | 2300000 | 24600000 | 19100000 | 0 | 373983.7398 | 0 | 430081.3008 | 0 | 494593.4959
11 | EHL/07/001/14-16-EIG | Mbombela | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mbombela | Mbombela |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construct 24 Classrooms, Administration block, library, computer centre, School Hall, 36 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | 2016-04-01 | 2017-06-30 | C | 42000000 |  | 0 | 0 | 0 | 0 | 2300000 | 24600000 | 15100000 | 0 | 341463.4146 | 0 | 392682.9268 | 0
12 | NKA/12/001/12-13-EIG | Middelburg | C | 800014274 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Middelburg 2 | Steve Tshwete |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools | PWRT/1495/10/MP | Demolish 39 classrooms and construct 39 classrooms. | 2014-06-01 | 2015-05-30 | A | 42846000 |  | 4252413.82 | 28323000 | 14467000 | 0 | 348341.4634 | 0 | 400592.6829 | 0 | 460681.5854 | 0 | 529783.8232 | 0
13 | EHL/10/001/14-16-EIG | MJ Lushaba | S | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 20 classrooms, administration block, laboratory, library, computer center, school hall, 30 toilets, fence, electricity, water, kitchen, 3 sports grounds and car park. | 2016-04-01 | 2017-06-30 | C | 40000000 |  | 0 | 0 | 0 | 0 | 2000000 | 20400000 | 17600000 |  | 325203.252 |  | 373983.7398 | 0
14 | EHL/10/002/14-16-EIG | Mmoyila | S |  | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 28 classrooms, administration block, laboratory, library, computer centre, school hall. 42toilets, fence, electricity, water, kitchen, ramps / rails, 3sports grounds and car park. | 2016-04-01 | 2017-06-30 | B | 46000000 |  | 0 | 0 | 2300000 | 20000000 | 23700000 |  | 373983.7398 |  | 430081.3008 |  | 494593.4959
15 | EHL/07/001/16-17-EIG | Msholozi | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mbombela | Mbombela |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of Grade R centre, 20 Classrooms, Administration block, library, computer centre, School Hall, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps +rails, 3 Sports Grounds and Car Park. | 2017-04-01 | 2018-06-30 | C | 40000000 |  | 0 | 0 | 0 | 2820000 | 34380000 | 2800000 | 325203.252 | 0 | 373983.7398 | 0 | 430081.3008 | 0
16 | GSD/16/001/16-17-EIG | Nyandeni | P | 800017533 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Stanwest | Lekwa |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Renovations to 22 classrooms, administration block and toilets. Construction of library, computer centre, fence, electricity, water, kitchen, ramps / rails, 3 sports grounds and car park. | 2017-04-01 | 2018-03-30 | C | 25000000 |  | 0 | 0 | 0 | 1250000 | 24700000 | 0 | 203252.0325 | 0 | 233739.8374 | 0 | 268800.813 | 0
17 | GSD/10/001/13-14-EIG | Osizweni | SP | 800017806 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Highveld Ridge East | Govan Mbeki |  | New & Replacement Schools | Special Schools | Special Schools |  | Construction of 8 classrooms, administration block, school hall, 4 workshops, media centre, fence, electricity and water supply. | 2013-07-30 | 2014-10-31 | A | 46786000 |  | 5000000 | 40078000 | 6708000 | 0 | 380373.9837 | 0 | 437430.0813 | 0 | 503044.5935 | 0 | 578501.2825 | 0
18 | EHL/07/001/12-13-EIG | School for the Deaf | SP | - | Equitable Share (ES) | Capital Assets | Ehlanzeni | Mbombela | Mbombela |  | New & Replacement Schools | Special Schools | Special Schools |  | All buildings to be sound proof. Construction of 30 classrooms with supporting facilities, ablution block with 15 toilets, administration block with a staff room for 40 educators, boardroom for 30 people, multi purpose hall with supporting facilities including fitness centre, laboratory, library, e-learning centre, 6 workshops, 3 therapy rooms with offices, counselling room, office for professional nurse with dispensary, 4 sickrooms and 3 toilets inclusive of a toilet for persons with disability, audiology room, art theater, covered walkways, fence, electricity, water, dining hall, car park, garages, hostel cluster with supporting facilities, 2 guest rooms and flats, 6 sports grounds and swimming pool with 2 cloak rooms. | TBA | TBA | B | 250000000 |  | 3000000 | 0 | 129222610 | 65777390 | 55000000 | 0 | 2032520.3252 | 0 | 2337398.374 | 0 | 2688008.1301 | 0
19 | EHL/09/001/15-16-EIG | Silulu | S | 800035304 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | crdp - Planning and Design: Construct 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | 2016-04-01 | 2017-06-30 | B | 48000000 |  | 0 | 0 | 2400000 | 21125000 | 24475000 | 0 | 390243.9024 | 0 | 448780.4878 | 0 | 516097.561 | 0 |  | 15200000 | [24 empty] | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667 | 1266666.6667
20 | EHL/07/003/14-16-EIG | Tekwane North | S | - | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mbombela | Mbombela |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construct 24 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | 2016-04-01 | 2017-06-30 | B | 39000000 |  | 0 | 0 | 1950000 | 22945078 | 14104922 | 0 | 317073.1707 | 0 | 364634.1463 | 0 | 419329.2683 | 0
21 | EHL/07/002/12-13-EIG | Tekwane South | S | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mbombela | Mbombela |  | New & Replacement Schools | New Schools | Public Ordinary Schools | PW/514/07/MP | Construct 24 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | 2013-04-01 | 2014-07-31 | A | 48857000 |  | 13000000 | 36362580 | 2931420 | 0 | 488570 | 0 | 561855.5 | 0 | 646133.825 | 0 | 743053.8987 | 0
22 | GSD/14/001/12-13-EIG | Ubuhle Buzile | S | 800036512 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools | PWRT/1780/11/MP | CRDP: Construction of 28 classrooms, administration block, laboratory, library, computer centre, School Hall, 40Toilets, Fence, Electricity, Watre, Kitchen, ramps / rails, 3 Sports Grounds & Car Park. | 2013-10-01 | 2014-03-31 | A | 45489000 |  | 26687000 | 13809000 | 0 | 369829.2683 | 0 | 425303.6585 |  | 489099.2073 |  | 562464.0884 |  | 646833.7017
23 | NKA/07/001/16-17-EIG | Vezikgono | P | 800035602 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | KwaMhlanga North East | Thembisile Hani | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construct 24 Classroomss, Administration block, library, computer centre, School Hall, 36 Toilets, Fence, Elelctricity, Water, Kitchen, ramps +rails, 3 Sports Grounds and Car Park. | 2016-04-01 | 2017-06-30 | B | 42000000 |  | 0 | 0 | 2961000 | 39039000 | 2520000 | 0 | 420000 | 0 | 483000 | 0 | 555450 | 0
24 | EHL/15/001/14-15-EIG | White River | S | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White River | Mbombela |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construct 28 Classroomss, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Elelctricity, Water, Kitchen, ramps +rails, 3 Sports Grounds and Car Park. | 2015-04-01 | 2016-06-30 | B | 47933162 |  | 0 | 0 | 3379287.921 | 44553874.079 | 2875989.72 | 0 | 479331.62 | 0 | 551231.363 | 0 | 633916.0674 | 0
25 | GSD/14/004/14-15-EIG | Berbice (Phase 2) | P | 800000943 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Grade R Centre, small administration block, computer centre, fence, electrical work, ramps and rails. | 2016-04-01 | 2017-03-30 | B | 8400462 | 9327462 |  | 0 | 856000 | 7123154 | 421308 | 0 | 121951.2195 | 0 | 140243.9024 | 0 | 161280.4878 | 0 |  | 151791.1354 | 252985.2257 | 354179.3159 | 455373.4062 | 556567.4965 | 657761.5867 | 758955.677 | 860149.7673 | 961343.8575 | 1062537.9478 | 1163732.038 | 1264926.1283 | 1366120.2186 | 1467314.3088 | 1568508.3991 | 1669702.4894 | 1770896.5796 | 1872090.6699 | 1973284.7602 | 2074478.8504 | 2175465.3631 | 2136752.1368 | 1978474.2007 | 1820196.2646 | 1661918.3286 | 1503640.3925 | 1345362.4565 | 1187084.5204 | 1028806.5844 | 870528.6483 | 712250.7123 | 553972.7762 | 395694.8401 | 237416.9041 | 79138.968
26 | GSD/08/001/12-13-EIG | Netherlands Park [Wesselton] | S | 800035526 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa |  | New & Replacement Schools | New Schools | Public Ordinary Schools | PWRT/1439/10/MP | Construct 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | 2012-09-05 | 2014-05-30 | A | 44065185 |  | 12311000 | 22915000 | 0 | 358253.5366 | 0 | 411991.5671 |  | 473790.3021 |  | 544858.8475 |  | 626587.6746
27 | NKA/02/001/12-13-EIG | New Coronation [Klarinet] | S | New | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Emalahleni 2 | Emalahleni |  | New & Replacement Schools | New Schools | Public Ordinary Schools | PWRT/1728/11/MP | Construct 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | 2012-09-07 | 2014-05-30 | A | 46644000 |  | 22904000 | 24357000 | 0 | 379219.5122 | 0 | 436102.439 | 0 | 501517.8049 | 0 | 576745.4756 | 0 | 663257.297
28 | NKA/10/001/12-13-EIG | Ramantsho | P | 800019042 | Equitable Share (ES) | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP | Upgrades & Additions | Special Projects | Public Ordinary Schools |  | CRDP - Special Projects: MEDT. Substitution of buildings: 5classroom, administration block, library, computer centre and kitchen. | 2016-04-01 | 2017-03-31 | B | 13139901.4547 |  | 1500000 | 0 | 926363.0526 | 11556543.3294 | 656995.0727 | 0 | 106828.4671 | 0 | 122852.7372 | 0 | 141280.6478 | 0
29 |  | Education Facilities Management System [EFMS] | All | All | Equitable Share (ES) | Capital Assets | All | All | All |  | Maintenance & Repairs | Special Projects | Public Ordinary Schools |  | Infrastructure Management | 2011-09-01 | 2014-09-30 | A | 13791032 |  | 2408731 | 3766232 | 3390225 | 2203646.25 | 2357901.4875 | 2522954.5916 | 2699561.413 | 2888530.712 | 3090727.8618 | 3307078.8121 | 3538574.329 | 3786274.532
30 |  | Ndebele College | TT | - | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | - | Dr JS Moroka | CRDP | Maintenance & Repairs | Maintenance | Public Ordinary Schools |  | Maintenance | 2013-07-01 | 2014-03-31 | A | 16000000 |  | 2000000 | 2000000 | 2200000 | 2420000 | 2662000 | 2928200 | 3221020 | 3543122 | 3897434.2 | 4287177.62 | 4715895.382 | 5187484.9202
31 |  | Programme Management Unit | All | All | Equitable Share (ES) | Capital Assets | All | All | All |  | Maintenance & Repairs | Special Projects | Public Ordinary Schools |  | Infrastructure Management | 2013-05-02 | 2016-04-30 | A | 28000000 |  | 7777778 | 10764443 | 9333333.33 | 672777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 |  | DORA Compensation | All | All | Education Infrastructure Grant (EIG) | Current Paymens | All | All | All |  | Goods & Services | Special Projects | Conditional Grants |  | Infrastructure Management | 2014-04-01 | 2015-03-31 | A | 0 |  | 7777778 | 9487000 | 17200000 | 18576000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 |  | Infrastructure Equipment | All | All | Education Infrastructure Grant (EIG) | Current Paymens | All | All | All |  | Goods & Services | Special Projects | Conditional Grants |  | Infrastructure Functionality Management : Supply of furniture to completed facilities | 2014-04-01 | 2015-03-31 | A | 0 |  | 7777778 | 17807000 | 19000000 | 21000000 | 23100000 | 25410000 | 27951000 | 30746100 | 33820710 | 37202781 | 40923059.1 | 45015365.01
34 | GSD/10/001/12-13-EIG | Highveld Comprehensive | Tec | 800005116 | MST - Technical Recapitalisation | Capital Assets | Gert Sibande | Highveld Ridge East | Albert Luthuli | CRDP | Upgrades & Additions | Technical Schools | Conditional Grants | PWRT/1750/11/MP | CRDP: Construction of 1 new workshop and refurbishment of 1 workshops. | 2014-06-01 | 2015-01-31 | A | 11270460 |  | 3000000 | 3500000 | 7770460 | 0 | 91629.7561 | 0 | 105374.2195 | 0 | 121180.3524 | 0 | 139357.4053 | 0
35 | MPA-RFP 105/10 | Acorns To Oaks Comprehensive (addition to current scope) | S | 800035522 | Equitable Share (ES) | Capital Assets | Bohlabela [Ehlanzeni] | Greenvalley | Bushbuckridge | CRDP | New & Replacement Schools | Special Projects | Public Ordinary Schools | 009/BOH/S/2010-2011-EIG | CRDP: Construction of 18 Classrooms, Administration block, Laboratory, Media Centre, Computer Centre, School Hall, Electricity, Fence, Water, 5 Toilets Blocks | 2012-06-01 | 2014-04-30 | A | 41631558.25 |  |  | 9845771.66 | 0 | 338467.9533 | 0 | 389238.1462 |  | 447623.8682 |  | 514767.4484 |  | 591982.5657
36 | BOH/11/001/13-15-EIG | Mbhandule | S | 800035106 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools | PWRT/1314/10/MP | CRDP: Phase 1 - Construction of 8 classrooms, administration block, fencing, guard house, ablution block, water & electricity. Phase 2 - Construction of 20 classroom, laboratory, library, computer centre, school hall, kitchen, ablution blocks and sports grounds. | 2013-08-01 | 2014-11-30 | A | 42890000 |  | 4885000 | 12800812 | 30089188 | 0 | 348699.187 | 0 | 401004.065 | 0 | 461154.6748 | 0 | 530327.876 | 0
37 | BOH/13/001/12-13-EIG | Sabeka | P | 800035170 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools | PW/413/07/MP | CRDP: Construction of 12 classrooms, administration block, library, computer centre, kitchen, 3 sports grounds and car park on a new site. | 2013-08-14 | 2014-08-31 | A | 26610948 |  | 3000000 | 23732000 | 0 | 216349.1707 | 0 | 248801.5463 |  | 286121.7783 |  | 329040.045 |  | 378396.0518
38 | BOH/02/001/12-13-EIG | Chueu | P | 800034853 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Arthurseat | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools | PWRT/1301/10/MP | CRDP: Construction of 10 classrooms, administration block, 15 toilets, fence, library, Grade R Centre with 4 toilets and fence, 3 sports grounds and car park. | 2013-08-01 | 2014-11-30 | A | 27817974 |  | 3316000 | 24732000 | 3085974 | 0 | 226162.3902 | 0 | 260086.7488 | 0 | 299099.7611 | 0 | 343964.7253 | 0
39 | NKA/15/001/13-14-EIG | Seabe | S | 800020016 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools | PWRT/1741/12/MP | CRDP: Construction of 10 classrooms, administration block,laboratory, library, fence, electricity, water, 16 toilets, kitchen, 3 sports grounds and car park on a new site. | 2013-02-21 | 2014-04-21 | A | 27821822.568 |  | 12912000 | 11603000 | 0 | 226193.6794 | 0 | 260122.7313 | 0 | 299141.141 | 0 | 344012.3122 | 0 | 395614.159
40 | EHA/14/001/13-14-EIG | Hazyview | C | 800029173 | MST - Technical Recapitalisation | Capital Assets | Ehlanzeni | White Hazy | Mbombela |  | Upgrades & Additions | Technical Schools | Conditional Grants |  | Construction of 1 workshop and renovations and refurbishment to 3 other workshops. | 2014-06-01 | 2015-01-31 | A | 11700000 |  | 1200000 | 8100000 | 3600000 | 0 | 95121.9512 | 0 | 109390.2439 | 0 | 125798.7805 | 0 | 144668.5976 | 0
41 |  | FET and MRTT (Backlog Maintenance) | All | All | Education Infrastructure Grant (EIG) | Capital Assets | All | All | All |  | Maintenance & Repairs | Maintenance | Public Ordinary Schools |  | Maintenance | 2013-04-01 | 2016-03-31 | A | 335397875 | 27175715 | 84000000 | 27175715 | 108208355 | 84000000 | 89000000 | 95230000 | 101896100 | 109028827 | 116660844.89 | 124827104.0323 | 133565001.3146 | 142914551.4066
42 | GSD/14/001/13-14-EIG | Cana Combined | C | 800001909 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | CRDP: Construction of a Grade R Center with toilets and fence. | 2014-03-01 | 2014-09-30 | A | 2082108 |  | 2082108 | 0 | 2082108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | BOH/08/003/13-14-EIG | Mugena | S | 800035037 | MST - Dinaledi Grant | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Construction of a laboratory. | 2014-06-01 | 2015-01-31 | A | 2120000 |  | 1900000 | 1832203 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
44 | GSD/18/002/13-14-EIG | Daggakraal | P | 800002345 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | CRDP: Construction of a Grade R Center with toilets and fence. | 2014-03-01 | 2014-09-30 | A | 2683417 |  | 2683417 | 0 | 2683417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | GSD/01/001/13-14-EIG | Esibusisweni | C | 800003954 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | CRDP: Construction of a Grade R Center with toilets and fence. | 2014-03-01 | 2014-09-30 | A | 2201865 |  | 2201865 | 0 | 2201865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | GSD/14/002/13-14-EIG | Kemp Siding | C | 800007476 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | CRDP | Upgrades & Additions | Grade R Centres | Public Ordinary Schools |  | CRDP: Construction of a Grade R Center with toilets and fence. | 2014-03-01 | 2014-09-30 | A | 5027556 |  | 1900000 | 0 | 5027556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | BOH/08/002/13-14-EIG | Matikinya | P | 800035033 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | CRDP: Construction of a Grade R Center with toilets and fence. | 2014-03-01 | 2014-09-30 | A | 2952627 |  | 1900000 | 0 | 2952627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | BOH/08/004/13-14-EIG | Nwa Macingele | P | 800035039 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | CRDP: Construction of a Grade R Center with toilets and fence. | 2014-03-01 | 2014-09-30 | A | 2617031 |  | 1900000 | 0 | 2617031 | 0 | 0
49 | NKA/05/002/13-14-EIG | Sinetjhudu | P | 800021246 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | CRDP: Construction of a Grade R Center with toilets and fence. | 2014-03-01 | 2014-09-30 | A | 2502998 |  | 1900000 | 0 | 2502998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | GSD/18/004/13-14-EIG | Sizenzele | P | 800021709 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | CRDP: Construction of a Grade R Center with toilets and fence. | 2014-03-01 | 2014-09-30 | A | 2568937 |  | 1900000 | 0 | 2568937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | NKA/05/003/13-14-EIG | Somlingo | P | 800022061 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | CRDP: Construction of a Grade R Center with toilets and fence. | 2014-03-01 | 2014-09-30 | A | 2573719 |  | 1900000 | 0 | 2573719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | BOH/11/001/14-16-EIG | Chayaza | S | 800035091 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 28 Classrooms, administration block, laboratory, library, computer centre, 42 toilets, Scholl Hall, Electricity, Water, 3 Sports Grounds & Car Park. | 2016-04-01 | 2017-03-30 | B | 45000000 |  | 0 | 0 | 2300000 | 20000000 | 22700000 | 0 | 450000 | 0 | 517500 | 0 | 595125 | 0
53 | EHL/11/001/15-17-EIG | Chief Fana Dlamini | S | 800005611 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkululeko | Mbombela |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of 24 Classrooms, administration block, laboratory, library, computer centre, 30 toilets, School Hall, Elelctricity, Water, 3 Sports Grounds & Car Park. | 2016-04-01 | 2017-03-30 | C | 42000000 |  | 0 | 0 | 0 | 2961000 | 23439000 | 15600000 | 0 | 420000 | 0 | 483000 | 0 | 555450
54 | EHL/01/001-13-15-EIG | Emjindini | S | 800003574 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Barberton | Umjindi |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction of 7 classrooms, 10 toilets, school hall, kitchen, ramps and rails, 3 sports grounds and car park. | 2015-04-01 | 2016-03-30 | B | 9767160.9 |  | 0 | 0 | 688584.8434 | 9078576.0565 | 0 | 101514.6248 | 0 | 116741.8185 | 0 | 134253.0912 | 0 | 154391.0549 |  | 6938334.3929 | 54765.2381 | 164295.7142 | 273826.1904 | 383356.6665 | 492887.1427 | 602417.6188 | 711948.095 | 821478.5711 | 931009.0473 | 1040539.5234 | 1150069.9995 | 1259600.4757 | 1369130.9518 | 1478661.428 | 1588191.9041 | 1697722.3803 | 1807252.8564 | 1916783.3326 | 2026313.8087 | 2135844.2849 | 2139088.0721 | 1970144.3338 | 1798827.4352 | 1627510.5366 | 1456193.638 | 1284876.7394 | 1113559.8408 | 942242.9422 | 770926.0437 | 599609.1451 | 428292.2465 | 256975.3479 | 85658.4493
55 | BOH/13/001-13-15-EIG | Eric Nxumalo | S | 800035151 | MST - Technical Recapitalisation | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Technical Schools | Conditional Grants |  | CRDP: Planning and Design: Refurbishment of workshops to comply with safety standards. | 2016-05-01 | 2017-03-31 | C | 10800000 |  | 0 | 0 | 0 | 10800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | GSD/17/001/13-14-EIG | Hlelimfundo | S | 800035485 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Planning and Design of 6 classrooms, laboratory, library, computer centre, upgrade electricity, ramps and rails, kitchen, school hall, 3 sports grounds and car park. | 2015-06-01 | 2016-05-31 | A | 12486148.4 |  | 0 | 0 | 11861841 | 624307.42 | 0 | 124861.484 | 0 | 143590.7066 | 0 | 165129.3126 | 0 | 189898.7095
57 | EHL/03/002/13-15-EIG | Ilanga [Bosfontein] | S | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 12 classrooms, administration block, laboratory, library, computer centre, school hall, 18 toilets, fence, electricity, water, kitchen, ramps and rails, 3 sports ground and car park. | 2016-04-01 | 2017-06-30 | B | 21177012.78 |  | 0 | 0 | 500000 | 16177013 | 4500000 | 0 | 211770.1278 | 0 | 243535.647 | 0 | 280065.994 | 0
58 | NKA/10/001/13-16-EIG | Lehlabile | S | 800010041 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Planning and Design: Construction of administration block, computer centre, kitchen, laboratory, 12 toilets, School Hall, upgrade electricity, 3 Sports Grounds and Car Park and renovations of 16 classrooms. | 2013-08-01 | 2015-03-31 | C | 17361941.0002 |  | 0 | 0 | 0 | 1224016.8405 | 15096207.6997 | 1041716.46 | 0 | 173619.41 | 0 | 199662.3215 | 0 | 229611.6697
59 | GSD/17/002/13-14-EIG | Louwra | P | 800010702 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Supply of electricity and renovation of a house in the school yard for conversion to an administration block or kitchen and storeroom and fence. | 2013-08-01 | 2014-12-31 | A | 1800000 |  | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | GSD/18/001/13-15-EIG | Nalithuba | S | 800016238 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction of school hall, library, computer centre, kitchen, laboratory, sports grounds and car park. | 2015-06-01 | 2016-05-31 | A | 20000000 |  | 0 | 0 | 17175000 | 2825000 | 0
61 | BOH/05/001/14-16-EIG | Ndlamakhosi | S | 800034951 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Planning and Design - Construction of 2 classrooms, laboratory, library, computer centre, 4 toilets, electricity, ramps and rails, 3 sports grounds and car park. Substitution of 10 pit toilets. | 2014-04-01 | 2016-03-31 | C | 7130098.08 |  | 0 | 0 | 0 | 356505 | 6773593 | 0 | 71300.9808 | 0 | 81996.1279 | 0 | 94295.5471 | 0
62 | GSD/18/001/13-15-EIG | Seme | S | 800020263 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of a computer centre, kitchen, ramps and rails, upgrade of electricity, school hall and laboratory. | 2013-08-01 | 2015-12-31 | B | 20000000 |  | 0 | 0 | 1410000 | 17390000 | 1200000 | 0 | 200000 | 0 | 230000 | 0 | 264500 | 0
63 | EHL/10/001/13-15-EIG | Shayaza | S | 800020495 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Planning and Design: Addition of 10 classrooms, Library, Computer Centre, School Hall, 16 toilets, Fence, Kitchen, 3 Sports Grounds, Car Park and renovation of 18 Classrooms | 2013-08-01 | 2015-03-31 | C | 26703946.1744 |  | 0 | 0 | 0 | 1882628.2053 | 23486120.6604 | 1335197.3087 | 0 | 133519.7309 | 0 | 153547.6905 | 0 | 176579.8441
64 | EHL/03/001/13-14-EIG | Shongwe Boarding School | BS | 800020578 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | CRDP | Upgrades & Additions | Boarding Schools | Public Ordinary Schools |  | CRDP: Construction of a Grade R Center with toilets and fence, addition of hostels and upgrading of existing hostels and toilets. | 2013-08-01 | 2014-09-30 | A | 214485000 |  | 5000000 | 0 | 90569750 | 111046150 | 12869100 | 0 | 1608637.5 | 0 | 1849933.125 | 0 | 2127423.0937 | 0
65 | NKA/09/001/13-15-EIG | Hlalakahle | S | 800005223 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Libangeni | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of administration block, computer centre, School Hall, kitchen, laboratory, 12 toilets, 3 Sports Grounds and Car Park and renovation of 16 classrooms. | 2013-08-01 | 2014-12-31 | B | 20000000 |  | 0 | 0 | 935000 | 16823000 | 2242000 | 0 | 200000 | 0 | 230000 | 0 | 264500 | 0
66 | NKA/11/001/13-14-EIG | Hoërskool Middelburg | S | 800005876 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Middelburg 1 | Steve Tshwete |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Completion of the renovations of the school. | 2015-04-01 | 2016-03-31 | A | 15000000 |  | Term Contractor | 0 | 15000000 | 0 | 282460 | 0 | 324829 | 0 | 373553.35 | 0 | 429586.3525 | 0
67 | EHL/09/001/14-15-EIG | Mehlobomvu | S | 800013961 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools | - | CRDP - Planning and Design: Renovation of 16 Classrooms. Construction of additional 4 classrooms and administration block, laboratory, library, computer centre, school hall, kitchen, 3 sports grounds and car park. | 2014-06-01 | 2015-03-31 | B | 20000000 |  | 0 | 0 | 1800000 | 17200000 | 1000000 |  | 200000 | 0 | 230000 | 0 | 264500 | 0
68 | NKA/08/002/14-15-EIG | Mkhanyo | P | 800013441 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | KwaMhlanga South West | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools | - | CRDP - Planning and Design: Construction of a Grade R centre, 8 classrooms, library, computer centre, fence and kitchen. | 2014-10-01 | 2016-06-30 | B | 14674714.0236 |  | 0 | 0 | 1320724.2621 | 10978989.7614 | 2375000 |  | 146747.1402 | 0 | 168759.2113 | 0 | 194073.093 | 0
69 | BOH/04/002/13-14-EIG | Moses Mnisi | S | 800034921 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP - Planning and Design: Substitution of unsafe 28 Crms, administration block, laboratory, library, computer centre, School Hall, kitchen, 3 Sports Grounds and Car Park. | 2014-02-01 | 2015-02-28 | A | 52597826 |  | 3612000 | 34161000 | 15395826 | 0 | 525978.26 | 0 | 604874.999 | 0 | 695606.2488 | 0 | 799947.1862 | 0
70 | BOH/05/001/13-14-EIG | Mpisana | P | 8000034949 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP: Demolish existing classrooms and construct 12 classrooms and 18 toilets, administration block, library, kitchen, school hall, computer centre, ramps and rails, 3 sports grounds and car park. | 2014-02-01 | 2015-02-28 | A | 36091802 |  | 3547000 | 25315351 | 12259717 | 0 | 0
71 | BOH/06/001/14-15-EIG | Mugidi | P | 800034979 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Greenvalley | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP - Planning and Design: Demolition of 10 classrooms and the construction of 10 classrooms, administration block, library, kitchen, computer centre, ramps and rails, 3 sports grounds and car park. | 2016-04-01 | 2017-06-30 | B | 15025620.72 |  | 0 | 0 | 751281.036 | 14274339.684 | 0 | 150256.2072 |  | 172794.6383 |  | 198713.834 |  | 228520.9091
72 |  | Thathakusa | P | 800022996 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning, design and construction: 2 Classrooms | 2014-04-01 | 2015-03-30 | A | 1502788.785 |  | 0 | 0 | 1502788.785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | NKA/16/001/14-16-EIG | Sibonelo | P | 800020685 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP - Planning and Design: Replace 10 classrooms and renovations of 5 classrooms. Construction of an administration block, library, computer centre, kitchen, ramps and rails, 3 sports grounds and car park. | 2016-04-01 | 2017-06-30 | B | 19986140.3238 |  | 0 | 0 | 1649400 | 17137571.9044 | 1199168.4194 | 0 | 199861.4032 | 0 | 229840.6137 | 0 | 264316.7058 | 0
74 | EHL/08/001/14-15-EIG | Tenteleni | P | 800022780 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mgwenya | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Phase 1 - Construction of a Grade R Centre with toilets and fence, kitchen and library (by Education) Multi-purpose centre (COGTA) Phase 2 - Administration block and upgrade of sports facilities. | 2014-05-05 | 2014-04-03 | A | 24701206.5 |  | 0 | 6000000 | 0 | 0 | 247012.065 | 0 | 284063.8747 | 0 | 326673.456 | 0 | 375674.4744 | 0
75 | NKA/16/001/15-16-EIG | Thabana | P* | 800022830 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP - Planning and Design: Renovation of 2 classrooms and the substitution of 3 classrooms and 10 toilets. Addition of a scaled down administration block, kitchen, computer centre, ramps and rails, 2 sports grounds, car park and library. | 2016-04-01 | 2017-01-31 | B | 14904999.4409 |  | 0 | 0 | 1050802.4606 | 12959897.0138 | 894299.9665 | 0 | 1028444.9614 | 0 | 1182711.7056 | 0 | 1360118.4615 | 0
76 | BOH/08/001/13-14-EIG | Welverdiend | P | 800035047 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Planning and Design - Construction of a Grade R Centre, fence and toilets, 10 classrooms, administration block, library, computer centre, kitchen, 30 toilets, ramps and rails, 3 sports grounds and car park. | 2014-06-01 | 2015/06/31 | A | 18905782.18 |  | 0 | 5000000 | 13905782.18 | 1134346.9308 | 0 | 153705.5462 | 0 | 176761.3781 | 0 | 203275.5848 | 0 | 233766.9225
77 |  | Ehlanzeni and other District Office | CIR | N/A | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Ehlanzeni | Mbombela |  | Maintenance & Repairs | Maintenance | Public Ordinary Schools |  | Refurbishment, maintenance and repairs to 4 district offices. | 2014-06-01 | 2015-03-31 | A | 7240000 |  | 0 | 7240000 | 0 | 0 | 289600 | 0 | 333040 | 0 | 382996 | 0 | 440445.4 | 0
78 | NKA/12/001/15-17-EIG | Aerorand | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Middelburg 2 | Steve Tshwete |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | 2015-05-01 | 2017-03-31 | A | 42000000 |  |  | 0 | 31265000 | 10735000 | 0 | 420000 |  | 483000 |  | 555450 |  | 638767.5
79 | EHL/08/001/14-16-EIG | Mtfophi (Daantjie) | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mgwenya | Mbombela |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of a Grade R centre, 24classrooms, administration block, library, computer centre, scholl hall. 36toilets, fence, electricity, water, kitchen, ramps & rails, 3 sports grounds & car park. | 2014-04-01 | 2016-03-31 | A | 42000000 |  |  | 0 | 35800000 | 6200000 | 0 | 420000 | 0 | 483000 | 0 | 555450 | 0 | 638767.5
80 | EHL/07/002/15-16-EIG | Yinhlelentfo | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White Hazy | Mbombela |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Construction of a Grade R Centre, 16classroom, administration block, library, computer centre, School Hall, 24Toilets, Fence, Electricity, Watre, Kitchen, ramps / rails, 3 Sports Grounds & Car Park. | 2015-04-01 | 2016-12-31 | C | 30000000 |  |  | 0 |  | 1500000 | 28500000 | 0
81 | GSD/03/002/16-17-EIG | Balfour | P | 800000489 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Balfour | Dipaleseng | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 10 classrooms, administration block, library, kitchen, ramps and rails, 15 toilets and the renovations to 14 classrooms, computer centre, 14 toilets, sports grounds and car park. | 2016-04-01 | 2017-12-31 | C | 22000000 |  |  | 0 | 0 | 600000 | 21400000 | 0 | 220000 | 0 | 253000 | 0 | 290950 | 0
82 | EHL/03/002/14-15-EIG | Bukhosibetfu | P | 800001743 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Planning and Design: Renovations of 19 classrooms and the construction of 5 classrooms, library, computer centre, kitchen, ramps and rails, 8 toilets, palisade fence and a skills centre for learners with disability. | 2016-04-01 | 2017-03-31 | B | 18000000 |  |  | 0 | 900000 | 17100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | EHL/10/001/16-17-EIG | Chief Makunyula | C | 800002089 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction 2 Grade R Centres with toilets and fence, 8 classrooms, administration block, library, laboratory, 24 toilets, computer centre, kitchen, ramps and rails, 15 toilets, 3 sports grounds, car park and the renovations to 16 classrooms. | 2016-04-01 | 2017-12-31 | C | 23000000 |  |  | 0 | 0 | 1150000 | 21850000 | 0 | 230000 | 0 | 264500 | 0 | 304175 | 0
84 | NKA/03/002/16-17-EIG | Dunbar | P | 800002964 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Emalahleni 2 | Emalahleni |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction of 14 classrooms, administration block, library, computer centre, kitchen, 22 toilets, ramps and rails, 3 sports grounds and car park. Renovations to 9 existing classrooms and 12 toilets. | 2016-04-01 | 2017-03-31 | C | 26155402.0873 |  |  | 0 | 0 | 1843955.8472 | 22742122.1149 | 1569324.1252 | 0 | 261554.0209 | 0 | 300787.124 | 0 | 345905.1926
85 | NKA/03/001/16-17-EIG | Hlangu-Phala | P | 800005322 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Emalahleni 2 | Emalahleni |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of library, computer centre, upgrade electricity, ramps and rails, kitchen, school hall, 3 sports grounds and car park. Renovations to 25 classrooms and administration block. | 2016-04-01 | 2017-12-31 | C | 19507392.132 |  |  | 0 | 0 | 1375271.1453 | 16961677.4588 | 1170443.5279 | 0 | 195073.9213 | 0 | 224335.0095 | 0 | 257985.2609
86 | GSD/04/001-16-17-EIG | Ikhwezi | P | 800034496 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Bethal | Govan Mbeki |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 1 Grade R center, 12 Classrooms,administration block, library, computer centre, ramps and rails, kitchen, 12 toilets, 3 sports ground, car parking | 2016-04-01 | 2017-12-31 | C | 23737560.2036 |  |  | 0 | 0 | 1673497.9944 | 20639808.597 | 1424253.6122 | 0 | 237375.602 | 0 | 272981.9423 | 0 | 313929.2337
87 |  | Jackie Manana | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande |  | Govan Mbeki |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of Grade R Centre, 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 40 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. | 2014-04-01 | 2016-03-31 | A | 48000000 |  |  | 0 | 16450000 | 31550000 | 0 | 480000 | 0 | 552000 | 0 | 634800 | 0 | 730020
88 | EHL/09/001/16-17-EIG | Kamaqhekeza | P | 800012625 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 8 classrooms, library, computer centre, kitchen, school hall, upgrade electricity, ramps and rails, 20 toilets, 3 sports grounds and car park. Renovation to 16 classrooms and administration block | 2016-04-01 | 2015-12-31 | C | 18000000 |  |  | 0 | 0 | 1269000 | 15651000 | 1080000 | 0 | 180000 | 0 | 207000 | 0 | 238050
89 | EHL/09/005-16-17-EIG | Khula | S | 800007781 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 7 classrooms, library, laboratory, school hall, computer centre, kitchen, ramps and rails, 20 toilets, 3 sports grounds, car park and the renovations to 21 classrooms and 10 toilets. | 2016-04-01 | 2017-12-31 | C | 30000000 |  |  | 0 | 0 | 0 | 2115000 | 26085000 | 1800000 | 0 | 300000 | 0 | 345000 | 0
90 | GSD/13/001/15-16-EIG | Khuphukani | P* | 800007898 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction of a library, computer centre, kitchen, ramps and rails, 3 sports grounds and car park. Renovations to 16 existing classrooms and administration block. | 2015-04-01 | 2016-03-31 | C | 8000000 |  |  | 0 | 0 | 400000 | 7600000 | 0 | 80000 | 0 | 92000 | 0 | 105800 | 0
91 | EHL/10/001-16-17-EIG | Kwalodakada | P | 800008672 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction 2 Grade R Centres with toilets and fence, 4 classrooms, administration block, library, computer centre, kitchen, upgrade electricity, ramps and rails, 15 toilets, 3 sports grounds, car park and the renovations to 12 classrooms and 14 toilets. | 2016-04-01 | 2017-12-31 | C | 18000000 |  |  | 0 | 0 | 900000 | 17100000 | 0 | 180000 | 0 | 207000 | 0 | 238050 | 0
92 | EHL/03/001/14-15-EIG | Magogeni# | P | 800011536 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Renovations of 20 classrooms, administration block, Home Economics Centre and substitution of 4 unsafe structures. | 2014-06-01 | 2015-03-31 | A | 14026010.2626 |  |  | 0 | 6311704.6181 | 7714305.6444 | 0
93 | BOH/03/001/16-17-EIG | Makata | S | 800034892 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Casteel | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Planning and Design - Construction of an administration block, laboratory, library, school hall, 16 toilets, kitchen, ramps and rails, upgrade of electricity, 3 sports grounds and car park. Renovations to 11 classrooms. | 2016-04-01 | 2017-12-31 | C | 12000000 |  |  | 0 | 0 | 600000 | 11400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | NKA/14/001/16-17-EIG | Maloka | P | 800012112 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of a Grade R Centre, administration block, library, computer centre, kitchen, 10 toilets, electricity, water, fence, 2 sports grounds, car park, ramps and rails and the renovation of 6 classrooms. | 2016-06-01 | 2017-12-31 | C | 18985658.1296 |  |  | 0 | 0 | 1338488.8981 | 16508029.7437 | 1139139.4878 | 0 | 189856.5813 | 0 | 218335.0685 | 0 | 251085.3288
95 | NKA/15/001/14-15-EIG | Malontone | P | 800012138 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of a Grade R Centre, 10 Classrooms , administration block, library, computer centre, kitchen, 28 toilets, electricity, water, fence, 3 sports grounds, car park, ramps and rails. | 2014-06-01 | 2015-03-31 | C | 26853078.96 |  |  | 0 | 0 | 0 | 1893142.0667 | 23348752.1557 | 1611184.7376 | 0 | 268530.7896 | 0 | 308810.408 | 0
96 | NKA/14/002/16-17-EIG | Mapala | C | 800012484 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction of 5 classrooms, administration block, laboratory, library, school hall, 20 toilets, kitchen, ramps and rails, 3 sports grounds and car park. Renovations to 14 classrooms. | 2016-04-01 | 2017-03-31 | C | 27834587.5673 |  |  | 0 | 0 | 0 | 1962338.4235 | 24202173.8898 | 1670075.254 | 0 | 278345.8757 | 0 | 320097.757 | 0
97 | EHL/09/004-16-17-EIG | Maqhekeza | P | 800012625 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 10 Classrooms, Administration Block, library, computer centre, Multi Media Center, Music room, School hall, ramps and rails, fence, kitchen, water, 13 toilets, 2 sports grounds & car parking | 2016-04-01 | 2017-12-31 | C | 31040193.1076 |  |  | 0 | 0 | 0 | 2188333.6141 | 26989447.9071 | 1862411.5865 | 0 | 310401.9311 | 0 | 356962.2207 | 0
98 |  | Masizakhe |  | 800013029 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Tweefontein South | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of Grade R Centre library , kitchen , 16 toilets . Renovation and refurbishment of 16 existing classrooms . | 2016-04-01 | 2017-03-31 | C | 10601841.7577 |  |  | 0 | 0 | 747429.8439 | 9324319.8259 | 530092.0879 | 0 | 53009.2088 | 0 | 60960.5901 | 0 | 70104.6786
99 | BOH/12/001/15-16-EIG | Mathule | P | 800035130 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Shatale | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Planning and Design - Construction of 2 Grade R Centers with toilets and fence and 6 classrooms, administration block, library, computer centre, 10 toilets, kitchen, and car park. Substitute current pit toilets with 20 Enviroloo toilets. | 2014-04-01 | 2016-03-31 | B | 18206609.4 |  |  | 0 | 1283565.9627 | 15830646.8733 | 1092396.564 | 0 | 182066.094 | 0 | 209376.0081 | 0 | 240782.4093 | 0
100 | EHL/04/001/16-17-EIG | Mbangwane | C | 800013656 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 2 Grade R Centres with toilets and fence, | 2016-04-01 | 2017-12-31 | C | 2409849.078 |  |  | 0 | 0 | 169894.36 | 2239954.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | EHL/10/001-16-17-EIG | Mdladla | P | 800013870 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction 2 Grade R Centres with toiltes and fence, 9 classrooms, library, computer centre, 36 toilets, kitchen, ramps and rails, 3 sports grounds, car park and the renovations to 15 classrooms. | 2016-04-01 | 2017-12-31 | C | 26000000 |  |  | 0 | 0 | 2181000 | 22259000 | 1560000 |  | 260000 |  | 299000 |  | 343850
102 | EHL/09/002/16-17-EIG | Mjokwane | S | 800014365 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 3 classrooms, 30 toilets, kitchen, upgrade electricity and the renovations to 25 classrooms, laboratory, library, computer centre, upgrade electricity, ramps and rails, 20 toilets, 3 sports grounds and car park. Renovation to 21 classrooms, school hall and administration block | 2016-04-01 | 2017-12-31 | C | 18000000 |  |  | 0 | 0 | 1269000 | 15831000 | 900000 | 0 | 90000 | 0 | 103500 | 0 | 119025
103 | GSD/03/001/16-17-EIG | Mlamlankunzi | P | 800014506 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Balfour | Dipaleseng | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of a kitchen, and the renovations to 23 classrooms, library, computer centre, ramps and rails, 45 toilets, 3 sports grounds and car park. | 2016-04-01 | 2017-12-31 | C | 30000000 |  |  | 0 | 0 | 2115000 | 26085000 | 1800000 | 0 | 300000 | 0 | 300000 | 0 | 345000
104 | BOH/03/001/14-16-EIG | Mothaileng Mashego | P | 800034979 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Casteel | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Planning and Design - Construction of 2 Grade R Centres, construction of 8 Classrooms, administration block, library, computer centre, kitchen, 12 Toilets, ramps and rails, 2 sports grounds and car park. | 2014-04-01 | 2016-03-31 | C | 19852125.3 |  |  | 0 | 0 | 1399574.8336 | 17261422.9484 | 1191127.518 | 0 | 119112.7518 | 0 | 136979.6646 | 0 | 157526.6143
105 | BOH/09/001/14-15-EIG | Nwa Mahumana | P | 800035072 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Marite | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Demolition of 3 classrooms and the construction of 3 classrooms, administration block, library, computer centre, 18 toilets, kitchen, ramps and rails, 3 sports grounds and car park. | 2014-04-01 | 2015-12-31 | A | 15394690.9991 |  |  | 700000 | 13771009.5392 | 923681.4599 | 0 | 153946.91 | 0 | 177038.9465 | 0 | 203594.7885 | 0 | 234134.0067
106 | EHL/12/001-16-17-EIG | Panorama | S | 800032631 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Sabie | Thaba Chueu |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction of 2 classrooms, ramps and rails, sports grounds and car park and renovations to an administration block, laboratory, library, computer centre, kitchen. | 2016-04-01 | 2017-12-31 | C | 8000000 |  |  | 0 | 0 | 564000 | 7036000 | 400000 | 0 | 40000 | 0 | 46000 | 0 | 52900
107 | BOH/04/001/14-15-EIG | Panyana | P | 800034925 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP- Planning and Design: Construction of administration block, library, computer centre, kitchen, ramps and rails, 3 sports grounds and car park. | 2014-04-01 | 2015-12-31 | C | 11492257.5855 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810204.1598 | 10802722.1304 | 689535.4551
108 | GSD/17/002/14-15-EIG | Perdekop Agricultural | S | 800017996 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Planning and Design: Renovation of 6 classrooms, administration block, library and the construction of a laboratory, ramps and rails, 2 sports grounds and car park. | 2017-04-01 | 2018-03-31 | C | 15000000 |  |  | 0 | 0 | 750000 | 13350000 | 900000 |  | 90000 | 0 | 103500 | 0 | 119025 |  | 0 | 39845.173 | 119535.5191 | 199225.8652 | 278916.2113 | 358606.5574 | 438296.9035 | 517987.2495 | 597677.5956 | 677367.9417 | 757058.2878 | 836748.6339 | 916438.98 | 996129.326 | 1075819.6721 | 1142269.1607 | 1059472.9345 | 934829.0598 | 810185.1852 | 685541.3105 | 560897.4359 | 436253.5613 | 311609.6866 | 186965.812 | 62321.9373
109 | EHL/12/002-16-17-EIG | Pilgrims Rest | P | 800017947 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Sabie | Thaba Chueu |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Demolition of 8 classrooms, kitchen and the Construction of 5 classrooms, a kitchen, computer centre. Renovations to administration block. | 2016-04-01 | 2017-12-31 | C | 7421900.5295 |  |  | 0 | 0 | 523243.9873 | 6898656.5421 | 0 | 74219.0053 | 0 | 85351.8561 | 0 | 98154.6345 | 0
110 | EHL/09/003-16-17-EIG | Sekusile | P | 800020206 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction Administration Block, library, computer centre, School hall, ramps and rails, fence, kitchen, water, 23 toilets, 2 sports grounds & car parking | 2016-04-01 | 2017-12-31 | C | 20807182.5508 |  |  | 0 | 0 | 1466906.3698 | 18299917.0534 | 1040359.1275 | 0 | 104035.9128 | 0 | 119641.2997 | 0 | 137587.4946
111 | NKA/10/002/14-15-EIG | Seruane | S | 800020362 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP - Planning and Design: Renovations of 14 classrooms and administration block and the construction of a laboratory, library, computer centre, school hall, kitchen and 3 sports grounds. | 2017-04-01 | 2018-03-31 | A | 17209361.8407 |  |  | 0 | 6023276.6442 | 11186085.1965 | 0 | 172093.6184 | 0 | 197907.6612 | 0 | 227593.8103 | 0 | 261732.8819
112 | NKA/10/003/13-15-EIG | Sibongile | P | 800020719 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP: Planning and Design: Renovations of 8 classrooms and alterations to cater for the Circuit Office. | 2016-04-01 | 2016-09-30 | B | 3000000 |  |  | 0 | 211500 | 2788500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | GSD/02/001-16-17-EIG | Siyeta | P | 800021618 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Construction of a Grade R Center with toilets and fence, library, computer centre, 24 toilets, kitchen, ramps and rails, 3 sports grounds and car park. Renovations to 16 classrooms and administration block. | 2016-04-01 | 2017-12-31 | C | 18000000 |  |  | 0 | 0 | 900000 | 17100000 | 0 | 180000 | 0 | 207000 | 0 | 238050 | 0
114 | GSD/06/001/14-15-EIG | Zinikeleni | S | 800025965 | MST - Technical Recapitalisation | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | CRDP | Upgrades & Additions | Technical Schools | Conditional Grants |  | CRDP: Construction of 2 workshops and refurbishment of 2 workshops to comply with safety standards. | 2014-10-01 | 2015-09-30 | A | 12400000 |  |  | 7000000 | 5400000 | 0 | 0
115 | BOH/01/001/15-16-EIG | Daniye | P | 800035236 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Agincourt | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP - Planning and Design: Renovation of 5 classrooms and the substitution of 5 classrooms and 18 toilets. Addition of an administration block, kitchen, computer centre, ramps and rails, 3 sports grounds, car park and library. | 2015-05-01 | 2016-12-31 | C | 20000000 |  |  | 0 | 0 | 1410000 | 17390000 | 1200000 | 0 | 200000 | 0 | 230000 | 0 | 264500
116 | EHA/10/001-16-17-EIG | DD Mabuza | S | 800029322 | MST - Technical Recapitalisation | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | Upgrades & Additions | Technical Schools | Conditional Grants |  | CRDP: Construct of 4 new Workshops. | 2014-10-01 | 2015-09-30 | A | 14000000 |  |  | 7000000 | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | NKA/15/001/16-17-EIG | Ditholo Combined | Combined | 800002683 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP - Planning and Design: Demolition of 14 classrooms and the construction of 14 classrooms, library, computer centre, kitchen, 22 toilets, school hall, 3 sports grounds and car park. Renovation to the existing administration block. | 2016-05-01 | 2016-12-31 | C | 27463497.2952 |  |  | 0 | 0 | 1936176.5593 | 23879510.8981 | 1647809.8377 | 0 | 274634.973 | 0 | 315830.2189 | 0 | 363204.7517
118 | BOH/14/001/15-16-EIG | Dyondzekani | P | 800035184 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP - Planning and Design: Demolition of 13 classrooms and the construction of 18 classrooms, administration block, library, computer centre, kitchen, 28 toilets, school hall, 3 sports grounds and car park. | 2015-05-01 | 2016-12-31 | C | 28000000 |  |  | 0 | 0 | 1974000 | 24346000 | 1680000 | 0 | 280000 | 0 | 322000 | 0 | 370300
119 | BOH/13/001/15-16-EIG | Godide | P | 800035154 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Demolition of 12 classrooms and the construction 10 classrooms, laboratory, library, computer centre, school hall, kitchen, ramps and rails, Renovate existing administration block. | 2015-05-01 | 2016-12-31 | B | 36000000 |  |  | 0 | 800000 | 17700000 | 17500000 | 0 | 360000 | 0 | 414000 | 0 | 476100 | 0
120 | BOH/05/001/14-15-EIG | Kufakwezwe | S* | 800034941 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 12 classrooms, administration, 1 toilets, fence, kitchen, ramps and rails, 2 sports grounds and 10 car parking | 2014-09-01 | 2015-09-30 | B | 19047138.8637 |  |  | 0 | 1342823.2899 | 17704315.5738 | 1142828.3318 | 0 | 190471.3886 | 0 | 219042.0969 | 0 | 251898.4115 | 0
121 | GSD/08/001/14-15-EIG | Lungelo (Phase 2) | P | 800010843 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replace 5 classrooms and the renovations to 4 classrooms and the construction of a Grade R Centre, library, computer centre, ramps and rails, 2 sports grounds and car park. | 2014-04-01 | 2015-12-30 | B | 18000000 |  |  | 0 | 200000 | 17800000 | 0 | 180000 | 0 | 207000 | 0 | 238050 | 0 | 273757.5
122 |  | Madiba | S | 800035197 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 12 classrooms, library, laboratory, computer centre, multi-purpose centre, music room, home economics, school hall, 15 toilets, kitchen, ramps and rails, 2 sports grounds and 10 car parking |  |  | C | 29670352.3994 |  |  | 0 | 0 | 0 | 0 | 0 | 2091759.8442 | 25798371.4113 | 1780221.144 | 0 | 296703.524 | 0
123 |  | Mhlahle | P | 800035759 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 1 Grade R, 10 classrooms, library, laboratory, computer centre, multi-purpose centre, music room, home economics, school hall, 17 toilets, kitchen, ramps and rails, 2 sports grounds and 10 car parking |  |  | C | 28413785.6398 |  |  | 0 | 0 | 0 | 0 | 0 | 2003171.8876 | 24705786.6138 | 1704827.1384 | 0 | 284137.8564 | 0
124 |  | Apols chiloana | P | 800034851 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 1 Grade R, 9 classrooms, electricity |  |  | B | 9708981.5685 |  |  | 0 | 684483.2006 | 8539049.2895 | 485449.0784 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 |  | Rhandzekile | P | 800035510 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 1 Grade R, 15 classrooms, library, laboratory, computer centre, multi-purpose centre, music room, home economics, school hall, kitchen, ramps and rails, 2 sports grounds and 10 car parking |  |  | C | 30402297.8108 |  |  | 0 | 0 | 0 | 2143361.9957 | 26434797.9465 | 1824137.8686 | 0 | 304022.9781 | 0 | 349626.4248 | 0
126 |  | Hlangalezwe | P | 800034992 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Lehukwe | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 14 classrooms, library, computer centre, multi-purpose centre, music room, home economics, school hall, 8 toilets, fence, kitchen, ramps and rails, 1 sports grounds and car parking |  |  | C | 29362549.585 |  |  | 0 | 0 | 0 | 2070059.7457 | 25530736.8642 | 1761752.9751 | 0 | 293625.4959 | 0 | 337669.3202 | 0
127 |  | MO Mashego | P | 800034890 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Casteel | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 15 classrooms, library, computer centre, multi-purpose centre, music room, home economics, school hall, 14 toilets, fence, kitchen, ramps and rails, 1 sports grounds and car parking |  |  | C | 30663360.7229 |  |  | 0 | 0 | 0 | 2161766.931 | 26661792.1486 | 1839801.6434 | 0 | 306633.6072 | 0 | 352628.6483 | 0
128 |  | Casteel | P | 800034882 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Casteel | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 8 classrooms, library, computer centre, multi-purpose centre, music room, home economics, school hall, 8 toilets, fence, kitchen, ramps and rails, 1 sports grounds and car parking |  |  | C | 25016396.942 |  |  | 0 | 0 | 0 | 1763655.9844 | 21751757.1411 | 1500983.8165 | 0 | 250163.9694 | 0 | 287688.5648 | 0
129 |  | Kennen | C | 800034886 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Casteel | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 1 Grade R, 19 classrooms, administration block, library, laboratory, computer centre, multi-media centre, multi-purpose centre, music room, home economics, workshop, school hall, 18 toilets, fence, electricty, water, kitchen, ramps and rails, 2 sports grounds and car parking |  |  | C | 47477561.3549 |  |  | 0 | 0 | 0 | 3347168.0755 | 41281739.5981 | 2848653.6813 | 0 | 474775.6135 | 0 | 545991.9556 | 0
130 |  | Lydenburg | P | 800017764 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 4 classrooms |  |  | C | 2957437.2642 |  |  | 0 | 0 | 0 | 0 | 208499.3271 | 2748937.9371 | 0 | 0 | 0 | 0 | 0
131 |  | Spekboom | P | 800022244 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 3 classrooms |  |  | C | 2453832.9153 |  |  | 0 | 0 | 0 | 172995.2205 | 2280837.6948 | 0 | 0 | 0 | 0 | 0 | 0
132 |  | Matlolane | P | 800035131 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Shatale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 6 classrooms, administration block, computer centre, 6 toilets, electricity, water, kitchen, car parking |  |  | C | 14110749.2132 |  |  | 0 | 0 | 0 | 0 | 994807.8195 | 12269296.4409 | 846644.9528 | 0 | 846644.9528 | 0 | 973641.6957
133 |  | Relane | P | 800035141 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Shatale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 8 classrooms, administration block, 8 toilets, fence, kitchen |  |  | C | 14575647.9803 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1027583.1826 | 12673525.9189 | 874538.8788
134 |  | Serisha | S | 800035145 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Shatale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 20 classrooms, administration block, 8 toilets, water, kitchen |  |  | C | 21951853.2663 |  |  | 0 | 0 | 0 | 0 | 0 | 1547605.6553 | 19087136.4151 | 1317111.196 | 0 | 219518.5327 | 0
135 |  | Sibambayana | P | 800034958 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 1 Grade R, 8 classrooms, administration, 1 toilets, kitchen, ramps and rails, 2 sports grounds and 10 car parking |  |  | C | 16773061.3723 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1182500.8267 | 14584176.8632 | 1006383.6823 | 0 | 167730.6137
136 |  | Makgahlishe | P | 800034916 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 1 Grade R, 17 classrooms, 4 toilets, fence, electricity |  |  | C | 18823057.2753 |  |  | 0 | 0 | 0 | 0 | 1327025.5379 | 16366648.3008 | 1129383.4365 | 0 | 188230.5728 | 0 | 216465.1587
137 |  | Sebosegolo | P | 800034928 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 1 Grade R, 3 classrooms, school hall, 1 toilets, fence, electricity |  |  | C | 14038555.3625 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 989718.1531 | 12206523.8877 | 842313.3217 | 0 | 140385.5536
138 |  | Mahlale | S | 800035027 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 12 classrooms, administration block, computer centre, 8 toilets |  |  | C | 16584454.5492 |  |  | 0 | 0 | 0 | 0 | 0 | 1169204.0457 | 15415250.5034 | 0 | 165844.5455 | 0 | 190721.2273
139 |  | Munyamane | P | 800035038 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 4 classrooms |  |  | C | 14038555.3625 |  |  | 0 | 0 | 0 | 0 | 989718.1531 | 12206523.8877 | 842313.3217 | 0 | 140385.5536 | 0 | 161443.3867
140 |  | Matikinya | P | 800035033 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 12 classrooms, 4 toilets |  |  | C | 10370727.1773 |  |  | 0 | 0 | 0 | 731136.266 | 9017347.2807 | 622243.6306 | 0 | 103707.2718 | 0 | 119263.3625 | 0
141 |  | Londhindha | P | 800035097 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 10 classrooms |  |  | C | 7930908.0948 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559129.0207 | 7371779.0741 | 0
142 |  | Thwasani | P | 800035117 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 10 classrooms |  |  | C | 7930908.0948 |  |  | 0 | 0 | 0 | 0 | 559129.0207 | 6895924.5884 | 475854.4857 | 0 | 79309.0809 | 0 | 91205.4431
143 |  | Matikwana | P | 800035103 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 10 classrooms |  |  | C | 7930908.0948
144 |  | Shakwaneng | P | 800028589 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Sabie | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 8 classrooms |  |  | C | 6046484.5284 |  |  | 0 | 0 | 0 | 0 | 0 | 426277.1593 | 5257418.2974 | 362789.0717 | 0 | 60464.8453 | 0
145 |  | Matibidi | P | 800026856 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Sabie | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 6 classrooms |  |  | C | 4907665.8306
146 |  | Pilgrims City | S | 800028654 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Sabie | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures 1 classrooms |  |  | C | 790163.7738 |  |  | 0 | 0 | 0 | 0 | 55706.5461 | 687047.4013 | 47409.8264 | 0 | 7901.6377 | 0 | 9086.8834
147 |  | Malavutela | S | 80035063 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Marite | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 12 classrooms, library, laboratory, computer centre, multi-purpose centre, music room, home economics, workshop, school hall, fence, kitchen, ramps and rails, 1 sports grounds and car parking |  |  | C | 30109919.1766 |  |  | 0 | 0 | 0 | 2122749.302 | 26180574.7241 | 1806595.1506 | 0 | 301099.1918 | 0 | 346264.0705 | 0
148 |  | Marcia Mokoena | S | 80035065 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Maviljan | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 14 classrooms, library, computer centre, multi-purpose centre, music room, home economics, workshop, school hall, fence, electricty, water, kitchen, ramps and rails, 1 sports grounds and car parking |  |  | C | 32808931.7243 |  |  | 0 | 0 | 0 | 2313029.6866 | 28527366.1342 | 1968535.9035 | 0 | 328089.3172 | 0 | 377302.7148 | 0
149 |  | Mabonwana | P | 800034913 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures Grade R centre, 2 classrooms, administration block, school hall, 16 toilets, fence |  |  | C | 17886809.9528 |  |  | 0 | 0 | 0 | 0 | 0 | 1261020.1017 | 15552581.254 | 1073208.5972 | 0 | 178868.0995 | 0
150 |  | Khokhovela | P | 800034910 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures Grade R centre, 21 classrooms, school hall, 16 toilets, fence |  |  | C | 26912074.0617 |  |  | 0 | 0 | 0 | 0 | 1897301.2214 | 23400048.3967 | 1614724.4437 | 0 | 269120.7406 | 0 | 309488.8517
151 |  | Floraphophe | P | 800035153 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Rolle | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: of a Grade R centre, 8 classrooms, administration block, library, computer centre, music room, multi-media centre, multi-purpose centre, 22 toilets, kitchen, fence, ramps and rails, water, electricity, 2 sports grounds and car park. |  |  | C | 29766099.1862 |  |  | 0 | 0 | 0 | 2098509.9926 | 25881623.2424 | 1785965.9512 | 0 | 297660.9919 | 0 | 342310.1406 | 0
152 |  | Songeni | P | 800035171 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: of a Grade R centre, 8 classrooms, administration block, library, laboratory, computer centre, music room, multi-media centre, home ecomonic, workshop, multi-purpose centre, school hall, 12 toilets, kitchen, fence, ramps and rails, water, electricity, 2 sports grounds and car park. |  |  | C | 39069176.1493 |  |  | 0 | 0 | 0 | 2754376.9185 | 33970648.6618 | 2344150.569 | 0 | 390691.7615 | 0 | 449295.5257 | 0 | 2344150.569
153 |  | Jan Rikhotso | P | 80005193 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Kildare | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: of a Grade R centre, 9 classrooms, administration block, library, computer centre, music room, multi-media centre, home ecomonic, workshop, multi-purpose centre, school hall, 24 toilets, kitchen, fence, ramps and rails, water, electricity, 2 sports grounds and car park. |  |  | C | 40946439.6512 |  |  | 0 | 0 | 0 | 0 | 0 | 2886723.9954 | 35602929.2767 | 2456786.3791 | 0 | 409464.3965 | 0
154 | BOH/01/002/15-16-EIG | Manyakatana | P | 800034835 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Agincourt | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP: Planning and Design - Substitution of unsafe structures and the construction of a Grade R Centre with toilets and fence, 15 classrooms, administration block, library, computer centre, school hall, 22 toilets, kitchen, ramps and rails, upgrade electricity, 3 sports grounds and car park. | 2015-06-01 | 2016-09-30 | B | 33121116.3683 |  |  | 0 | 2335038.704 | 28798810.6822 | 1987266.9821 | 0 | 331211.1637 | 0 | 380892.8382 | 0 | 438026.764 | 0
155 | BOH/05/001/13-16-EIG | Masana | S | 800034943 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 15 classrooms, laboratory, library, computer centre, school hall, 22 toilets, kitchen, ablution blocks, 3 sports grounds and car park. Renovations to 10 classrooms and an administration block. | 2013-04-01 | 2013-09-04 | B | 30048182.1164 |  |  | 0 | 950000 | 27295291.1894 | 1802890.927 | 0 | 300481.8212 | 0 | 345554.0943 | 0 | 397387.2085 | 0
156 |  | Jongilanga | P | 800035194 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 1 Grade R Centre, 15 Classroom , administration block, laboratory, library, computer centre, mutli media centre, music room, home economic, mutli purpose centre, school hall, 26 toilets, fence, kitchen, ramps & rails, 2 sports grounds and 10 car park. |  |  | A | 11570960.1283 |  |  | 0 | 4049836.0449 | 7521124.0834 | 0 | 115709.6013 | 0 | 133066.0415 | 0 | 153025.9477 | 0 | 175979.8399
157 |  | Magudu | p | 800035199 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | ximhungwe | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 1 Grade R Centre, 13 Classroom, laboratory, library, computer centre, mutli media centre, music room, home economic, mutli purpose centre, school hall, 20 toilets, kitchen, ramps & rails, 2 sports grounds and 8 car park. |  |  | C | 9154979.8661 |  |  | 0 | 0 | 0 | 0 | 0 | 645426.0806 | 8509553.7856 | 0 | 91549.7987 | 0 | 105282.2685
158 |  | Moholoholo | S | 800034869 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Arhurseat | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 4 Classroom , administration block, laboratory, library, fence, kitchen |  |  | C | 4108200 | [5 empty] | 289628.1 | 3818571.9 | 0 | 0 | 0 | 0 | 0 | 0
159 |  | NP. Mathabela | P | 800034873 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Arhurseat | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 4 Classroom , administration block, laboratory, library, fence, kitchen |  |  | C | 4108200 |  |  | 0 | 0 | 0 | 4108200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 |  | Senianya | P | 800034876 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Arhurseat | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 9 Classroom, kitchen |  |  | C | 2472300 |  |  | 0 | 0 | 0 | 0 | 0 | 174297.15 | 2149664.85 | 148338 | 0 | 24723 | 0
161 |  | Mashishing | S | 800012898 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 26 Classroom, administration block, 1 toilet, fence |  |  | C | 6851100 |  |  | 0 | 0 | 0 | 0 | 483002.55 | 5957031.45 | 411066 | 0 | 411066 | 0 | 472725.9
162 |  | Spekboom | P | 800022244 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 4 Classroom, 1 toilet |  |  | C | 1254600 |  |  | 0 | 0 | 1254600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 |  | Hambanathi | P | 80004994 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 5 Classroom, administration block |  |  | A | 6851100 |  |  | 0 | 2397885 | 4453215 | 0 | 68511 | 0 | 78787.65 | 0 | 90605.7975 | 0 | 104196.6671
164 |  | Kellysville | P | 800012757 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 15 Classroom, administration block, library |  |  | C | 4391100 |  |  | 0 | 0 | 0 | 309572.55 | 4081527.45 | 0 | 0 | 0 | 0 | 0 | 0
165 |  | Marifaan | P | 800012757 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Mashishing | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 18 Classroom, administration block |  |  | A | 4760100 |  |  | 0 | 1666035 | 3094065 | 0 | 47601 | 0 | 54741.15 | 0 | 62952.3225 | 0 | 72395.1709
166 |  | Matlalong | P | 800035130 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Shatale | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 10 Classroom, administration block, electricity, kitchen |  |  | C | 3419400 |  |  | 0 | 0 | 0 | 0 | 241067.7 | 3178332.3 | 0 | 0 | 0 | 0 | 0
167 |  | Boikhutso | P | 800035120 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Shatale | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 21 Classroom, administration block, computer centre, 11 toilets, fence, car parking |  |  | A | 7773600 |  |  | 0 | 2720760 | 5052840 | 0 | 77736 | 0 | 89396.4 | 0 | 102805.86 | 0 | 118226.739
168 |  | Narishe | P | 800035136 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Shatale | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 21 Classroom, administration block, computer centre, 10 toilets |  |  | A | 5916300 |  |  | 0 | 2070705 | 3845595 | 0 | 59163 | 0 | 68037.45 | 0 | 78243.0675 | 0 | 89979.5276
169 |  | Lehlasedi | S | 800035125 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Shatale | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 24 Classroom, 16 toilets, fence, electricity, water, kitchen (ex Storm Damage School) |  |  | A | 8819100 |  |  | 0 | 8819100 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
170 |  | Mgangedwa | P | 800034950 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 4 Classroom, adminstration block, 1 toilets, kitchen, ramp & rails, 2 sport field, car parking |  |  | C | 2521500 |  |  | 0 | 0 | 0 | 0 | 0 | 177765.75 | 2192444.25 | 151290 | 0 | 25215 | 0
171 |  | Mkhweyantaba | P | 800034947 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Dwarsloop | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 4 Classroom, adminstration block, 1 toilets, kitchen, ramp & rails, 2 sport field, car parking |  |  | C | 2521500 |  |  | 0 | 0 | 0 | 0 | 0 | 2521500 | 0 | 0 | 0 | 0 | 0
172 |  | Beretta | P | 800034963 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Greenvalley | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 3 Grade R, 23 Classrooms |  |  | A | 6309900 |  |  | 0 | 2208465 | 4101435 | 0 | 63099 | 0 | 72563.85 | 0 | 83448.4275 | 0 | 95965.6916
173 |  | Chayiwe | P | 800034964 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Greenvalley | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 2 Grade R, 16 Classrooms |  |  | C | 4206600 |  |  | 0 | 0 | 0 | 296565.3 | 3910034.7 | 0 | 42066 | 0 | 48375.9 | 0 | 55632.285
174 |  | Funjwa | P | 800034965 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Greenvalley | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 4 Grade R, 5 Classrooms |  |  | C | 2103300 |  |  | 0 | 0 | 0 | 148282.65 | 1955017.35 | 0 | 0 | 0 | 0 | 0 | 0
175 |  | Dayimani | S | 800035021 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 12 Classrooms, 12 toilets |  |  | C | 2952000 |  |  | 0 | 0 | 0 | 0 | 208116 | 2743884 | 0 | 0 | 0 | 0 | 0
176 |  | Nyamazane | S | 800035041 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 12 Classrooms |  |  | C | 2804400 |  |  | 0 | 0 | 0 | 0 | 0 | 197710.2 | 2606689.8 | 0 | 0 | 0 | 0
177 |  | Shiviti | P | 800035044 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 8 Classrooms, administration block, 12 toilets, fence |  |  | C | 4231200 |  |  | 0 | 0 | 0 | 0 | 298299.6 | 3679028.4 | 253872 | 0 | 42312 | 0 | 48658.8
178 |  | Hobo | H | 800034993 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Lehukwe | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 4 Classroom, laboratory, computer centre, kitchen |  |  | C | 1771200 |  |  | 0 | 0 | 1771200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 |  | Hoyohoyo | H | 800034995 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Lehukwe | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of laboratory, school hall, 1 toilet |  |  | C | 1008600 |  |  | 0 | 0 | 0 | 0 | 1008600 | 0 | 0 | 0 | 0 | 0 | 0
180 |  | James Khosa | H | 800034996 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Lehukwe | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 16 classrooms, administration block, 8 toilets |  |  | C | 4391100 |  |  | 0 | 0 | 0 | 0 | 309572.55 | 3818061.45 | 263466 | 0 | 43911 | 0 | 50497.65
181 |  | LM Kganane | s | 800028613 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Sabie | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 4 Classroom, adminstration block, laboratory, mutli- purpose centre, 14 toilets, fence, water, kitchen, ramp & rails, 2 sport field, car parking |  |  | C | 5485800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386748.9 | 5099051.1 | 0
182 |  | Makorompne | p | 800035062 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Marite | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 10 Classroom , administration block, laboratory, library, computer centre, mutli media centre |  |  | C | 4440300 |  |  | 0 | 0 | 0 | 0 | 0 | 313041.15 | 4127258.85 | 0 | 44403 | 0 | 51063.45
183 |  | Nembe | P | 800035203 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of Grade R, 4 Classroom, adminstration block, laboratory, library, mutli- purpose centre, music room, school hall, home economic, kitchen, ramp & rails, 2 sport field, car parking |  |  | C | 5129100 |  |  | 0 | 0 | 0 | 0 | 361601.55 | 4459752.45 | 307746 | 0 | 51291 | 0 | 58984.65
184 |  | Lebadishang | P | 800034887 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Casteel | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of Grade R, 26 Classroom, adminstration block, laboratory, library, mutli- purpose centre, music room, 1 workshop, school hall, home economic, 12 toilets, fence, water, electricity, kitchen, ramp & rails, 2 sport field, car parking |  |  | A | 14809200 |  |  | 0 | 5183220 | 9625980 | 0 | 148092 | 0 | 170305.8 | 0 | 195851.67 | 0 | 225229.4205
185 | BOH/01/003/16-17 | Mathibela | S* | 800035005 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Lehukwe | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 2 classrooms, administration block, laboratory, library, computer centre, school hall, kitchen, 28 toilets, upgrade the electricity, ramps and rails 3 sports grounds and car park. Renovations to 16 classrooms. | 2018-04-01 | 2019-03-30 | C | 21513830.4775 |  |  | 0 | 0 | 0 | 1516725.0487 | 18706275.6002 | 1290829.8286 | 0 | 215138.3048 | 0 | 247409.0505 | 0
186 | BOH/03/001/15-16-EIG | Matlushe | P | 800034897 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Casteel | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Construction of 2 Grade R Centres, administration block, library, computer centre, 20 toilets, upgrade of electricity, ramps and rails, 3 sports grounds and car park. Renovations to 13 existing classrooms. | 2015-04-01 | 2016-12-14 | C | 6000000 |  |  | 0 | 0 | 0 | 300000
187 | NKA/02/001/15-16-EIG | Mmagobana | C* | 800014613 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Emalahleni 1 | Emalahleni |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planing and Design: Substitution of 7 unsafe structures and construction of Grade R Centre Centre, 4t and F, administration block, library, computer centre, kitchen, 28 toilets, 3 Sports Grounds and Car Park. Renovations of 7 classrooms. | 2015-04-01 | 2016-12-30 | B | 20231138.24 |  |  | 0 | 1011556.91 | 18005713.0356 | 1213868.2944 | 0 | 202311.3824 | 0 | 232658.0898 | 0 | 267556.8032 | 0
188 | NKA/12/001/14-15-EIG | Mphephethe | P | 800015586 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Middelburg 2 | Steve Tshwete |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Substitution of unsafe 14 Crms and construct a cc, kitchen, Grade R Centre, 4T and F. | 2014-09-01 | 2015-09-30 | C | 17000000 |  |  | 0 | 0 | 1198500 | 14951500 | 850000 | 0 | 85000 | 0 | 97750 | 0 | 112412.5
189 | BOH/04/001/14-15-EIG | Mpisi | P | 800034924 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Substitution of unsafe structures: of a Grade R centre, 19 classrooms, administration block, library, laboratory, computer centre, music room, multi-media centre, multi-purpose centre, 24 toilets, kitchen, ramps and rails, water, 2 sports grounds and car park. | 2017-04-01 | 2018-03-31 | A | 35359801.4864 |  |  | 0 | 12375930.5202 | 22983870.9662 | 0 | 353598.0149 | 0 | 406637.7171 | 0 | 467633.3747 | 0 | 537778.3809
190 | BOH/14/002/14-16-EIG | Njonjela | P* | 800035206 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Substitution of unsafe structures: 1 Grade R, 12 classrooms, library, laboratory, computer centre, multi-purpose centre, music room, home economics, school hall, 18 toilets, kitchen, ramps and rails, 2 sports grounds and 10 car parking | 2014-04-01 | 2015-12-31 | B | 29958578.5814 |  |  | 0 | 1217258.03 | 15000000 | 8127902.56 | 0 | 299585.7858 | 0 | 344523.6537 | 0 | 396202.2017 | 0
191 | NKA/15/002/16-17-EIG | Pungutsha | S | 800018770 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP: Planning and Design - Construction of a computer centre and renovations to 16 classrooms, administration block laboratory, library, ramps and rails and upgrading of 3 sports grounds. | 2016-04-01 | 2017-12-31 | C | 7841573.3793 |  |  | 0 | 0 | 552830.9232 | 7288742.4561 | 0 | 78415.7338 | 0 | 90178.0939 | 0 | 103704.8079 | 0
192 | BOH/13/002/14-16-EIG | Thulamahashe | P* | 8000035173 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Thulamahashe | Bushbuckridge | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Demolition of 12 classrooms and the construction 12 classrooms, administration block, library, computer centre, school hall, kitchen, ramps and rails, 3 sports grounds and car park. | 2014-04-01 | 2016-12-31 | C | 20552705.46 |  |  | 0 | 0 | 0 | 1448965.7349 | 17870577.3975 | 1233162.3276 | 0 | 1233162.3276 | 0 | 1418136.6767 | 0
193 | GSD/18/002/15-17-EIG | Uthaka | S* | 800029926 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of 13 classrooms, computer centre, kitchen, 20 toilets, school hall, 3 sports grounds and car park. Fitting of shelves and counter in the library and necessary shelves and gas tubes in the laboratory. | 2014-04-01 | 2015-12-31 | C | 25000000 |  |  | 0 | 0 | 1762500 | 21987500 | 1250000 | 0 | 125000 | 0 | 143750 | 0 | 165312.5
194 | GSD/18/001/15-16-EIG | Vukubone | P | 800024844 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP - Planning and Design: Demolition of 15 classrooms and the construction of 15 classrooms, administration block, library, computer centre, kitchen, 36 toilets, school hall, 3 sports grounds and car park. | 2015-05-01 | 2016-12-31 | C | 26554248 |  |  | 0 | 0 | 0 | 1872074.484 | 23088918.636 | 1593254.88 | 0 | 265542.48 | 0 | 305373.852 | 0
195 |  | Badlangaye | P | 800035482 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Maviljan | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2015-06-01 | 2015-10-31 | A | 1090680 |  |  | 0 | 1090680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 |  | Bantomu | P | 800035050 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1090680 |  |  | 0 | 1090680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 |  | Bhekimfundo | P |  | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni |  | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1090680 |  |  | 0 | 1090680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 |  | Buyisonto | P | 800034935 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Dwarsloop | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1305240 |  |  | 0 | 1305240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 |  | Ezrom | P | 800035152 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Thulamahashe | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1184550 |  |  | 0 | 1184550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 |  | Halemela | S | 800035053 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1090680 |  |  | 0 | 1090680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 |  | Hlulani | P | 800035054 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 2842920 |  |  | 0 | 2842920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 |  | Homuzeya | P | 800035094 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 295020 |  |  | 0 | 295020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 |  | Letsamaile | P | 800034912 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 84930 |  |  | 0 | 84930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 |  | Londhindha | P | 800035097 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1636020 |  |  | 0 | 1636020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 |  | Madille | P | 800034914 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 4188390 |  |  | 0 | 4188390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 |  | Madukulushe | P | 800035061 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) and completion of 8 Enviro-Loo toilets | 2015-05-01 | 2015-11-30 | A | 3339090 |  |  | 0 | 4042081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 |  | Magolane |  |  | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni |  | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 411240 |  |  | 0 | 411240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 |  | Makhosana Manzini | S | 800035100 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 438060 |  |  | 0 | 438060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 |  | Makorompane | P | 800035062 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1090680 |  |  | 0 | 1090680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 |  | Malengeza | P | 800025064 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Marite | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1725420 |  |  | 0 | 1725420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Mapaleni | P | 800035102 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1090680 |  |  | 0 | 1090680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 |  | Matlalong | P | 800035131 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Shatale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 3289920 |  |  | 0 | 3289920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 |  | Matlolane |  |  | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni |  | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 2842920 |  |  | 0 | 2842920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 |  | Mbatini | P | 800035105 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1090680 |  |  | 0 | 1090680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 |  | Mkhumbini | P | 800035109 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mkhuhlu | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1090680 |  |  | 0 | 1090680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 |  | Morage | P | 800034920 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 273027.6 |  |  | 0 | 273027.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 |  | Morithing | P | 800035497 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Casteel | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1090680 |  |  | 0 | 1090680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 |  | Relane | P | 800025141 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Shatale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 2552370 |  |  | 0 | 2552370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Sebosekgolo sa mapulane | P | 800024928 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 3303330 |  |  | 0 | 3303330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 |  | Sihlekisi | P | 800034931 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 4188390 |  |  | 0 | 4188390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 |  | Tfolinhlanhla | P | 800022806 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White Hazy | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Planning and Design: Replacement of condemn structures (ex Storm Damage Schools) | 2014-05-01 | 2015-03-31 | A | 1070500 |  |  | 0 | 1070500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 |  | Dlomodlomo | S | 800002766 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 9 Classrooms, Laboratory, library, computer centre, school hall, ramps and rails, kitchen, water, 6 toilets, fence, 3 sports ground, car parking | 2015-04-01 | 2016-09-30 | C | 23309358.1692 |  |  | 0 | 0 | 0 | 1643309.7509 | 20267486.9282 | 1398561.4902 | 0 | 233093.5817 | 0 | 268057.6189 | 0
223 |  | Letabogiye | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | 4 Classrroms, Adminstration, Lab, Lib, Computer Room, Multi-Media Room, Music Room, Home Economic, Technical/Workshop, Multi Purpose Center, School Hall, 12 Toilets, Fence, Electricity, Water, Kitchen, Ramp&Rails, Sport Field LRG, Sport Field SML | 2015-04-01 | 2016-09-30 | C | 25479700 |  |  | 0 | 0 | 0 | 0 | 1796318.85 | 22154599.15 | 1528782 | 0 | 254797 | 0 | 293016.55
224 |  | Ekuphakameni Primary | P | 800003277 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Libangeni | Dr JS Moroka | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP. Construction of a Grade R Centre, 16 Classrooms, administration block, library, computer centre, 18 toilets, fence, electricity, water, kitchen, 3 sports grounds and car park. | 2015-04-01 | 2016-09-30 | A | 29843647.663 |  |  | 0 | 24471791.0836 | 5371856.5793 | 0 | 298436.4766 | 0 | 343201.9481 | 0 | 394682.2403 | 0 | 453884.5764
225 |  | Duvha Primary | P | 800002980 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | eMalahleni 3 | eMalahleni |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park in partnership with Eskom | 2015-04-01 | 2016-09-30 | A | 43025355.8489 |  |  | 0 | 36571552.4715 | 6453803.3773 | 0 | 430253.5585 | 0 | 494791.5923 | 0 | 569010.3311 | 0 | 654361.8808
226 |  | Laerskool Onverwacht | P | 80009514 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | eMalahleni 3 | eMalahleni |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Demolition of 14 asbestos structures and construction of 14 classrooms. Refurbishment of other existing structures. | 2015-04-01 | 2016-09-30 | C | 32112953.4144 |  |  | 0 | 0 | 0 | 2263963.2157 | 27922212.9938 | 1926777.2049 | 0 | 321129.5341 | 0 | 369298.9643 | 0
227 |  | Mokebe Secondary | S | 800014969 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Weltevrede | Dr JS Moroka | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | CRDP. Demolition of existing structures and Construction of 12 Classrooms, administration block, library, computer centre, 18 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. | 2015-04-01 | 2016-09-30 | C | 30697138.3667 |  |  | 0 | 0 | 0 | 2164148.2549 | 26691161.8099 | 1841828.302 | 0 | 306971.3837 | 0 | 353017.0912 | 0
228 |  | Witbank High | S | 800025478 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala |  | eMalahleni |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Demolition of 6 asbestos classrooms and construction of 6 classrooms. Refurbishment and renovation of existing 26 classrooms , 1 administration block, 5 special centres , 1 library , 1 school hall and 45 toilets. | 2015-04-01 | 2016-09-30 | C | 14420898.143 |  |  | 0 | 0 | 0 | 0 | 1016673.3191 | 12538970.9353 | 865253.8886 | 0 | 144208.9814 | 0 | 165840.3286
229 |  | J Mdaka | P | 800007021 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Construction of administration block , library ,Fence laboratory , kitchen, 3 Sports Grounds , Car Park and renovation of 16 classrooms. | 2015-04-01 | 2016-09-30 | C | 16477348.9149 |  |  | 0 | 0 | 0 | 0 | 1161653.0985 | 14327054.8815 | 988640.9349 | 0 | 164773.4891 | 0 | 189489.5125
230 |  | Borolo Primary School | P | 800001495 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Weltevrede | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Demolition of 5 classrooms and construction of 5 classrooms , Grade R Centre , Administration block , Kitchen , Computer Centre , Car Park , 3 Sports Grounds and renovation of 16 classrooms. | 2015-04-01 | 2016-09-30 | C | 19293517.3212 |  |  | 0 | 0 | 0 | 0 | 1360192.9711 | 16582778.1376 | 1350546.2125 | 0 | 192935.1732 | 0 | 221875.4492
231 |  | Fakazi | P | 800001503 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 16 Classrooms, Administration block | 2015-04-01 | 2016-09-30 | C | 14788800 |  |  | 0 | 0 | 0 | 0 | 1042610.4 | 12858861.6 | 887328 | 0 | 1478880 | 0 | 1700712
232 |  | Numbi | P | 800000433 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White Hazy | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | 4 Classrooms | 2015-04-01 | 2015-03-31 | C | 2947200 |  |  | 0 | 0 | 0 | 0 | 207777.6 | 2562590.4 | 176832 | 0 | 29472 | 0 | 33892.8
233 |  | Thanda | C | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Construction of 16 Classrooms, Administration block, Laboratory, Library, Computer Centre,Multi-Media Centre, Music Room, Home Economic, Technical/Workshops, Multi-Purpose Center, School Hall, Kitchen, Elelctricity,Water, 24 Toilets,Ramps & Rails, Fence, 1 Sport Field SML, 1 Sport Field LRG, Parking, Guard House | 2015-04-01 | 2016-09-30 | C | 34808800 |  |  | 0 | 0 | 2454020.4 | 30614339.6 | 1740440 | 0 | 174044 | 0 | 200150.6 | 0 | 230173.19
234 |  | Shishila | P | 800020529 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Sikhulile | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | Administration Block | 2015-04-01 | 2015-12-31 | C | 4815091.3566 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339463.9406 | 4475627.416
235 |  | Buyani | C | 800001826 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Malelane | Nkomazi | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 12 Classrooms, Administration block, 20 Toilets | 2015-04-01 | 2015-12-31 | C | 11255100 |  |  | 0 | 0 | 0 | 0 | 793484.55 | 9898860.45 | 562755 | 0 | 112551 | 0 | 129433.65
236 |  | Bashele Primary School | p | 800000729 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Ermelo | Msukaligwa |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 12 Classrooms, 10 Toilets,Fence, 21 REN, Guard house | 2019-04-01 | 2020-03-30 | C | 17341600 |  |  | 0 | 0 | 0 | 1222582.8 | 16119017.2 | 0 | 0 | 0 | 0 | 0 | 0
237 |  | Carolina Combined | C | 800001941 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Caroline | Albert Luthuli | CRDP | Upgrades & Additions | Grade R Centres | Public Ordinary Schools |  | 1 Grade R | 2015-04-01 | 2015-12-31 | A | 2235200 |  |  | 0 | 2235200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 |  | Esithembisweni | P | 800003970 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | CRDP | Upgrades & Additions | Grade R Centres | Public Ordinary Schools |  | 1 Grade R | 2015-04-01 | 2015-12-31 | C | 2400092.604 |  |  | 0 | 0 | 0 | 0
239 |  | Sakhisizwe Primary | P | 800030809 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | 8 Classrooms, Admin Block, MP, Computer Centre, Kitchen, Ramps & Rails, 3 Sport Fields, Parking, 1 Grade R | 2015-04-01 | 2016-09-30 | C | 23444876.7147 |  |  | 0 | 0 | 0 | 1652863.8084 | 20385320.3034 | 1406692.6029 | 0 | 234448.7671 | 0 | 269616.0822 | 0
240 |  | Violet Jiyane Secondary | S | 800035308 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Caroline | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 12 Classrooms, Laboratory, library, computer centre, school hall, ramps and rails, kitchen, 18 toilets, 3 sports ground, car parking | 2015-04-01 | 2016-09-30 | C | 24397969.2188 |  |  | 0 | 0 | 0 | 0 | 1720056.8299 | 21214034.2358 | 1463878.1531 | 0 | 243979.6922 | 0 | 280576.646
241 |  | Thuto-thebe | S | 800022392 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Stanwest | Lekwa |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 6 Classrooms, library, computer centre, kitchen, 4 toilets, fence, school hall, ramps & rails, 3 sports ground, car parking | 2015-04-01 | 2016-09-30 | C | 18841836.351 |  |  | 0 | 0 | 0 | 1328349.4627 | 16382976.7072 | 1130510.1811 | 0 | 188418.3635 | 0 | 216681.118 | 0
242 |  | Simunye | p | 800010398 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 8 Classrooms, Admin Block,10 Toilets | 2019-04-01 | 2020-03-30 | C | 7907900 |  |  | 0 | 0 | 0 | 0 | 0 | 557506.95 | 6875919.05 | 474474 | 0 | 79079 | 0
243 |  | Makhosonke | P | 800011916 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | CRDP | Upgrades & Additions | Grade R Centres | Public Ordinary Schools |  | 1 Grade R | 2015-04-01 | 2015-12-31 | C | 2400092.604 |  |  | 0 | 0 | 0 | 0 | 169206.5286 | 2230886.0754 | 0 | 24000.926 | 0 | 27601.0649 | 0
244 |  | Isu Elihle | P | 800006791 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 5 Classrooms, 1 Grade R Centre | 2015-04-01 | 2016-09-30 | C | 6175636.4732 |  |  | 0 | 0 | 0 | 0 | 435382.3714 | 5740254.1018 | 0 | 61756.3647 | 0 | 71019.8194 | 0
245 |  | MST Academy (Witbank) | N/A | N/A | Equitable Share (ES) | Capital Assets | Nkangala | Emalahleni 1 | Emalahleni |  | Upgrades & Additions | Special Projects | Public Ordinary Schools |  | Refurbishment to existing buildings and conversion of existing offices to 2 lecture rooms, 4 technology centre, administration offices, toilets per MST Specifications | 2014-06-01 | 2015-09-30 | A | 20000000 |  |  | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 |  | Pelonolo Special | C | 800017962 | Education Infrastructure Grant (EIG) | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP |  | Upgrades and Additions | Special Schools |  | TBA | 2015-04-01 | 2016-03-31 | C | TBA |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 |  | Joseph Mathebula | S | 800034157 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | CRDP |  | Maintenance | Public Ordinary Schools |  | CRDP: Repairs to roof structure undermined by termites and general maintenance | 2015-04-01 | 2016-03-31 | C | TBA |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 |  | Final Account - Backlog | All | All | Equitable Share (ES) | Capital Assets | All | All | All |  | Goods & Services | Final Accounts | Public Ordinary Schools |  | Reconciliation and payment of outstanding final accounts (prev. financial years) | N/A | N/A | D | N/A |  |  | 70934718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 |  | Other Circuits (Mmamethlake, Nokaneng) | All | All | Education Infrastructure Grant (EIG) | Capital Assets | All | All | All |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Planning and Design: Refurbishment and Renovations | 2014-04-01 | 2020-03-30 | A | 30000000 |  |  | 3999998 | 3999999 | 15000000 | 16050000 | 17173500 | 18375645 | 19661940.15 | 21038275.9605 | 22510955.2777 | 24086722.1472 | 25772792.6975
250 |  | Valencia | C | 800024521 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mbombela | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 4 Classrooms |  |  | C | 2760022.2642 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194581.5696 | 2428819.5925 | 165601.3359 | 0
251 |  | Laerskool BTN | P | 800008987 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Barberton | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 3 Classrooms |  |  | C | 2256417.9153 |  |  | 0 | 0 | 0 | 0 | 159077.463 | 2097340.4523 | 0 | 0 | 0 | 0 | 0
252 |  | L/S Laeveld | P | 800009381 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mbombela | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 4 Classrooms |  |  | C | 2760022.2642 |  |  | 0 | 0 | 0 | 0 | 194581.5696 | 2565440.6946 | 0 | 0 | 0 | 0 | 0
253 |  | Matsulu | P | 800007195 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkululeko | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 16 Classrooms, Administration block, 9 Toilets |  |  | C | 17269510.284 |  |  | 0 | 0 | 0 | 1217500.475 | 15015839.1919 | 1036170.617 | 0 | 172695.1028 | 0 | 198599.3683 | 0
254 |  | Mbombo | C | 800013755 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 4 Classrooms |  |  | C | 2760022.2642 |  |  | 0 | 0 | 0 | 2300000 | 24600000 | 15100000 | 0 | 22439.2054 | 0 | 25805.0862 | 0
255 |  | Mtfonjeni | P | 800003632 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Insikazi | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 12 Classrooms |  |  | C | 8280066.7926 |  |  | 0 | 0 | 0 | 0 | 0 | 583744.7089 | 7199518.0762 | 496804.0076 | 0 | 82800.6679 | 0
256 |  | Magogeni | P | 800011536 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 5 Classrooms |  |  | C | 3759206.7003 |  |  | 0 | 0 | 0 | 0 | 0 | 265024.0724 | 3494182.6279 | 0 | 37592.067 | 0 | 43230.8771
257 |  | Schoemansdal | P | 800019968 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Malelane | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 12 Classrooms, Fence |  |  | C | 10056801.7926 |  |  | 0 | 0 | 0 | 709004.5264 | 8744389.1587 | 603408.1076 | 0 | 100568.0179 | 0 | 115653.2206 | 0
258 |  | Lundanda | C | 800010835 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White Hazy 1 | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 12 Toilets |  |  | A | 1152904.7281 |  |  | 0 | 1152904.7281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 |  | Mambane | S | 800013680 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 5 Classrooms |  |  | C | 3759206.7003 |  |  | 0 | 0 | 0 | 0 | 0 | 265024.0724 | 3494182.6279 | 0 | 37592.067 | 0 | 43230.8771
260 |  | Thembeka | P | 800023119 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mgwenya | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 23 Classrooms |  |  | C | 16660251.7982 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174547.7518 | 14661021.5824 | 999615.1079 | 0
261 |  | Hoyi | P | 800005686 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 12 Toilets |  |  | A | 1152904.7281 |  |  | 0 | 1152904.7281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 |  | Evimbilanga | P | 800004093 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 10 Classrooms, Administration block, Computer Centre, Library, School Hall, 28 Toilets, Fence, Water, Kitchen, Ramp & rail, Large Sport Field & parking |  |  | C | 27308213.9781 |  |  | 0 | 0 | 0 | 1925229.0855 | 23744492.054 | 1638492.8387 | 0 | 273082.1398 | 0 | 314044.4607 | 0
263 |  | Ndlaphu | P | 800016436 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mgwenya | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 24 Classrooms |  |  | C | 16560133.5852 |  |  | 0 | 0 | 0 | 0 | 1167489.4178 | 14399036.1523 | 993608.0151 | 0 | 165601.3359 | 0 | 190441.5362
264 |  | Sindzawonye | P | 800001220 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Sikhulile | Mbombela |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 4 Classrooms |  |  | C | 2760022.2642 |  |  | 0 | 0 | 0 | 0 | 0 | 194581.5696 | 2399839.3587 | 165601.3359 | 0 | 27600.2226 | 0
265 |  | Klipspringer | P | 800008177 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mbombela | Mbombela |  | Upgrades & Additions | Substitution of unsafe structures | Public Ordinary Schools |  | 10 Classrooms, Administration block, Computer Centre, School Hall and construction of 3 classrooms |  |  | C | 6032517.9153 |  |  |  |  | 0 | 425292.513 | 5607225.4023 | 0 | 60325.1792 | 0 | 69373.956 | 0 | 79780.0494
266 |  | Emjindini | S | 800003574 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Barberton | Umjindi |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 4 toilets |  |  | A | 384301.576 |  |  | 0 | 384301.576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 |  | H/S Barberton | S | 800005710 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Barberton | Umjindi |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 11 toilets, fence & supply water |  |  | C | 3294199.3341 |  |  | 0 | 0 | 0 | 0 | 232241.0531 | 3061958.281 | 0 | 0 | 0 | 0 | 0
268 |  | Kwa-Jelusa |  | 800008623 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction of Kitchen |  |  | C | 1222933.281 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86216.7963 | 1136716.4847
269 |  | Evimbilanga | P | 800004093 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 10 classrooms, Administration Block, Laboratory, library, computer centre, School hall, ramps and rails, fence, water, 28 toilets, 2 sports grounds. |  |  | C | 29147288.6868 |  |  | 0 | 0 | 0 | 2054883.8524 | 25343567.5132 | 1748837.3212 | 0 | 291472.8869 | 0 | 335193.8199 | 0
270 |  | Masibonisane | P | 800012955 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 12 Classroom, Administration Block, library, computer centre, School hall, ramps and rails, fence, kitchen, water, 12 toilets, 1 sport field |  |  | C | 28574268.5027 |  |  | 0 | 0 | 0 | 2014485.9294 | 24845326.4631 | 1714456.1102 | 0 | 285742.685 | 0 | 328604.0878 | 0
271 |  | Mpumelelo | P | 800015719 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 7 Classroom, Administration Block, library, computer centre, School hall, ramps and rails, fence, kitchen, 20 toilets, 1 sport field |  |  | C | 24865612.7856 |  |  | 0 | 0 | 0 | 1753025.7014 | 21620650.3171 | 1491936.7671 | 0 | 248656.1279 | 0 | 285954.547 | 0
272 |  | Sabatha | P | 800019646 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Malelane | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Supply water |  |  | A | 553500 |  |  | 0 | 553500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 |  | Amon Nkosi | P | 800035381 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Barberton | Umjindi |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 8 Classroom, library, computer centre, School hall, ramps and rails, fence, water, electricty, kitchen, 24 toilets, 1 sport field | 2017-04-01 | 2018-03-31 | C | 22870111.7788 |  |  | 0 | 0 | 1612342.8804 | 20114263.3095 | 1143505.5889 | 0 | 114350.5589 | 0 | 131503.1427 | 0 | 151228.6141
274 |  | Mayibuye | S | 800013565 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mgwenya | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 4 Classrooms |  |  | C | 2760022.2642 |  |  | 0 | 0 | 0 | 0 | 194581.5696 | 2399839.3587 | 165601.3359 | 0 | 165601.3359 | 0 | 190441.5362
275 |  | S'bongile | P | 800020131 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkululeko | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 1 Grade R center, 10 classrooms, Administration Block, library, multi media centre, Multi purpose, School hall, ramps and rails, kitchen, 10 toilets, 1 sports ground, car parking |  |  | C | 29137016.1503 |  |  | 0 | 0 | 0 | 2054159.6386 | 25334635.5427 | 1748220.969 | 0 | 291370.1615 | 0 | 335075.6857 | 0
276 |  | Camalaza | S | 800001875 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 12 Classrooms |  |  | C | 8280066.7926 |  |  | 0 | 0 | 0 | 0 | 583744.7089 | 7696322.0837 | 0 | 82800.6679 | 0 | 95220.7681 | 0
277 |  | MC Zitha | P | 800013647 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 1 Grade R Centre, 12 Classrooms |  |  | C | 10680159.3966 |  |  | 0 | 0 | 0 | 0 | 752951.2375 | 9286398.5953 | 640809.5638 | 0 | 640809.5638 | 0 | 736930.9984
278 |  | Gutjwa | P | 800004903 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Insikazi | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 1 Grade R center, 8 Classrooms Administration Block, library, computer center, multi media centre, music room |  |  | C | 20045483.8578 |  |  | 0 | 0 | 0 | 0 | 0 | 1413206.612 | 17429548.2143 | 1202729.0315 | 0 | 200454.8386 | 0
279 |  | Emtfonjeni | P | 800003632 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Insikazi | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 1 Grade R center, 12 Classrooms Administration Block, library, computer center, multi media centre, music room |  |  | C | 22942918.9531 |  |  | 0 | 0 | 0 | 0 | 1617475.7862 | 19948868.0297 | 1376575.1372 | 0 | 229429.1895 | 0 | 263843.568
280 |  | Phola | S | 800034589 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White Hazy 2 | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 12 Classrooms, library, computer center, 8 toilets |  |  | C | 16496338.1446 |  |  | 0 | 0 | 0 | 0 | 1162991.8392 | 14343566.0167 | 989780.2887 | 0 | 164963.3814 | 0 | 189707.8887
281 |  | Malekutu | P | 800012070 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White River | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 2 Classrooms, Administration Block, library, computer centre, multi media centre, music room, ramps and rails, kitchen, 10 toilets, 2 sports ground, car parking |  |  | C | 17062245.8318 |  |  | 0 | 0 | 0 | 0 | 0 | 1202888.3311 | 15859357.5007 | 0 | 170622.4583 | 0 | 196215.8271
282 |  | Hlanganani | S | 800005314 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White River | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 5 Classrooms, library, computer centre, multi media centre, music room, ramps and rails, kitchen, 10 toilets, 2 sports ground, car parking |  |  | C | 14420230.7967 |  |  | 0 | 0 | 0 | 0 | 1016626.2712 | 12538390.6778 | 865213.8478 | 0 | 144202.308 | 0 | 165832.6542
283 |  | Lwaleng | P | 800010926 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White River | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 5 Classrooms, Administration block, library, computer centre, ramps and rails, kitchen, 4 toilets, 2 sports ground, car parking |  |  | C | 15103523.0307 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1064798.3737 | 13132513.2752 | 906211.3818 | 0 | 151035.2303
284 |  | Bhekiswayo | S | 800001065 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White Hazy 1 | Mbombela |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 8 Classrooms, computer centre, multi purpose, 10 toilets, car parking |  |  | C | 10508385.8893 |  |  |  |  | 0 | 0 | 740841.2052 | 9767544.6841 | 0 | 0 | 0 | 0 | 0
285 |  | Thula | P | 800023333 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction Administration block, library, computer centre, multi media centre, music room, ramps and rails, kitchen, 6 toilets, 2 sports ground, car parking |  |  | C | 15229226.7081 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073660.4829 | 13401719.5032 | 913753.6025 | 0
286 |  | Lowveld High | S | 800010736 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mbombela | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 43 Classrooms |  |  | A | 10049100 | 275230 | 0 | 0 | 3517185 | 6531915 | 0 | 100491 | 0 | 115564.65 | 0 | 132899.3475 | 0 | 152834.2496
287 |  | Ndindindi | P | 800016428 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 15 Classrooms |  |  | C | 3505500 |  |  | 0 | 0 | 247137.75 | 3258362.25 | 0 | 35055 | 0 | 40313.25 | 0 | 46360.2375 | 0
288 |  | Mtungwa | S | 800014761 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White River | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 22 Classrooms, Administration block, Laboratory, Library, Computer Centre |  |  | C | 6691200 |  |  | 0 | 0 | 471729.6 | 5884910.4 | 334560 | 0 | 33456 | 0 | 38474.4 | 0 | 44245.56
289 |  | Sidlamafa | S | 800020834 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Malelane | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 20 Classrooms, Administration block, Laboratory, Library, Computer Centre |  |  | C | 6223800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438777.9 | 5785022.1 | 0 | 62238
290 |  | Tiphembeleni | P | 800023598 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mgwenya | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 1 Grade R, 8 Classrooms |  |  | C | 2103300 |  |  | 0 | 0 | 148282.65 | 1955017.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 |  | Mayibuye | S | 800013565 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Mgwenya | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 20 Classrooms, 16 Toilets, Fence |  |  | A | 6531300 |  |  | 0 | 2285955 | 4245345 | 0 | 65313 | 0 | 75109.95 | 0 | 86376.4425 | 0 | 99332.9089
292 |  | Khumbula | S | 800007872 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White River | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 26 Classrooms, 19 Toilets |  |  | C | 6309900 |  |  | 0 | 0 | 0 | 0 | 444847.95 | 5486458.05 | 378594 | 0 | 63099 | 0 | 72563.85
293 |  | Laerskool BTN | P | 800008987 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Barberton | Umjindi |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 27 Classrooms |  |  | C | 6309900 |  |  | 0 | 0 | 0 | 0 | 444847.95 | 5865052.05 | 0 | 0 | 0 | 0 | 0
294 |  | Hoechst | P | 800005538 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Malelane | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 4 Grade R, 16 Classrooms, 12 Toilets, Fence |  |  | A | 6482100 |  |  | 0 | 2268735 | 4213365 | 0 | 64821 | 0 | 74544.15 | 0 | 85725.7725 | 0 | 98584.6384
295 |  | Sihlangu | P | 800020982 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 14 Classrooms, 16 Toilets |  |  | C | 3468600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244536.3 | 3224063.7 | 0 | 0
296 |  | Vukasambe | P | 800024810 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Sikhulile | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 16 Classrooms |  |  | C | 3739200 |  |  | 0 | 0 | 0 | 0 | 263613.6 | 3251234.4 | 224352 | 0 | 37392 | 0 | 43000.8
297 |  | Joseph Mathebula | S | 800034157 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 22 Classrooms, Administration block |  |  | C | 5694900 |  |  | 0 | 0 | 0 | 0 | 0 | 401490.45 | 5293409.55 | 0 | 56949 | 0 | 65491.35
298 |  | Sekusile | P | 800020206 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 16 Classrooms, 28 Toilets |  |  | C | 4083600 |  |  | 0 | 0 | 0 | 0 | 287893.8 | 3550690.2 | 245016 | 0 | 40836 | 0 | 46961.4
299 |  | Khanyisani | S | 800007633 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White Hazy 2 | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 5 Classrooms, Electricity |  |  | C | 1476000 |  |  | 0 | 0 | 0 | 0 | 1476000 | 0 | 0 | 0 | 0 | 0 | 0
300 |  | Kusile | C | 800008599 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White River | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 12 Classrooms, 12 Toilets |  |  | C | 2952000 |  |  | 0 | 0 | 0 | 208116 | 2743884 | 0 | 0 | 0 | 0 | 0 | 0
301 |  | Etimbondvweni | P | 800004044 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 10 Toilets |  |  | A | 123000 |  |  | 0 | 123000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 |  | Salubindza | P | 800019778 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White Hazy 1 | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 12 Classrooms |  |  | C | 2804400 |  |  | 0 | 0 | 0 | 0 | 0 | 197710.2 | 2438425.8 | 168264 | 0 | 28044 | 0
303 |  | Zakheleni | P | 800025742 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White Hazy 1 | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 14 Classrooms, Administration block, 10 Toilets, Fence |  |  | C | 5608800 |  |  | 0 | 0 | 0 | 0 | 395420.4 | 4876851.6 | 336528 | 0 | 56088 | 0 | 64501.2
304 |  | Mpumelelo | P | 800015719 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 10Classrooms, 6 Toilets |  |  | C | 2410800 |  |  | 0 | 0 | 2410800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 |  | Enzani | P | 800003848 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Nkululeko | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 16 Classrooms, Administration block, 12 Toilets, Kitchen |  |  | C | 4612500 |  |  | 0 | 0 | 0 | 325181.25 | 4287318.75 | 0 | 0 | 0 | 0 | 0 | 0
306 |  | Matsamo | P | 8000013391 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Malelane | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | 17 Classrooms, Administration block |  |  | C | 4526400 |  |  | 0 | 0 | 0 | 0 | 319111.2 | 4207288.8 | 0 | 0 | 0 | 0 | 0
307 |  | Njeyeza | S | 800026393 | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Malelane | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Laboratory |  |  | C | 332100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 332100 | 0 | 0 | 0 | 0
308 |  | Kwadela Secondary | S | 800035503 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Ermelo 2 | Msukaligwa |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 9 Classrooms, Laboratory, library, computer centre, school hall, ramps and rails, kitchen, 18 toilets, fence, 3 sports ground, car parking | 2018-04-01 | 2019-03-30 | C | 24001627.8973 |  |  | 0 | 0 | 0 | 1692114.7668 | 20869415.4567 | 1440097.6738 | 0 | 240016.279 | 0 | 276018.7208 | 0
309 |  | Cana Combined | C | 800001909 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 1 Grade R center, 8 Classrooms, administration block, laboratory, library, school hall, kitchen, 10 toilets, fence, ramps & rails, 3 sports ground |  |  | C | 27748761.5527 |  |  | 0 | 0 | 0 | 1956287.6895 | 24127548.1701 | 1664925.6932 | 0 | 277487.6155 | 0 | 319110.7579 | 0
310 |  | Mpuluzi Secondary | S | 800015701 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction Laboratory, library, school hall, home economics, kitchen, 10 toilets, ramps & rails, water, kitchen, 3 sports ground |  |  | C | 15200280.7808 |  |  | 0 | 0 | 0 | 0 | 1071619.795 | 13216644.1389 | 912016.8468 | 0 | 152002.8078 | 0 | 174803.229
311 |  | Tokoloho Primary | P | 800035314 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Balfour | Dipaleseng | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 1 Grade R center, 6 Classrooms, administration block, library, computer centre, kitchen, 6 toilets, fence, kitchen, ramps & rails, 2 sports ground, car parking |  |  | C | 20196860.1965 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1423878.6439 | 17773236.973 | 1211811.6118 | 0
312 |  | Malibongwe Primary | P | 800012104 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 1 Grade R center, 5 Classrooms, administration block, library, computer centre, kitchen, 10 toilets, fence, kitchen, ramps & rails, 3 sports ground, car parking |  |  | C | 20251632.9987 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1427740.1264 | 17608794.8924 | 1215097.9799 | 0 | 202516.33
313 |  | Zamokuhle Primary | P | 800025825 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Highveldridge East | Govan Mbeki |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 1 Grade R center, 4 Classrooms, administration block, library, laboratory, computer centre, kitchen, 12 toilets, fence, kitchen, ramps & rails, 3 sports ground, car parking |  |  | C | 21361084.7216 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1505956.4729 | 18573463.1654 | 1281665.0833
314 |  | Imizamoyethu Primary | P | 800029363 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Planning and Design: Construction 1 Grade R center, 3 Classrooms, library, computer centre, kitchen, 4 toilets, fence, kitchen, 1 sports ground, car parking |  |  | C | 12226881.7304 |  |  | 0 | 0 | 0 | 0 | 861995.162 | 10631273.6646 | 733612.9038 | 0 | 122268.8173 | 0 | 140609.1399
315 |  | Ithole Primary | P | 800006817 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 12 Classrooms, 12 Toilets |  |  | C | 10634870.0141 |  |  | 0 | 0 | 0 | 0 | 749758.336 | 9885111.6781 | 0 | 130170.1289 | 0 | 149695.6483 | 0
316 |  | Zamokuhle | P | 800025825 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Highveldridge east | Govan Mbeki |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 12 Classrooms |  |  | C | 9481965.286 |  |  | 0 | 0 | 0 | 0 | 668478.5527 | 8244568.8162 | 568917.9172 | 0 | 94819.6529 | 0 | 109042.6008
317 |  | Msinyane Secondary | S | 800015792 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 10 Classrooms |  |  | C | 7901637.7383 |  |  | 0 | 0 | 0 | 0 | 0 | 557065.4606 | 6870474.0135 | 474098.2643 | 0 | 79016.3774 | 0
318 |  | Phaphamani Primary | P | 800034488 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 9 Classrooms |  |  | C | 7111473.9645 |  |  | 0 | 0 | 0 | 0 | 501358.9145 | 6183426.6121 | 426688.4379 | 0 | 71114.7396 | 0 | 81781.9506
319 |  | Yellowstone | P | 800025676 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 9 Classrooms |  |  | C | 7111473.9645 |  |  | 0 | 0 | 0 | 0 | 501358.9145 | 6183426.6121 | 426688.4379 | 0 | 71114.7396 | 0 | 81781.9506
320 |  | Isifisosethu Primary | P | 800006700 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Stanwest | Lekwa |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 8 Classrooms, Fence |  |  | C | 8098045.1907 |  |  | 0 | 0 | 0 | 0 | 570912.1859 | 7041250.2933 | 485882.7114 | 0 | 80980.4519 | 0 | 93127.5197
321 |  | The Gem | C | 800023028 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Breyten | Msukaligwa |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 8 Classrooms |  |  | C | 6321310.1907 |  |  | 0 | 0 | 0 | 0 | 0 | 445652.3684 | 5496379.2108 | 379278.6114 | 0 | 63213.1019 | 0
322 |  | Jeug krag Primary | P | 800009233 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Staneast | Lekwa |  | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 5 Classrooms |  |  | C | 3950818.8692 |  |  | 0 | 0 | 0 | 0 | 278532.7303 | 3672286.1389 | 0 | 39508.1887 | 0 | 45434.417 | 0
323 |  | Carolina Combined | P | 800001941 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | CRDP | New & Replacement Schools | Substitution of unsafe structures | Public Ordinary Schools |  | 2 Classrooms |  |  | C | 1580327.5477 |  |  | 0 | 0 | 0 | 111413.0921 | 1580327.5477 | 0 | 0 | 0 | 0 | 0 | 0
324 |  | Peter Mabuza Primary | P | 800018531 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa |  | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 24 Toilets, water |  |  | A | 2766444.4562 |  |  | 0 | 2766444.4562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 |  | Ithole Primary | P | 800006817 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 20 Toilets, water |  |  | A | 2382142.8801 |  |  | 0 | 2382142.8801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 |  | Sisukumile Secondary | S | 800021345 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mashishila | Albert Luthuli | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 20 Toilets |  |  | A | 1921507.8801 |  |  | 0 | 1921507.8801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 |  | Sakhisizwe Primary | P | 800019737 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Bethal | Govan Mbeki |  | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 20 Toilets |  |  | A | 1921507.8801 |  |  | 0 | 1921507.8801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 |  | Ligugu Secondary | S | 800010397 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 16 Toilets | 2015-06-01 | 2015-12-31 | A | 1537206.3041 |  |  | 0 | 1537206.3041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 |  | Cebisa Secondary | S | 800001990 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa |  | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 20 Toilets |  |  | A | 1921507.8801 |  |  | 0 | 1921507.8801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 |  | Libhaba | P | 800010363 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 10 Toilets | 2015-06-01 | 2015-12-31 | A | 960753.9401 |  |  | 0 | 960753.9401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 |  | Eluyengweni Primary | P | 800003467 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 10 Toilets, water |  |  | A | 1421388.9401 |  |  | 0 | 1421388.9401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 |  | Salem Combined | C | 800019752 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 10 toilets |  |  | A | 960753.9401 |  |  | 0 | 960753.9401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 |  | Bhekithemba Primary | P | 800000389 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 8 Toilets |  |  | A | 768603.1521 |  |  | 0 | 768603.1521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 |  | Sibongangwane | P | 800020701 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | 6 Toilets, water |  |  | A | 1037087.364 |  |  | 0 | 1037087.364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 |  | Mabombe Primary School | P | 800011148 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | 1 Grade R Centre |  |  | A | 2400092.604 |  |  | 2400092.604 | 360013.8906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 |  | New Ermelo Primary | P | 800030486 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Ermelo 2 | Msukaligwa |  | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | 2 Grade R Centre |  |  | C | 4800185.208 |  |  | 0 | 0 | 0 | 0 | 338413.0572 | 4461772.1508 | 0 | 0 | 48001.8521 | 0 | 55202.1299
337 |  | Kwachibikhulu Primary | P | 800034784 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Breyten | Msukaligwa |  | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | 1 Grade R Centre |  |  | C | 2400092.604 |  |  | 0 | 0 | 0 | 169206.5286 | 2230886.0754 | 0 | 0 | 0 | 0 | 0 | 0
338 |  | T.P Stratten | P | 800022640 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Highveld Ridge East | Govan Mbeki |  | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | 1 Grade R Centre |  |  | C | 2400092.604 |  |  | 0 | 0 | 0 | 0 | 169206.5286 | 2230886.0754 | 0 | 0 | 0 | 0 | 0
339 |  | Phumula Primary | P | 800018416 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa |  | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | 2 Grade R Centre |  |  | C | 4800185.208 |  |  | 0 | 0 | 0 | 0 | 338413.0572 | 4173761.0384 | 288011.1125 | 0 | 48001.8521 | 0 | 55202.1299
340 |  | Welgevond | P | 800026534 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | 1 Grade R Centre |  |  | C | 2400092.604 |  |  | 0 | 0 | 0 | 0 | 0 | 169206.5286 | 2086880.5192 | 144005.5562 | 0 | 24000.926 | 0
341 |  | Thandeka Primary | P | 800022947 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Stanwest | Lekwa |  | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | 1 Grade R Centre |  |  | C | 2400092.604 |  |  | 0 | 0 | 0 | 0 | 169206.5286 | 2230886.0754 | 0 | 0 | 0 | 0 | 0
342 |  | Lamlile Primary | P | 800009803 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Bethal | Govan Mbeki |  | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | 1 Grade R Centre |  |  | C | 2400092.604 |  |  | 0 | 0 | 0 | 169206.5286 | 2230886.0754 | 0 | 0 | 0 | 0 | 0
343 |  | Vuka Primary | P | 800024760 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mashishila | Albert Luthuli | CRDP | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | 1 Grade R Centre |  |  | C | 2400092.604 |  |  | 0 | 0 | 0 | 0 | 169206.5286 | 2086880.5192 | 144005.5562 | 0 | 24000.926 | 0 | 27601.0649
344 |  | SS Mshayisa Primary | P | 800028928 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Highveld Ridge West | Govan Mbeki |  | Upgrades & Additions | Grade R Centres | Early Childhood Development |  | 1 Grade R Centre |  |  | C | 2400092.604 |  |  | 0 | 0 | 0 | 0 | 0 | 169206.5286 | 2230886.0754 | 0 | 0 | 0 | 0
345 |  | Leseli Combined | C | 800010264 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Stanwest | Lekwa |  | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 24 classrooms, 32 Toilets, Fence |  |  | B | 7662900 |  |  | 0 | 540234.45 | 7122665.55 | 0 | 76629 | 0 | 88123.35 | 0 | 101341.8525 | 0 | 116543.1304
346 |  | Nthoroane Secondary | P | 800017327 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Balfour | Dipaleseng | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 16 classrooms, 24 Toilets |  |  | B | 4034400 |  |  | 0 | 284425.2 | 3749974.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 |  | Mbalenhle Primary | P | 800013615 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Highveld Ridge East | Govan Mbeki |  | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 24 Toilets |  |  | A | 295200 |  |  | 0 | 295200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 |  | Elangwane Secondary | S | 800003384 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 22 Toilets |  |  | A | 270600 |  |  | 0 | 270600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 |  | Zinikeleni Secondary | S | 800025965 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 16 Toilets |  |  | A | 196800 |  |  | 0 | 196800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 |  | Sobhuza Primary | P | 800021907 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 5 classrooms, 15 Toilets |  |  | A | 1353000 |  |  | 0 | 1353000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 |  | Klein Vrystad Primary | P | 800008011 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Piet-Retief | Msukaligwa |  | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 2 classrooms, 15 Toilets |  |  | A | 651900 |  |  | 0 | 651900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 |  | Chief T.D Secondary School | S | 800002105 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 12 classrooms, 10 Toilets |  |  | A | 2927400 |  |  | 0 | 2927400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 |  | Sunduza Primary | S | 800022558 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 3 classrooms, 10 Toilets |  |  | A | 824100 |  |  | 0 | 824100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 |  | Baadjiesbult Combined | P | 80000406 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 10 toilets |  |  | A | 123000 |  |  | 0 | 123000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 |  | Khuphukani Primary | P | 800007898 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 8 toilets |  |  | A | 98400 |  |  | 0 | 98400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 |  | Bhekimfundvo Primary | P | 800034957 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 8 toilets | 2015-05-01 | 2015-08-31 | A | 98400 |  |  | 0 | 98400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 |  | Lindzalokuhle Primary | P | 800010520 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 8 toilets |  |  | A | 98400 |  |  | 0 | 98400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 |  | Imisebeyelanga Primary | P | 800006197 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Stan East | Lekwa |  | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of damages to 6 toilets |  |  | A | 73800 |  |  | 0 | 73800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 |  | Reggie Masuku Secondary | S | 800028779 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence |  |  | C | 1660500 |  |  | 0 | 0 | 1660500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 |  | Siyabonga Secondary | S | 800021451 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence |  |  | C | 1660500 |  |  | 0 | 0 | 0 | 1660500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 |  | Phembindlela Primary | P | 800018242 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Volksrust | Dr Pixley Ka Isaka Seme | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence |  |  | C | 1660500 |  |  | 0 | 0 | 1660500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 |  | Rev SA Nkosi Secondary | S | 800019380 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence |  |  | C | 1660500 |  |  | 0 | 0 | 1660500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 |  | Mkhomazi primary | P | 800014415 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Breyten | Msukaligwa |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence |  |  | C | 1660500 |  |  | 0 | 0 | 0 | 0 | 1660500 | 0 | 0 | 0 | 0 | 0 | 0
364 |  | Diepgezet Primary | P | 800009092 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence |  |  | C | 1660500 |  |  | 0 | 0 | 0 | 0 | 1660500 | 0 | 0 | 0 | 0 | 0 | 0
365 |  | Maqhwauzela Combined | C | 800012609 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Badplaas | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence |  |  | C | 1660500 |  |  | 0 | 0 | 1660500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 |  | MD coovidia Combined | C | 800010975 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Bethal | Govan Mbeki |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence |  |  | C | 1660500 |  |  | 0 | 0 | 0 | 1660500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 |  | Siphumelele Combined | C | 800021287 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Electricity |  |  | A | 799500 |  |  | 0 | 799500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 |  | Silindzile Primary | P | 800021139 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Dundonald | Albert Luthuli | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence |  |  | C | 1660500 |  |  | 0 | 0 | 0 | 0 | 1660500
369 |  | Buhlebuyeza Primary | P | 800034454 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence |  |  | C | 1660500 |  |  | 0 | 0 | 1660500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 |  | Ziwelile Primary | P | 800034782 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Piet Retief | Mkhondo | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Electrricity |  |  | A | 799500 |  |  | 0 | 799500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 |  | Isiyalu Primary | P | 800006783 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Stan East | Lekwa |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence, electricity |  |  | C | 2460000 |  |  | 0 | 0 | 0 | 0 | 0 | 2460000 | 0 | 0 | 0 | 0 | 0
372 |  | Nokuthula Primary | P | 800017194 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Amsterdam | Mkhondo | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Fence, electricity |  |  | C | 2460000 |  |  | 0 | 0 | 2460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 |  | Basizeni Special School | SP | 800000737 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Highveld Ridge East | Govan Mbeki |  | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Special Schools |  | Phase 1 : Remedial works to ceilings, electrical worksand minorworks repair to roof. Phase 2 : Dismantling and carting away of existing damaged prefab buildings and construction of 8New Special School Classrooms | 2014-02-24 | 2014-09-30 | A | 11658541.2544 |  |  | 345261 | 821927.1584 | 10836614.0959 | 0 | 116585.4125 | 0 | 134073.2244 | 0 | 154184.2081 | 0 | 177311.8393
374 |  | Tsandzanani Primary School | P | 800023820 | Equitable Share (ES) | Capital Assets | Ehlanzeni | Nkululeko | Mbombela |  | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of Storm Damaged Structures. Demolishing of 18 unsafe classrooms and construction of 18 new classrooms and 20 Enviro-loo toilets. | 2014-06-30 | 2015-05-31 | A | 10749220 |  |  | 9566805.8 | 1182414.2 | 0 | 107492.2 | 0 | 123616.03 | 0 | 142158.4345 | 0 | 163482.1997 | 0
375 |  | Panyana Primary School | P | 800034925 | Equitable Share (ES) | Capital Assets | Bohlabela | Cottondale | Bushbuckridge | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | CRDP: Rehabilitation of Storm Damaged Structures. Demolishing of unsafe classrooms and construction of 12 new classrooms and 22 Enviro-loo toilets. | 2014-06-30 | 2015-05-31 | A | 7764220 |  |  | 6910155.8 | 854064.2 | 0 | 77642.2 | 0 | 89288.53 | 0 | 102681.8095 | 0 | 118084.0809 | 0
376 |  | Luthango | P | 800010892 | Equitable Share (ES) | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Demolishing of 4 storm damaged and unsafe classrooms and construction of 4 new (Retention) | 2014-02-24 | 2014-09-30 | A | 1352066 |  |  | 1352066 | 202809.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 |  | Ngilandi | S | 800016758 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mashishila | Albert Luthuli | CRDP | Rehabilitation, Renovation & Refurbishment | Storm Damaged Schools | Public Ordinary Schools |  | Rehabilitation of Storm Damaged Structures. (Scope of works currently being finalized) | 2014-04-21 | 2014-10-31 | A | 1512574.8 |  |  | 1421820.312 | 90754.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 |  | Letshele | S | 800035127 | Extended Public Works Programme (EPWP) | Capital Assets | Bohlabela | Shatale | Bushbuckridge | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | CRDP: Construction of 20 Enviro-Loo toilets | 2015-06-01 | 2015-12-31 | A | 1757476.7196 |  |  | 0 | 1757476.7196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 |  | Lobhengula | P | 800007898 | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Mpuluzi | Albert Luthuli | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | CRDP: Construction of 14 Enviro-Loo toilets | 2014-04-01 | 2014-09-30 | A | 1230233.7038 | 393600 | 0 | 0 | 1230233.7038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 |  | Senianya | P | 800034876 |  | Capital Assets | Bohlabela | Arhurseat | Bushbuckridge | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | Completion of 18 Enviro-Loo toilets |  |  | A | 1581729.0477 |  |  | 0 | 1581729.0477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 |  | Puledi | S | 800034875 |  | Capital Assets | Bohlabela | Arhurseat | Bushbuckridge | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | Completion of 12 Enviro-Loo toilets |  |  | A | 1054486.0318 |  |  | 0 | 1054486.0318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 |  | Shalamuka | P | 800035115 |  | Capital Assets | Bohlabela | Mkhulhu | Bushbuckridge | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | Completion of 12 Enviro-Loo toilets |  |  | A | 1054486.0318 |  |  | 0 | 1054486.0318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 |  | Samson Sibuyi | P | 800035043 |  | Capital Assets | Bohlabela | Manyeleti | Bushbuckridge | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | Completion of 8 Enviro-Loo toilets |  |  | A | 702990.6879 |  |  | 0 | 702990.6879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 |  | Salani | P | 800035012 |  | Capital Assets | Bohlabela | Clare A | Bushbuckridge | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | Completion of 8 Enviro-Loo toilets |  |  | A | 702990.6879 |  |  | 0 | 702990.6879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 |  | Hundzukani | P | 80035190 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | CRDP: Construction of 8 Enviro-Loo toilets | 2014-04-01 | 2014-09-30 | B | 702990.6879 | 688800 | 0 | 702990.6879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 |  | Ian Mackenzie | S | 800035191 | Education Infrastructure Grant (EIG) | Capital Assets | Bohlabela | Ximhungwe | Bushbuckridge | CRDP | Upgrades & Additions | Water & Sanitation | Public Ordinary Schools |  | CRDP: Construction of 10 Enviro-Loo toilets | 2014-04-01 | 2014-09-30 | B | 878738.3598 | 688800 | 0 | 878738.3598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 |  | EPWP - Data Capturing | N/A | N/A | Extended Public Works Programme (EPWP) | Capital Assets | All | All | All |  | Upgrades & Additions | Water & Sanitation | Conditional Grants |  | Data capturing and reports for EPWP projects | 2014-04-01 | 2015-03-31 | A | 0 |  |  | 275000 | 288750 | 303187.5 | 318346.875 | 334264.2188 | 350977.4297 | 368526.3012 | 386952.6162 | 406300.247 | 426615.2594 | 447946.0224
388 |  | Sinethemba Secondary School | S | 800021238 | MST - Technical Recapitalisation | Capital Assets | Gert Sibande | Wakkerstroom | Mkhondo | CRDP | Upgrades & Additions | Technical Schools | Conditional Grants |  | CRDP: Construction of 1 new workshop and refurbishment of 3 workshops. | 2015-06-01 | 2016-05-31 | A | 11600000 |  | 3000000 | 0 | 8100000 | 3500000 | 0 | 116000 | 0 | 133400 | 0 | 153410 | 0 | 176421.5
389 |  | Bonginsimbi ComprehensiveSchool | S | 800001412 | MST - Technical Recapitalisation | Capital Assets | Nkangala | eMalahleni 1 | Emalahleni |  | Upgrades & Additions | Technical Schools | Conditional Grants |  | Refurbishment of 4 workshops to comply with safety standards. | 2016-06-01 | 2017-05-31 | C | 10800000 |  | 3000000 | 0 | 0 | 10800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 |  | Kusasalethu Secondary School | S | 800008581 | MST - Technical Recapitalisation | Capital Assets | Gert Sibande | Highveld Ridge East | Govan Mbeki |  | Upgrades & Additions | Technical Schools | Conditional Grants |  | Refurbishment of 4 workshops to comply with safety standards. | 2017-06-01 | 2018-05-31 | C | 10800000 |  | 3000000 | 0 | 0 | 0 | 10800000 | 0 | 108000 | 0 | 124200 | 0 | 142830 | 0
391 |  | Masizakhe Secondary School | S | 800013037 | MST - Technical Recapitalisation | Capital Assets | Gert Sibande | Breyten | Msukaligwa |  | Upgrades & Additions | Technical Schools | Conditional Grants |  | Construction of 2 new workshops and refurbishment of 2 workshops to comply with safety standards. | 2017-06-01 | 2018-05-31 | C | 12400000 |  | 3000000 | 0 | 0 | 0 | 12400000 | 0 | 124000 | 0 | 142600 | 0 | 163990 | 0
392 |  | Sophungane Combined School | S | 800022160 | MST - Dinaledi Grant | Capital Assets | Ehlanzeni | Lubombo | Nkomazi | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2015-06-01 | 2016-01-31 | A | 300000 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 |  | Lugebhuta Secondary School | S | 800010785 | MST - Dinaledi Grant | Capital Assets | Ehlanzeni | Malelane | Nkomazi | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2015-06-01 | 2016-01-31 | A | 300000 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 |  | Mjokwane Secondary School | S | 800014365 | MST - Dinaledi Grant | Capital Assets | Ehlanzeni | Nkomazi East | Nkomazi | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2015-06-01 | 2016-01-31 | A | 300000 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 |  | Thomas Nhlabathi Secondary School | S | 800023275 | MST - Dinaledi Grant | Capital Assets | Gert Sibande | Highveld Ridge West | Govan Mbeki |  | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | Renovation and furnishing of science laboratory. | 2015-06-01 | 2016-01-31 | A | 300000 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 |  | Zinikeleni Secondary School | S | 800025965 | MST - Dinaledi Grant | Capital Assets | Gert Sibande | Carolina | Albert Luthuli | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2015-06-01 | 2016-01-31 | A | 300000 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 |  | Lindile Secondary School | S | 800010496 | MST - Dinaledi Grant | Capital Assets | Gert Sibande | Ermelo 1 | Msukaligwa |  | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | Renovation and furnishing of science laboratory. | 2015-06-01 | 2016-01-31 | A | 300000 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 |  | Bonginsimbi Comprehensive School | S | 800001412 | MST - Dinaledi Grant | Capital Assets | Nkangala | eMalahleni 1 | Emalahleni |  | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | Renovation and furnishing of science laboratory. | 2015-06-01 | 2015-12-31 | A | 300000 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 |  | Ramoshidi Secondary School | S | 800019117 | MST - Dinaledi Grant | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2015-06-01 | 2016-01-31 | A | 300000 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 |  | Sofunda Secondary School | S | 800021923 | MST - Dinaledi Grant | Capital Assets | Nkangala | Middelburg 1 | Steve Tshwete |  | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | Renovation and furnishing of science laboratory. | 2015-06-01 | 2016-01-31 | A | 300000 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 |  | Khamane Secondary School | S | 800007583 | MST - Dinaledi Grant | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2015-06-01 | 2016-01-31 | A | 300000 |  |  | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 |  | Lehlasedi High School | S | 800035125 | MST - Dinaledi Grant | Capital Assets | Bohlabela | Shatale | Bushbuckridge | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2016-06-01 | 2017-01-31 | C | 300000 |  |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 |  | Inkomazi Secondary School | S | 800006411 | MST - Dinaledi Grant | Capital Assets | Ehlanzeni | Nkomazi West | Nkomazi | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2016-06-01 | 2017-01-31 | C | 300000 |  |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 |  | Khutsalani Secondary School | S | 800008607 | MST - Dinaledi Grant | Capital Assets | Ehlanzeni | Insikazi | Mbombela |  | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | Renovation and furnishing of science laboratory. | 2016-06-01 | 2017-01-31 | C | 300000 |  |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 |  | Alpheus D Nkosi Secondary School | S | 800000091 | MST - Dinaledi Grant | Capital Assets | Gert Sibande | Bethal | Govan Mbeki |  | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | Renovation and furnishing of science laboratory. | 2016-06-01 | 2017-01-31 | C | 300000 |  |  | 0 | 0 | 300000 | 0
406 |  | Takheni Secondary School | S | 800022681 | MST - Dinaledi Grant | Capital Assets | Gert Sibande | Mashishila | Albert Luthuli | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2016-06-01 | 2017-01-31 | C | 300000 |  |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 |  | Highveld Secondary School | S | 800005132 | MST - Dinaledi Grant | Capital Assets | Gert Sibande | Mashishila | Albert Luthuli | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2016-06-01 | 2017-01-31 | C | 300000 |  |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 |  | Mmametlhake Secondary School | S | 800014654 | MST - Dinaledi Grant | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2016-06-01 | 2017-01-31 | C | 300000 |  |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 |  | Sozama Secondary School | S | 800022228 | MST - Dinaledi Grant | Capital Assets | Nkangala | Middelburg 1 | Steve Tshwete |  | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | Renovation and furnishing of science laboratory. | 2016-06-01 | 2017-01-31 | C | 300000 |  |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 |  | Allendale Secondary School | S | 800000075 | MST - Dinaledi Grant | Capital Assets | Nkangala | eMalahleni 3 | Emalahleni |  | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | Renovation and furnishing of science laboratory. | 2016-06-01 | 2017-01-31 | C | 300000 |  |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 |  | Kwamhlanga Secondary School | S | 800008730 | MST - Dinaledi Grant | Capital Assets | Nkangala | KwaMhlanga South West | Thembisile Hani | CRDP | Upgrades & Additions | Dinaledi Schools | Conditional Grants |  | CRDP: Renovation and furnishing of science laboratory. | 2016-06-01 | 2017-01-31 | C | 300000 |  |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 |  | District Administration | CIR | N/A | Equitable Share (ES) | Capital Assets | All | All | All |  | Maintenance & Repairs | Maintenance | Administration |  | District Administered Maintenance | 2014-04-01 | 2015-03-31 | C | 0 |  | 0 | 0 | 0 | 0 | 0
413 |  | Vulamehlo Primary | Primary | 800024950 |  | Capital Assets | Nkangala | T/Fontein N | Thembisile Hani | CRDP | New & Replacement Schools | Substitution of unsafe structures |  |  | CRDP. Demolition of 16 precast classrooms and Construction 16 Classrooms, administration block, library, computer centre, 20 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 33819626.7501 |  |  | 0 | 0 | 0 | 2384283.6859 | 29406165.4592 | 2029177.605 | 0 | 338196.2675 | 0 | 388925.7076 | 0
414 |  | Bonginhlanhla Primary | Primary | 800001388 |  | Capital Assets | Nkangala | eMalahleni 3 | eMalahleni |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Demolition of 24 asbestos structures and Construction of a Grade R Centre, 18 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 39468863.2059 |  |  | 0 | 0 | 0 | 2782554.856 | 34318176.5575 | 2368131.7924 | 0 | 394688.6321 | 0 | 453891.9269 | 0
415 |  | Mphephethe Primary | Primary | 800015586 |  | Capital Assets | Nkangala | Steve Tshwete 2 | Steve Tshwete |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Demolition of 17 asbestos structures and construction of 14 classrooms , Grade R Centre kitchen , library , computer centre , 12 toilets , car park and 3 sports grounds. |  |  | C | 20535698.8947 |  |  | 0 | 0 | 0 | 0 | 0 | 1447766.7721 | 17855790.1889 | 1232141.9337 | 0 | 205356.9889 | 0
416 |  | HTS Middelburg | Secondary | 80005876 |  | Capital Assets | Nkangala | Steve Tshwete 1 | Steve Tshwete |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Replacement of 7 asbestos structures and construction of 6 classrooms. |  |  | C | 4576470.143 |  |  | 0 | 0 | 0 | 32264.1145 | 4544206.0285 | 0 | 0 | 0 | 0 | 0 | 0
417 |  | Thushanang Primary | Primary | 800023390 |  | Capital Assets | Nkangala | Steve Tshwete 3 | Steve Tshwete |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Demolition of existing asbestos structures and construction of 1 Grade R Centre, kitchen , fence, library , car park and 3 sports grounds. |  |  | C | 8747295.4536 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616684.3295 | 7697619.9992 | 524837.7272 | 0
418 |  | Laeskool Delmas | Primary | 800005769 |  | Capital Assets | Nkangala | Victor Khanye | Victor Khanye |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Demolotion of 8 asbestos structures and construction of 8 classrooms. |  |  | C | 6058090.1907 |  |  | 0 | 0 | 0 | 0 | 427095.3584 | 5267509.4208 | 363485.4114 | 0 | 60580.9019 | 0 | 69668.0372
419 |  | Mmadimo Primary | Primary | 800004597 |  | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | CRDP | New & Replacement Schools | Substitution of unsafe structures |  |  | CRDP. Construction of a Grade R Centre, 12 Classrooms, administration block, library, computer centre, 18 toilets, fence, electricity, water, kitchen, 3 sports grounds and car park. |  |  | C | 26946212.5676 |  |  | 0 | 0 | 0 | 0 | 1899707.986 | 23429731.8276 | 1616772.7541 | 0 | 269462.1257 | 0 | 309881.4445
420 |  | Makhosoke Primary | Primary | 800022574 |  | Capital Assets | Nkangala | Libangeni | Dr JS Moroka | CRDP | New & Replacement Schools | Substitution of unsafe structures |  |  | CRDP. Demolition of 12 delapidated classrooms and 12 Classrooms, administration block, library, computer centre, 18 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 30598430.8667 |  |  | 0 | 0 | 0 | 2157189.3761 | 26605335.6386 | 1835905.852 | 0 | 305984.3087 | 0 | 351881.955 | 0
421 |  | Laerskool Ellof | Primary | 800009126 |  | Capital Assets | Nkangala | Victor Khanye | Victor Khanye |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Demolition of 5 asbestos classrooms , Construction of 5 classrooms , Grade R Centre , administration block , completion of an existing School Hall and refurbishment of & renovation of 13 classrooms. |  |  | C | 20535698.8947 |  |  | 0 | 0 | 0 | 0 | 1447766.7721 | 17855790.1889 | 1232141.9337 | 0 | 205356.9889 | 0 | 236160.5373
422 |  | Benzangani Primary | Primary | 800000935 |  | Capital Assets | Nkangala | Tweefontein South | Thembisile Hani | CRDP | New & Replacement Schools | Substitution of unsafe structures |  |  | CRDP. Construction of a Grade R Centre, 12 Classrooms, administration block, library, computer centre, 18 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 27788602.1141 |  |  | 0 | 0 | 0 | 1959096.449 | 23745360.5065 | 2084145.1586 | 0 | 277886.0211 | 0 | 319568.9243 | 0
423 |  | Laerskool Klipfontein | Primary | 80009290 |  | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Demolition of 10 asbestos classrooms , 1 laboratory and construction of 10 classrooms and laboratory . Refurbishment of other existing structures. |  |  | C | 10629079.947 |  |  | 0 | 0 | 0 | 0 | 749350.1363 | 9241985.0139 | 637744.7968 | 0 | 106290.7995 | 0 | 122234.4194
424 |  | Laerskool Kragbron | Primary | 800009332 |  | Capital Assets | Nkangala | Emalahleni 1 | eMalahleni |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Replacement of 12 asbestos classrooms and construction 8 classrooms. |  |  | C | 6387115.1907 |  |  | 0 | 0 | 0 | 0 | 450291.6209 | 5553596.6583 | 383226.9114 | 0 | 63871.1519 | 0 | 73451.8247
425 |  | Tjhidelani Primary | Primary | 800023655 |  | Capital Assets | Nkangala | KwaMhlanga S/W | Thembisile Hani | CRDP | New & Replacement Schools | Substitution of unsafe structures |  |  | Construction of Grade R Centre , library ,kitchen, demolition of 18 asbestos toilets and construction of 24 toilets. |  |  | C | 7749693.9098 |  |  | 0 | 0 | 0 | 546353.4206 | 6738358.8545 | 464981.6346 | 0 | 77496.9391 | 0 | 89121.48 | 0
426 |  | Robert Carruthers | P | 800019471 |  | Capital Assets | Nkangala | eMalahleni 1 | eMalahleni |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Replacement of 5 asbestos classrooms and construction of 5 classrooms. Refurbishment and rehabilitation of 36 classrooms , 1 administration , 1 library , 1 laboratory , 3 computer centres |  |  | C | 18779204.2383 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1323933.8988 | 16328518.0852 | 1126752.2543 | 0 | 187792.0424
427 |  | Laerskool Krielpark | Primary | 800009357 |  | Capital Assets | Nkangala | eMalahleni 3 | eMalahleni |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Demolition of 2 asbestos classrooms and construction of 2 classrooms. Refurbishment and renovation of existing 21 classrooms , 1 administration block, 2 special centres , 1 library , 1 lab and 49 toilets. |  |  | C | 9101839.0477 |  |  | 0 | 0 | 0 | 0 | 641679.6529 | 7914049.0519 | 546110.3429 | 0 | 91018.3905 | 0 | 104671.149
428 |  | Laerskool Balmoral | Primary | 80008979 |  | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni |  | New & Replacement Schools | Substitution of unsafe structures |  |  | Demolition of 3 asbestos classrooms , 1 school hall and construction of 3 classrooms and 1 school hall. Refurbishment and renovation of existing facilities. |  |  | C | 9311169.7246 |  |  | 0 | 0 | 0 | 0 | 656437.4656 | 8096062.0755 | 558670.1835 | 0 | 93111.6972 | 0 | 107078.4518
429 |  | Buhlebemfundo Primary School | P | 800001701 |  | Capital Assets | Nkangala | Kwaggafontein West | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Demolition of 16 precast classrooms and Construction 16 Classrooms, administration block, library, computer centre, 20 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 33819626.7501 |  |  | 0 | 0 | 2384283.6859 | 29067969.1917 | 2367373.8725 | 0 | 338196.2675 | 0 | 388925.7076 | 0 | 447264.5638
430 |  | Mabothe Secondary | Secondary | 800028902 |  | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 5 additional classrooms , 10 toilets, kitchen and renovation of existing structures. |  |  | C | 7121581.0902 |  |  | 0 | 0 | 0 | 0 | 502071.4669 | 6619509.6234 | 0 | 71215.8109 | 0 | 81898.1825 | 0
431 |  | Siphumule Primary | Primary | 800021303 |  | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 5 classrooms , Grade R Centre administration block , library , kitchen, School Hall , fence , 12 toilets , 2 Sports Grounds , Car Park and renovation of classrooms. |  |  | C | 24850031.3106 |  |  | 0 | 0 | 0 | 1751927.2074 | 21607102.2245 | 1491001.8786 | 0 | 248500.3131 | 0 | 285775.3601 | 0
432 |  | Somabedlana Primary | Primary | 800002012 |  | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 20 classrooms , administration block , Library , Grade R Centre , 12 toilets , Fence , Kitchen , 3 Sports Grounds and Car Park. |  |  | C | 29136662.015 |  |  | 0 | 0 | 0 | 2054134.6721 | 25334327.622 | 1748199.7209 | 0 | 291366.6201 | 0 | 335071.6132 | 0
433 |  | Mkhulu Combined | Combined | 800014449 |  | Capital Assets | Nkangala | Middelburg 3 | Steve Tshwete |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 5 classrooms , Grade R Centre administration block , library , kitchen, fence , 12 toilets , 2 Sports Grounds , Car Park and renovation of classrooms. |  |  | C | 19192550.4075 |  |  | 0 | 0 | 0 | 0 | 1353074.8037 | 16687922.5793 | 1151553.0244 | 0 | 1151553.0244 | 0 | 1324285.9781
434 |  | Sikhulisiwe Primary | Primary |  |  | Capital Assets | Nkangala | Tweefontein South | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Construction of 6 Classrooms , administration block , library , kitchen , laboratory fence and 12 ablution facilities. Renovation and refurbishment of 16 existing classrooms. |  |  | C | 20658830.286 |  |  | 0 | 0 | 0 | 1456447.5352 | 17962852.9337 | 1239529.8172 | 0 | 206588.3029 | 0 | 237576.5483 | 0
435 |  | Entokozweni Secondary | Secondary | 800003838 |  | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 8 classrooms , Life Science Laboratory , Kitchen , Library , 12 toilets , 3 Sports Grounds and palisade fence. |  |  | C | 14673417.4771 |  |  | 0 | 0 | 0 | 0 | 1034475.9321 | 12758536.4963 | 880405.0486 | 0 | 146734.1748 | 0 | 168744.301
436 |  | Sithenjisiwe Secondary | Secondary | 800021386 |  | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Construction of administration block , library, Fence laboratory , kitchen, 3 Sports Grounds , Car Park and renovation of 16 classrooms. |  |  | C | 16739092.9149 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1180106.0505 | 14554641.2895 | 1004345.5749 | 0 | 167390.9291
437 |  | Masobye Primary | Primary | 800013045 |  | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP . Construction of administration block , library , Computer Centre , kitchen and Grade R Centre , 2 Sports Grounds ,Car Park. |  |  | C | 13102690.1895 |  |  | 0 | 0 | 0 | 0 | 923739.6584 | 11392789.1198 | 786161.4114 | 0 | 786161.4114 | 0 | 904085.6231
438 |  | Sukumani | Primary | 800022571 |  | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of administration block , library , Computer Centre , kitchen and Grade R Centre , 2 Sports Grounds ,Car Park. |  |  | C | 13102690.1895 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 923739.6584 | 11392789.1198 | 786161.4114 | 0
439 |  | Matempule Primary | Primary | 800003169 |  | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP.Construction of Grade R Centre , Administration block , Kitchen , Computer Centre , Car Park , 3 Sports Grounds and renovation of 16 classrooms. |  |  | C | 15796054.6209 |  |  | 0 | 0 | 0 | 0 | 0 | 1113621.8508 | 13734669.4929 | 947763.2773 | 0 | 157960.5462 | 0
440 |  | Sobantu Secondary | Secondary | 800021899 |  | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP.Completion of Administration block construnction of Kitchen , Computer Centre , Car Park , 3 Sports Grounds and renovation of 16 classrooms. |  |  | C | 10004408.6351 |  |  | 0 | 0 | 0 | 0 | 0 | 705310.8088 | 8698833.3082 | 600264.5181 | 0 | 100044.0864 | 0
441 |  | Ndayi Primary | Primary | 800016345 |  | Capital Assets | Nkangala | KwaMhlanga North East | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Construction of Grade R Centre , library , kitchen , fence and 12 ablution facilities. Renovation and refurbishment of 16 existing classrooms and 1 administration block. |  |  | C | 12547775.1817 |  |  | 0 | 0 | 0 | 0 | 884618.1503 | 10910290.5205 | 752866.5109 | 0 | 125477.7518 | 0 | 144299.4146
442 |  | Hlalakahle Secondary | Secondary | 800005223 |  | Capital Assets | Nkangala | Libangeni | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP - Planning and Design: Construction of administration block, computer centre, School Hall, kitchen, laboratory, 12 toilets, 3 Sports Grounds and Car Park and renovation of 16 classrooms. |  |  | C | 21586263.3568 |  |  | 0 | 0 | 0 | 1521831.5667 | 18769255.9887 | 1295175.8014 | 0 | 215862.6336 | 0 | 248242.0286 | 0
443 |  | Ziphakamiseni Secondary | Secondary | 800029629 |  | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Construction of 12 additional classrooms , library ,Fence laboratory , kitchen, ramp & rails , water , electricity , 3 Sports Grounds , Car Park and renovation of 15 classrooms. |  |  | C | 24347471.6151 |  |  | 0 | 0 | 0 | 0 | 0 | 1716496.7489 | 21170126.5693 | 1460848.2969 | 0 | 243474.7162 | 0
444 |  | Phumzile Secondary | S | 800018457 |  | Capital Assets | Nkangala | Tweefoontein North | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Construction of administration block , library ,Fence laboratory , kitchen, 3 Sports Grounds , Car Park and renovation of 16 classrooms. |  |  | C | 16477348.9149 |  |  | 0 | 0 | 0 | 0 | 1161653.0985 | 14327054.8815 | 988640.9349 | 0 | 164773.4891 | 0 | 189489.5125
445 |  | Sibongimpumelelo Primary | Primary | 800020727 |  | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Construction of administration block , library ,Fence laboratory , kitchen, 3 Sports Grounds , Car Park and renovation of 16 classrooms. |  |  | C | 16477348.9149 |  |  | 0 | 0 | 1161653.0985 | 14491828.3707 | 823867.4457 | 0 | 82386.7446 | 0 | 94744.7563 | 0 | 108956.4697
446 |  | LD Moetanalo Secondary | Secondary | 800029330 |  | Capital Assets | Nkangala | Steve Tshwete 1 | Steve Tshwete |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 8 classrooms , Life Science Laboratory , Kitchen , Library , 12 toilets , fence, 3 Sports Grounds and palisade fence. |  |  | C | 14398591.8148 |  |  | 0 | 0 | 0 | 0 | 1015100.7229 | 12519575.583 | 863915.5089 | 0 | 143985.9181 | 0 | 165583.8059
447 |  | Sothembani Primary | Primary | 800022194 |  | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Demolition of 5 unsafe classrooms , Construction of 5 classrooms , administration block, library , laboratory , kitchen , fence , 12 ablution facilities, car park and 2 sports grounds . Renovation of 8 classrooms. |  |  | C | 19125030.3433 |  |  | 0 | 0 | 0 | 1348314.6392 | 16629213.8835 | 1147501.8206 | 0 | 191250.3034 | 0 | 219937.8489 | 0 | 1147501.8206
448 |  | Zakheni Secondary | S | 800031088 |  | Capital Assets | Nkangala | kwaMhlanga S/W | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of administration block , library , kitchen , 12 toilets , 2 Sports Grounds and Car Park. Renovation of existing 16 classrooms. |  |  | C | 13817028.9343 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 974100.5399 | 12158985.4622 | 829021.7361 | 0
449 |  | Vukuzame Secondary | S | 800024885 |  | Capital Assets | Nkangala | Tweefontein North | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 3 additional classrooms , 1 administration block , 1 library , kitchen , School hall , 3 sports grounds and car park. Renovation of existing 16 classrooms , computer cenre and laboratory. |  |  | C | 21637053.0246 |  |  | 0 | 0 | 0 | 0 | 1525412.2382 | 18813417.6049 | 1298223.1815 | 0 | 216370.5302 | 0 | 248826.1098
450 |  | Ramodiegi Primary | P | 800019075 |  | Capital Assets | Nkangala | Weltevrede | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of administration block , library ,computer centre Grade R Centre , fence and 12 ablution facilities.Refurbishment and renovation of 7 existing classrooms. |  |  | C | 15260806.6366 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075886.8679 | 13269271.3705 | 915648.3982 | 0
451 |  | Makerana Primary | Primary | 800011841 |  | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of administration block , library , Kitchen , Computer Centre , Grade R Centre , fence and 12 ablution facilities.Refurbishment and renovation of 16 classrooms. |  |  | C | 18587039.9176 |  |  | 0 | 0 | 0 | 0 | 1310386.3142 | 16161431.2083 | 1115222.3951 | 0 | 185870.3992 | 0 | 213750.9591
452 |  | Poolzee Combined | Combined | 800018655 |  | Capital Assets | Nkangala | Steve Tshwete 3 | Steve Tshwete |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 5 Classrooms , administration block , laboratory, library, Kitchen, Fence, Car park and 2 Sports Grounds and refurbishment of 13 classrooms. |  |  | C | 19140625.6152 |  |  | 0 | 0 | 0 | 0 | 1349414.1059 | 16642773.9724 | 1148437.5369 | 0 | 191406.2562 | 0 | 220117.1946
453 |  | Sizamakwethu Primary | Primary | 800007740 |  | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Construction of administration block , library , computer centre , kitchen , fence and 12 ablution facilities. Renovation and refurbishment of 16 existing classrooms . |  |  | C | 16186947.3136 |  |  | 0 | 0 | 0 | 0 | 0 | 1141179.7856 | 14074550.6892 | 971216.8388 | 0 | 161869.4731 | 0
454 |  | Zidobhele Secondary | Secondary | 800025916 |  | Capital Assets | Nkangala | Tweefontein South | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 4 classrooms , 1 administration block , library , laboratory , computer centre , School Hall , kitchen , 1 fence , 12 toilets , car park and 2 sports grounds. |  |  | C | 23691400.1896 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1670243.7134 | 20848432.1668 | 1421484.0114 | 0
455 |  | Musi Primary | Primary | 800016030 |  | Capital Assets | Nkangala | KwaMhlanga S/W | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of Grade R facilities, library , Kithchen , Computer Centre , Fence , ramp & rails . |  |  | C | 14089765.1895 |  |  | 0 | 0 | 0 | 0 | 993328.4459 | 12251050.8323 | 845385.9114 | 0 | 140897.6519 | 0 | 162032.2997
456 |  | Andries Mashile Primary | Primary | 800000273 |  | Capital Assets | Nkangala | Mmametlhake | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 3 classrooms , 1 administration block , library , kitchen , 1 fence , 12 toilets , car park and 2 sports grounds. |  |  | C | 14110981.8496 |  |  | 0 | 0 | 0 | 994824.2204 | 13405432.7571 | 705549.0925 | 0 | 141109.8185 | 0 | 162276.2913 | 0
457 |  | Mafa Max Motloung | Secondary | 800029397 |  | Capital Assets | Nkangala | Victor Khanye | Victor Khanye |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 3 classrooms , laboratory , library , kitchen , 1 fence , 12 toilets , car park and 2 sports grounds. |  |  | C | 10937550.2017 |  |  | 0 | 0 | 0 | 0 | 0 | 771097.2892 | 9510199.9004 | 656253.0121 | 0 | 109375.502 | 0
458 |  | Nkosiphile Primary | Primary | 800017053 |  | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Demolition of 5 unsafe classrooms , Construction of 5 classrooms , administration block , kitchen , fence , 12 ablution facilities, car park and 2 sports grounds . Renovation of 8 classrooms. |  |  | C | 15934711.066 |  |  | 0 | 0 | 0 | 0 | 0 | 1123397.1302 | 13855231.2719 | 956082.664 | 0 | 159347.1107 | 0
459 |  | Somlingo Primary | Primary | 800022061 |  | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | CRDP. Construction of a library , kitchen , fence and 12 ablution facilities. Renovation and refurbishment of 16 existing classrooms and 1 administration block. |  |  | C | 10147682.5777 |  |  | 0 | 0 | 0 | 0 | 0 | 715411.6217 | 8823410.0013 | 608860.9547 | 0 | 101476.8258 | 0
460 |  | Hlonipha Secondary | S | 800005454 |  | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of 4 additional classrooms , library , kitchen , computer centre 1 fence , 12 toilets , car park and 3 sports grounds. Renovation and refurbishment of 16 existing classrooms , 1 administration block and laboratory. |  |  | C | 16596798.2212 |  |  | 0 | 0 | 0 | 0 | 1170074.2746 | 14430916.0533 | 995807.8933 | 0 | 165967.9822 | 0 | 190863.1795
461 |  | Somtshongweni Primary | Primary | 800022095 |  | Capital Assets | Nkangala | Kwaggafontein East | Thembisile Hani | CRDP | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of Grade R Centre , administration block , library , kitchen , fence , ablution facilities and renovation and refurbishment of 16 existing classrooms. |  |  | C | 16809366.5383 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1185060.3409 | 14615744.205 | 1008561.9923
462 |  | Mpilonhle Primary | Primary | 800015602 |  | Capital Assets | Nkangala | Emakhazeni | eMakhazeni |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of Grade R Centre , administration block , library , kitchen , fence . Renovation and refurbishment of 20 existing classrooms and 24 existing ablution facilities . |  |  | C | 16886461.8102 |  |  | 0 | 0 | 0 | 0 | 1190495.5576 | 14682778.544 | 1013187.7086 | 0 | 168864.6181 | 0 | 194194.3108
463 |  | Mapule Sindane | Primary | 800012575 |  | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of a kitchen, fence. Renovation and refurbishment of 23 existing classrooms and 18 existing ablution facilities. |  |  | C | 8596168.281 |  |  | 0 | 0 | 0 | 0 | 606029.8638 | 7990138.4172 | 0 | 85961.6828 | 0 | 98855.9352 | 0
464 |  | Siyathokoza Primary | Primary | 800029447 |  | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni |  | Upgrades & Additions | Upgrades and Additions | Public Ordinary Schools |  | Construction of Grade R Centre , 3 classrooms , library , kitchen , 16 toilets . Renovation and refurbishment of 20 existing classrooms and 24 existing ablution facilities . |  |  | C | 14088259.673 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 993222.3069 | 12249741.7857 | 845295.5804 | 0 | 140882.5967
465 |  | Lehlaka Combined | Combined | 800010058 |  | Capital Assets | Nkangala | eMalahleni 3 | eMalahleni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 16 classrooms , library , laboratory and computer centre. Construction of kitchen , fence , car park and 3 sports grounds. |  |  | A | 9314488.281 |  |  | 0 | 3260070.8983 | 6054417.3827 | 0 | 93144.8828 | 0 | 107116.6152 | 0 | 123184.1075 | 0 | 141661.7236
466 |  | Nyabela Primary | Primary | 800017475 |  | Capital Assets | Nkangala | Kwagga West | Thembisile Hani | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP. Renovations of 16 classrooms, Administration Block, and Construction of 12 toilets , 2 sports grounds , fence and Car Park . |  |  | C | 8406829.7281 |  |  | 0 | 0 | 0 | 0 | 0 | 592681.4958 | 7309738.4486 | 504409.7837 | 0 | 84068.2973 | 0
467 |  | Duduzile Secondary | Secondary | 800002873 |  | Capital Assets | Nkangala | Siyabuswa | Dr JS Moroka | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 16 classrooms , administration block , Laboratory , Library , 1 School Hall , and Construction of kitchen , 12 ablution facilities fence , Car Park and 2 Sports grounds. |  |  | A | 10847463.0091 |  |  | 0 | 3796612.0532 | 7050850.9559 | 0 | 108474.6301 | 0 | 124745.8246 | 0 | 143457.6983 | 0 | 164976.353
468 |  | Botleng Secondary School | S | 800001636 |  | Capital Assets | Nkangala | Victor Khanye | Victor Khanye |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 33 classrooms , 1 administration block , Library , 4 laboratories , 1 Computer Centre , 9 ablution blocks and Construction of kitchen , School Hall and 2 Sports grounds. |  |  | A | 16165950.885 |  |  | 0 | 5658082.8098 | 10507868.0752 | 0 | 161659.5089 | 0 | 185908.4352 | 0 | 213794.7005 | 0 | 245863.9055
469 |  | Sibukosethu Primary | Primary | 800020776 |  | Capital Assets | Nkangala | eMalahleni 1 | eMalahleni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 25 classrooms , administration block , Library , 1 School Hall , 35 toilets and Construction of Grade R Centre kitchen , fence , Car Park and 2 Sports grounds. |  |  | C | 14296350.885 |  |  | 0 | 0 | 0 | 0 | 0 | 1007892.7374 | 12430677.0945 | 857781.0531 | 0 | 142963.5089 | 0
470 |  | Zithuthukiseni Primary | Primary | 800026039 |  | Capital Assets | Nkangala | Tweefontein North | Thembisile Hani | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP. Renovation of existing 16 classrooms , administration block , construction of library , library , Kitchen , 2 sports grounds , car park and fence. |  |  | C | 10179267.8496 |  |  | 0 | 0 | 0 | 0 | 0 | 717638.3834 | 8850873.3952 | 610756.071 | 0 | 101792.6785 | 0
471 |  | Ebhudlweni | Primary | 800003079 |  | Capital Assets | Nkangala | Emakhazeni | Emakhazeni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovations of 35 classrooms , administration block, library and 17 toilets. Construction of kitchen , computer centre fence , car park and 3 sports grounds. |  |  | A | 15630861.6603 |  |  | 0 | 5470801.5811 | 10160060.0792 | 0 | 156308.6166 | 0 | 179754.9091 | 0 | 206718.1455 | 0 | 237725.8673
472 |  | Mmutle Primary | P | 800014753 |  | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP. Renovation of 10 classrooms , and construction of administration block , library , kitchen , 12 ablution facilities , 2 sports grounds , car park and fence. |  |  | C | 14191563.9343 |  |  | 0 | 0 | 1000505.2574 | 12481480.4802 | 709578.1967 | 0 | 70957.8197 | 0 | 81601.4926 | 0 | 93841.7165
473 |  | Siphendulwe Primary | Primary | 800021261 |  | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Construction of administration block , kitchen , library , 2 sports grounds , car park and renovation of 24 classrooms. |  |  | C | 14533724.2062 |  |  | 0 | 0 | 0 | 0 | 0 | 1024627.5565 | 12637073.1973 | 872023.4524 | 0 | 145337.2421 | 0
474 |  | Dumeleni Secondary | Secondary | 800002907 |  | Capital Assets | Nkangala | Kwagga West | Thembisile Hani | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP. Renovation of 16 classrooms , administration block , toilets , laboratory and construction of library , 2 sports grounds , car park and fence. |  |  | C | 9583634.5686 |  |  | 0 | 0 | 0 | 0 | 675646.2371 | 8332970.2574 | 575018.0741 | 0 | 95836.3457 | 0 | 110211.7975
475 |  | P Ndimande Secondary | Secondary | 800000283 |  | Capital Assets | Nkangala | Emalahleni 2 | eMalahleni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovation and refurbishment of existing classrooms , administration block , library , laboratory ablution facilities. |  |  | C | 8056500 |  |  | 0 | 0 | 0 | 0 | 0 | 567983.25 | 7005126.75 | 483390 | 0 | 80565 | 0
476 |  | Itireleng Primary | Primary | 800006833 |  | Capital Assets | Nkangala | eMalahleni 1 | eMalahleni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment and renovation of 18 classrooms , 1 administration block , fence , 22 ablution facilities and construction of library , kitchen , car park and 2 sports grounds. |  |  | C | 10801032.8496 |  |  | 0 | 0 | 761472.8159 | 10039560.0337 | 0 | 108010.3285 | 0 | 124211.8778 | 0 | 142843.6594 | 0
477 |  | Nancy Shiba | Primary | 800016246 |  | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment and renovation of 23 classrooms , 1 administration block , fence , 18 ablution facilities and construction of kitchen , 2 sports grounds and car park. |  |  | C | 10217923.281 |  |  | 0 | 0 | 0 | 0 | 720363.5913 | 9497559.6897 | 0 | 0 | 102179.2328 | 0 | 117506.1177
478 |  | Zidli Primary | P | 800025908 |  | Capital Assets | Nkangala | Tweefontein North | Thembisile Hani | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP. Renovation of 10 classrooms , and construction of administration block , library , kitchen , 12 ablution facilities , 2 sports grounds , car park and fence. |  |  | C | 30182178.9343 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2127843.6149 | 26560317.4622 | 1810930.7361 | 0
479 |  | Tsiki Naledi Secondary | Secondary | 800023986 |  | Capital Assets | Nkangala | Steve Tshwete 2 | Steve Tshwete |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment and renovation of 16 classrooms , 1 administration block , fence , sports facilities , 18 ablution facilities and construction of kitchen |  |  | A | 18403934.2182 |  |  | 0 | 6441376.9764 | 11962557.2418 | 0 | 184039.3422 | 0 | 211645.2435 | 0 | 243392.03 | 0 | 279900.8345
480 |  | Ukhwezi Primary | Primary | 800024133 |  | Capital Assets | Nkangala | Emakhazeni | Emakhazeni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment and renovation of 30 classrooms , 1 administration block , fence , 22 ablution facilities and construction of Grade R Centre , library , kitchen , car park and 2 sports grounds. |  |  | A | 14345025.4536 |  |  | 0 | 5020758.9088 | 9324266.5448 | 0 | 143450.2545 | 0 | 164967.7927 | 0 | 189712.9616 | 0 | 218169.9059
481 |  | Gugulethu Primary | Primary | 800007922 |  | Capital Assets | Nkangala | Tweefontein S | Thembisile Hani | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP. Renovation of 16 classrooms , administration block and construction of library , 12 toilets , 2 sports grounds , car park and fence. |  |  | C | 10109239.2967 |  |  | 0 | 0 | 0 | 0 | 0 | 712701.3704 | 8789983.5685 | 606554.3578 | 0 | 101092.393 | 0
482 |  | Njomane Primary | Primary | 800019631 |  | Capital Assets | Nkangala | Kwagga West | Thembisile Hani | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP. Renovation of 16 classrooms , construction of administration block , toilets , Grade R Centre , library , 2 sports grounds , car park and fence. |  |  | A | 17923827.9854 |  |  | 0 | 6273339.7949 | 11650488.1905 | 0 | 179238.2799 | 0 | 206124.0218 | 0 | 237042.6251 | 0 | 272599.0189
483 |  | Dikotelo Primary | Primary | 800002543 |  | Capital Assets | Nkangala | Nokaneng | Dr JS Moroka | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | CRDP. Renovation of 15 classroom, 1 administration block. Construction of kitchen, library , Computer Centre , 2 Sports Grounds , Car Park and Fence |  |  | A | 11723241.2289 |  |  | 0 | 4103134.4301 | 7620106.7988 | 0 | 117232.4123 | 0 | 134817.2741 | 0 | 155039.8653 | 0 | 178295.845
484 |  | Khonzimfundo C | C | 800007757 |  | Capital Assets | Nkangala | eMalahleni 1 | eMalahleni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 24 classrooms, 1 administration block , 1 library , 1 kitchen , 1 school hall and 24 toilets. |  |  | C | 7515300 |  |  | 0 | 0 | 0 | 0 | 529828.65 | 6534553.35 | 450918 | 0 | 75153 | 0 | 86425.95
485 |  | Mandlethu Secondary | Secondary | 800012229 |  | Capital Assets | Nkangala | Tweefontein N | Thembisile Hani | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 16 classrooms, 1 administration block , 1 library , 1 laboratory 12 toilets. |  |  | C | 5104500 |  |  | 0 | 0 | 0 | 0 | 359867.25 | 4744632.75 | 0 | 51045 | 0 | 58701.75 | 0
486 |  | Hoerskool Delmas | Secondary | 800005769 |  | Capital Assets | Nkangala | Victor Khanye | Victor Khanye |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 17 classrooms, 1 administration block , 1 library , 1 kitchen , 2 computer centres , 4 laboratories , 1 school hall and existing toilets. |  |  | A | 8462400 |  |  | 0 | 2961840 | 5500560 | 0 | 84624 | 0 | 97317.6 | 0 | 111915.24 | 0 | 128702.526
487 |  | Hoerskool Kanonkop | Secondary | 800005843 |  | Capital Assets | Nkangala | Steve Tswete 3 | Steve Tshwete |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 17 classrooms, 1 administration block , 1 library , 1 kitchen , 2 computer centres , 4 laboratories , 1 school hall and existing toilets. |  |  | A | 6494400 |  |  | 0 | 2273040 | 4221360 | 0 | 64944 | 0 | 74685.6 | 0 | 85888.44 | 0 | 98771.706
488 |  | Thulani Primary | Primary | 800023366 |  | Capital Assets | Nkangala | KwaMhlanga S/W | Thembisile Hani | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 16 classrooms , . Construction of administration block , Library , Computer Centre Grade R Centre kitchen , fence , Car Park and 2 Sports grounds. |  |  | A | 18880369.1895 |  |  | 0 | 6608129.2163 | 12272239.9732 | 0 | 188803.6919 | 0 | 217124.2457 | 0 | 249692.8825 | 0 | 287146.8149
489 |  | Khamane Secondary | Secondary | 800007583 |  | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 24 classroom , administration block , Library , Computer Centre , fence , and construction of kitchen , Car Park and 2 Sports grounds. |  |  | A | 10736928.3 |  |  | 0 | 3757924.905 | 6979003.395 | 0 | 107369.283 | 0 | 123474.6754 | 0 | 141995.8768 | 0 | 163295.2583
490 |  | Sibis Primary | Primary | 800020669 |  | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Renovation and refurbishment of 10 classrooms , construction of Grade R Centre , administration block , 10 ablution facilities, fence and computer centre. |  |  | A | 14230936.28 |  |  | 0 | 4980827.698 | 9250108.582 | 0 | 142309.3628 | 0 | 163655.7672 | 0 | 188204.1323 | 0 | 216434.7521
491 |  | Mabande Secondary | Secondary | 800011049 |  | Capital Assets | Nkangala | eMalahleni 2 | eMalahleni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 32 classroom , administration block , Library , Computer Centre , fence , technical centres and construction of kitchen , Car Park and 2 Sports grounds. |  |  | C | 12606528.3 |  |  | 0 | 0 | 0 | 0 | 888760.2451 | 11717768.0549 | 0 | 126065.283 | 0 | 144975.0755 | 0
492 |  | Imemeza Secondary | Secondary | 800006189 |  | Capital Assets | Nkangala | Emakhazeni | Emakhazeni |  | Rehabilitation, Renovation & Refurbishment | Refurbishment and Renovations | Public Ordinary Schools |  | Refurbishment of existing 20 classroom , administration block, Library, fence, and construction of kitchen , Car Park and 2 Sports grounds. |  |  | C | 9470028.3 |  |  | 0 | 0 | 0 | 0 | 667636.9951 | 8234189.6069 | 568201.698 | 0 | 94700.283 | 0 | 108905.3255
493 |  | Ext 24 Primary School ( New) | p | New |  | Capital Assets | Nkangala | Steve Tshwete 2 | Steve Tshwete |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 43025355.8489 |  |  | 0 | 0 | 0 | 0 | 0 | 3033287.5873 | 37410546.9106 | 2581521.3509 | 0 | 430253.5585 | 0
494 |  | New Klarinet Primary School | p | New |  | Capital Assets | Nkangala | eMalahleni 1 | eMalahleni |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 43025355.8489 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3033287.5873 | 37410546.9106 | 2581521.3509 | 0 | 430253.5585
495 |  | Mountainview Primary ( New School) | p | New |  | Capital Assets | Nkangala | KwaMhlanga S/W | Thembisile Hani | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 43025355.8489 |  |  | 0 | 0 | 0 | 0 | 0 | 3033287.5873 | 37410546.9106 | 2581521.3509 | 0 | 430253.5585 | 0
496 |  | Kwaguqa New Primary | p | New |  | Capital Assets | Nkangala | EMalahleni 3 | eMalahleni |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Construction of a Grade R Centre, 24 Classrooms, administration block, library, computer centre, 36 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 43025355.8489 |  |  | 0 | 0 | 0 | 0 | 3033287.5873 | 37410546.9106 | 2581521.3509 | 0 | 430253.5585 | 0 | 494791.5923
497 |  | De Beersprut ( New School) | p | New |  | Capital Assets | Nkangala | Marapyane | Dr JS Moroka | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Construction of 16 Classrooms, administration block, library, computer centre, 26 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 33869639.1141 |  |  | 0 | 0 | 0 | 0 | 0 | 2387809.5575 | 29449651.2097 | 2032178.3468 | 0 | 338696.3911 | 0
498 |  | New Primary (Sheldon ) | p | New |  | Capital Assets | Nkangala | KwaMhlanga N/E | Thembisile Hani | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Construction of 16 Classrooms, administration block, library, computer centre, 26 toilets, fence, electricity, water, school hall, kitchen, 3 sports grounds and car park. |  |  | C | 33409004.1141 |  |  | 0 | 0 | 0 | 0 | 0 | 2355334.79 | 29049129.0772 | 2004540.2468 | 0 | 334090.0411 | 0
499 |  | Langa | S | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | Khulangwane | Nkomazi | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of 16 Classrooms, administration block, laboratory, library, computer centre, 20 toilets, School Hall, Electricity, Water, Ramps and Rails, 2 Sports Grounds & Car Park. |  |  | C | 32330008.1778 |  |  | 0 | 0 | 0 | 0 | 2279265.5765 | 28110942.1106 | 1939800.4907 | 0 | 323300.0818 | 0 | 371795.094
500 |  | Shabalala | S | New | Education Infrastructure Grant (EIG) | Capital Assets | Ehlanzeni | White Hazy | Mbombela |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of 20 Classrooms, administration block, laboratory, library, computer centre, 30 toilets, School Hall, Elelctricity, Water, Ramps and Rails, 2 Sports Grounds & Car Park. |  |  | C | 44982735.6848 |  |  | 0 | 0 | 3171282.8658 | 39562316.0348 | 2249136.7842 | 0 | 224913.6784 | 0 | 258650.7302 | 0 | 297448.3397
501 |  | Volksrust Primary School | P | 800024711 | Equitable Share (ES) | Capital Assets | Gert Sibande | Volksrust | Dr Pixley ka Isaka Seme | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of Grade R Centre, 24 Classrooms, Administration block, library, computer centre, 30 Toilets, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. (PHASE 2) |  |  | C | 34159222.5817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2408225.192 | 30060115.8719 | 2049553.3549 | 0
502 |  | New Daggakraal Primary | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Wakkerstroom | Dr Pixley ka Isaka Seme | CRDP | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of Grade R Centre, 24 Classrooms, Administration block, library, computer centre, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. |  |  | C | 37186252.5817 |  |  | 0 | 0 | 2621630.807 | 32705309.1456 | 1859312.6291 | 0 | 185931.2629 | 0 | 213820.9523 | 0 | 245894.0952
503 |  | New Primary(Hlanganani) | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Highveldridge East | Govan Mbeki |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of Grade R Centre, 24 Classrooms, Administration block, library, computer centre, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. |  |  | C | 37186252.5817 |  |  | 0 | 0 | 2621630.807 | 32705309.1456 | 1859312.6291 | 0 | 185931.2629 | 0 | 213820.9523 | 0 | 245894.0952
504 |  | New Secondary School | S | New | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Highveldridge East | Govan Mbeki |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of 28 Classrooms, Administration block, laboratory, library, computer centre, School Hall, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. |  |  | C | 44982735.6848 |  |  | 0 | 0 | 3171282.8658 | 39562316.0348 | 2249136.7842 | 0 | 224913.6784 | 0 | 258650.7302 | 0 | 297448.3397
505 |  | ThusiVille Primary | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Ermelo1 | Msukaligwa |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of Grade R Centre, 24 Classrooms, Administration block, laboratory, library, computer centre, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. |  |  | C | 38827912.2904 |  |  | 0 | 0 | 2737367.8165 | 34149148.8594 | 1941395.6145 | 0 | 194139.5615 | 0 | 223260.4957 | 0 | 256749.57
506 |  | New Primary (Ethandukukhanya | P | New | Education Infrastructure Grant (EIG) | Capital Assets | Gert Sibande | Stanwest | Lekwa |  | New & Replacement Schools | New Schools | Public Ordinary Schools |  | Planning and Design: Construction of Grade R Centre, 24 Classrooms, Administration block, laboratory, library, computer centre, 30 Toilets, Fence, Electricity, Water, Kitchen, ramps + rails, 3 Sports Grounds and Car Park. |  |  | C | 38827912.2904 |  | 0 | 0 | 0 | 0 | 2737367.8165 | 34149148.8594 | 1941395.6145 | 0 | 388279.1229 | 0 | 446520.9913 | 0
[19 empty] | 7386931785.8817 |  | 12000000 | 561870754.2237 | 1105968400.8083 | 1308982054.6118 | 1251782198.0764 | 1460117891.6858 | 1155060719.62 | 811124797.9736 | 430802817.8906 | 421770956.9879 | 321029574.767 | 369359204.3714
Complied: |  |  |  |  | Ms NN Ntuli |  |  | Department of Education - PRFP - Deputy Director
Recommended / Not Recommended: |  |  |  |  | Ms NN Ntuli |  |  | Department of Education - PRFP - Acting Director
Approved / Not Approved: |  |  |  |  | Mrs MOC Mhlabane |  |  | Department of Education - Head of Department
Formulas:
START DATE = +[START DATE, row above]
END DATE = +[END DATE, row above]
Note on T46: sinugo: NO BUDGET.IDT TO CONFIRM
Note on V47: sinugo: begind scheduel. Non payment. Its a new school IDT
Note on V90: sinugo: ready for tender but reprioritize for 2014/15 need to chek 612, what for?
Note on V91: sinugo: planning
Note on T97: sinugo: TO BE CONFIRMED
Note on C220: Mpeps: