## DBE Communication Dashboard
STATUS REPORT _ ASIDI PHASE 1
Project Group | Project Name | School District | School Enrolment 2014 | Outputs | Site Handover | Planned Project Practical Completion (Batch 1) | Anticipated Sectional PC 1 dates | Benefical Occupation PC1 Achieved | Actual/Anticipated 2nd Sectional Practical Completion date | Anticipated 3rd Sectional Practical Completion date | Anticipated 4th Sectional Practical Completion date | % Project Completion based on work completed | Comments
A 1 | Delta Primary School | Metro South | Grade R = 87 Grade 1-7 = 771 Total Learners = 858 | Classroom = 5 (new) 17 (renovated) Grade R = 4 Speacialist Classroom = 4 Admin Block = Renovation GP Hall = New Build Feeding Kitchen = Yes | 2013-03-04 | 2014-02-25 | 2014-03-31 | 2014-05-06 | 2015-03-30 | N/A | N/A | 95% | * EOT claims adjudicated but still not approved by WCED & DBE. All three school have reached beneficial occupation. The next phase entails removing the temporary mobile units and resurfacing the new sports field. PC2 has been reached at Sophumelela SS on the 12 Dec 2014.
| Die Duine Primary School | Metro South | Grade R = 65 Grade 1-7 = 637 Total learners = 702 | Classroom = 25 Grade R = 4 Speacialist Classroom = 4 Admin Block = New Build GP Hall = New Build Feeding Kitchen = Yes | 2013-03-04 | 2014-02-07 | 2014-04-30 | 2014-06-23 | 2015-11-30 | N/A | N/A | 98%
| Sophumelela Secondary School | Metro South | Total Learners = 1143 | Classroom = 30 Speacialist Classroom = 8 Admin Block = Renovated GP Hall = Renovated Feeding Kitchen = Yes | 2013-03-04 | 2014-02-25 | 2014-04-30 | 2014-07-16 | 2014-12-12 | N/A | N/A | 100%
A 2 | Hawston Primary School | Overberg | Grade R = 123 Grade 1-7 = 937 Total learners = 1060 | Classroom = 28 Grade R = 2 (new) 2 existing Speacialist Classroom = 4 Admin Block = New Build GP Hall = New Build Feeding Kitchen = Yes | 2013-03-11 | 2014-01-10 | 2014-05-28 | 2014-07-22 | 2015-03-15 | N/A | N/A | 85% | * EOT claims adjudicated but still not approved by WCED & DBE. Second phase entails completing the new Multi-purpose Hall, Admin block and sports field. The has been a work stop instruction order by the PA in order to resolve the dispute between Structural Engineer and the contractor (Ruwacon) This will create a new delay but we expect work to continue in the next two weeks.
A 3 | Heideveld Primary School | Metro Central | Grade R = 60 Grade 1-7 = 750 Total Learners = 810 | Classroom = 23 Speacialist Classroom = 4 Admin Block = New Build GP Hall = New Build Feeding Kitchen = Yes | 2013-03-11 | 2014-03-31 | 2014-08-30 | 2014-08-27 | 2014-11-30 | N/A | N/A | 95% | * EOT claims adjudicated but still not approved by WCED & DBE. Kensington SS has reached PC2 on the 16 Jan 2015. Portia and Heideveld PS are currently working towards PC2.
| Kensington Secondary School | Metro Central | Total Learners = 1230 | Classroom = 39 Speacialist Classroom = 8 Admin Block = New Build GP Hall = Renovation Feeding Kitchen = Yes | 2013-03-11 | 2014-02-28 | 2014-04-04 | 2014-05-10 | 2015-01-16 | N/A | N/A | 100%
| Portia Primary School | Metro Central | Grade R = 59 Grade 1-7 = 577 Total Learners = 636 | Classroom = 23 Grade R = 2 Speacialist Classroom = 4 Admin Block = New Build GP Hall = New build Feeding Kitchen = Yes | 2013-03-11 | 2014-02-28 | 2014-08-15 | 2014-08-07 | 2014-11-30 | N/A | N/A | 95%
A 4 | Kasselvlei Primary School | Metro North | Grade R = 60 Grade 1-7 = 975 Total Learners = 1036 | Classroom = 22 Grade R = 5 Speacialist Classroom = 4 Admin Block = New build GP Hall = New Build Feeding Kitchen = Yes | 2013-03-19 | 2014-12-12 | 2015-01-29 | 2015-02-09 | 2015-04-30 | N/A | N/A | 75% | Construction contract has been cancelled and we are awaiting the conclusion of the procurment process and the appointment of the new contractor. The site hand over date is expected for 27 February 2014. PC 1 has been reached on Kasselsvlei PS on the 29 Jan 2015. Expecting PC1 on Valhalla PS by the 13 Feb 2015.
| Sophakama Primary School | Metro North | Grade R = 61 Grade 1-7 = 975 Total Learners = 1036 | Classroom = 30 Grade R = 3 Speacialist Classroom = 4 Admin Block = New Build GP Hall = New Build Feeding Kitchen = Yes | 2013-04-29 | 2014-12-12 | 2015-04-30 |  | 2015-07-30 | N/A | N/A | 60%
| Valhalla Primary School | Metro North | Grade R = 61 Grade 1-7 = 975 Total Learners = 1036 | Classroom = 28 Grade R= 3 Speacialist Classroom = 4 Admin Block = New Build GP Hall = New Build Feeding Kitchen = Yes | 2013-03-19 | 2014-12-12 | 2015-02-15 | 2015-02-13 | 2015-06-30 | N/A | N/A | 75%
A 5 | Knysna Secondary School | Eden Karoo | Total Leaners = 1576 | Classroom = 27 (new) 17 (renovate) Speacialist Classroom = 8 Admin Block = New Build GP Hall = Existing Structure Feeding Kitchen = Yes | 2012-12-13 | 2015-02-13 | 2013-05-30 | 2013-08-16 | 2014-06-04 | 2014-10-06 | 2015-02-27 | 98% | * Knysna Secondary is the multi-phase ASIDI school and has already reached PC1 date on 16 Aug 2013. EOT claims adjudicated but still not approved by WCED & DBE. PC 2 was achieved on the 4th June 2014. PC 3 which included the refurbishment of the last block of classrooms and abultion block has been reach on the 6th Oct 2014. Final PC4 which includes the new PT slabs and the resurfacing and landscaping of the sportfieldis expected to be reached by the end of Feb 2015.
A 6 | Parkview Primary School | Metro North | Grade R = 88 Grade 1-7 = 743 Total Learners = 831 | Classroom = 21 Grade R = 3 Speacialist Classroom = 4 Admin Block = New Build GP Hall = New Build Feeding Kitchen = Yes | 2013-03-18 | 2014-03-14 | 2015-08-30 |  | 2015-10-30 | N/A | N/A | 50% | Limited bid with Haw & Inglis are in process. Filcon has been cancelled and the final account is in process. Project is currently in tender negotiation, the expected site handover is 15th Nov 2014. The site was taken over by Haw & Inglis and is currently under construction.
| Wesfleur Primary School | Metro North | Grade R = 126 Grade 1-7 = 1193 Total learners = 1193 | Classroom = 33 Grade R = 6 Speacialist Classroom = 4 Admin Block = New Build GP Hall = New Build Feeding Kitchen = Yes | 2013-03-18 | 2014-02-03 | 2015-08-30 |  | 2015-10-30 | N/A | N/A | 50%
| Willemsvlei Primary School | West Coast | Grade R = 39 Grade 1-9 = 1554 Total learners = 1093 | Classroom = 29 Grade R = 3 Speacialist Classroom = 4 Admin Block = New Build GP Hall = New Build Feeding Kitchen = Yes | 2013-03-18 | 2014-02-03 | 2015-06-30 |  | 2015-10-30 | N/A | N/A | 65%
Assumptions & Constraints
** These dates include pending, adjucated and approved EOT claims.
** Variances includes week days, weekend days and builders holiday.
** Highest rainfall figures in 8 years did have an impact conditions on site.
** Construction workers strike had an impact on delays on site.
** Overall community involvment in the programme has had an adverse impact on projects in certain areas.
** The new replacement construction for Group A4 will be procured and vetted. They should start construction by Jan 2014.
** PC 1 is the beneficial occupation of the new school building.
** PC 2 includes the demolition of existing school structures or the removal of temporary mobile units and the establishment of sports fields.
** PC 2 for Sophakama only entails the removal of the temporary mobile schools. This school has not space for sports fields.
Mitigation Strategy
** The Social Facilitation Consultant has had massive impact with reagrds to the continuity of the projects.
** Construction companies has committed to 6-7day working weeks to catch up to slipping programme. (Weather conditions has improved of late.)
** We expect a 6-7 month delay in the completion of Group A4, as result of cancellation of the contract with Vusela Construction and the appointment of the replacement contractor.
** Should the Group A6 contract be cancelled then we expect a 12 month delay to completion.
ASIDI BATCH TWO
** Please note that all 11 school projects are currently in construction phase.
Note on B11: Lucian Agulhas: DBE to hand over the school on the 25th October2014. The minister of DBE is expected to attend.
Note on B13: Lucian Agulhas: DBE site handover of school on the 16th October 2014.
Note on B15: Lucian Agulhas: DBE to hand over the school on the 30th October 2014