## Slide 1: North west bojana district
STRATEGIES FOR THE IMPROVEMENT OF MATHEMATICS IN THE SENIOR PHASE

## Slide 2: INDEX
1. Introduction
2. Maths – Grade 9 performance
3. Challenges At Under Performing Schools
4. Interventions
5. Progressed Learners Interventions
6. 1 + 4 Intervention Programme
7. LAIP

## Slide 3: 1.INTRODUCTION
Senior Phase – with special reference to Grade 9 has continuously performed poorly in the last 5 years
NPPPR requires t learners to perform at 40% in Maths in the Senior Phase
Learners in the senior phase are at the peak of their physiological and anatomical development and that affect their performance adversly
Hence rigorous interventions are needed in this phase to improve performance and lay proper foundation for the FET phase

## Slide 4: 2.MATHS – GRADE 9 PERFORMANCE
AREA OFFICE | NUMBER WROTE | NUMBPASSED | TERM 2 % PASS | TERM 2 AVE % | TERM 1 % PASS | TERM 1 AVE% | 2016 TARGET% PASS | AVERAGE
RTB | 5540 | 2222 | 40.11 | 40.2 | 42.3 | 44.3 | 55 | 42.2
Madibeng | 2791 | 1507 | 53.5 | 42 | 55 | 46 | 60 | 44
M K East | 697 | 259 | 37,5 | 41,3 | 27.3 | 32,9 | 55 | 42,1
M K West | 951 | 370 | 38.9 | 36.2 | 30,2 | 41.8 | 65 | 39
Letlhabile | 1852 | 910 | 49 | 40.6 | 32.4 | 32.3 | 60 | 36.5
Moretele | 2800 | 1134 | 40.5 | 43.7 | 32.8 | 31.8 | 50 | 37.6
District | 14631 | 6402 | 43.4 | 40.7 | 36.5 | 38.2 | 55 | 40.4

## Slide 5: 3. CHALLENGES AT UNDER PERFORMING SCHOOLS
It has been realised that in most under performing schools amongst others:
Teaching is horizontal and shallow in most topics.
Some topics are not taught because of content gaps on the side of educators.
Content coverage is a challenge every term because learners sit for quarterly formal assessment before the completion of ATPs

## Slide 6: 4.INTERVENTIONS
PLANNED ACTIVITIES | TIME FRAME | PROGRESS | CHALLENGES | REMEDIAL ACTIONS
Signing of pledges by grade 9 learners and parents to enhance commitment to the improvement of Maths performance | February 2016 | Circulars were sent to schools to ensure that pledges were signed by April 2016 | Not all schools were able to do the activity | Principals to ensure that the activity is done and collaboration with EMGD and QLTC structures
Item analysis to identify gaps – after each task Continuation of reference to Diagnostic report | Jan – Dec 2016 | Schools are beginning to analyse the results meaningfully | Not all schools are implementing | Training teachers on how to do item analysis and strengthening monitoring

## Slide 7: INTERVENTIONS CONT…..
PLANNED ACTIVITIES | TIME FRAME | PROGRESS | CHALLENGES | REMEDIAL ACTIONS
Utilization of NECT: National Education Collaboration Trust strategies to support none Fresh start schools | April – Nov 2016 | Change agents and subject advisors visiting schools together to support teachers | Availability of hard copies for training | Infuse NECT into AO plans for teachers to use planner and tracker

## Slide 8: INTERVENTIONS CONT…..
PLANNED ACTIVITIES | TIME FRAME | PROGRESS | CHALLENGES | REMEDIAL ACTIONS | TIME FRAME
Mental Maths Speed test | Every Friday from Jan – Nov 2016 | Implementation as planned | Not all schools are implementing | Strengthening monitoring | During school visits
Weekly test / topic test | Jan – Nov 2016 | Implementation as planned | Not all schools are implementing | Strengthening monitoring | During school visits
Effective use of workbooks | Jan – Nov 2016 | Implementation as planned | Shortages of workbooks | Strengthening monitoring | During school visits

## Slide 9: INTERVENTIONS CONT…….
PLANNED ACTIVITIES | TIME FRAME | PROGRESS | CHALLENGES | REMEDIAL ACTIONS | TIME FRAME
Showing teachers how to develop a good problem –solving question | Jan to Nov 2016 | Shown how to set questions using different cognitive levels during school visits | Inability to develop quality problem-solving questions | Conduct workshop Incorporating the Japanese International Cooperation Agencies (JICA) programme | 4 hours in one day
Guiding teachers on how to develop love of Maths by contextualising lessons( real life situation) | Jan to Nov 2016 | Challenge teacher to identify everyday things/situations within their environment to link with current lesson | Teachers still struggling to use real-life situations to teach Mathematics |  | 

## Slide 10: INTERVENTIONS CONT…..
PLANNED ACTIVITIES | TIME FRAME | PROGRESS | CHALLENGES | REMEDIAL ACTIONS
The teaching of word problems should emphasize : Reading with comprehension by underlining and explaining keywords Translating key phrases from English into Mathematical sentences Identifying appropriate operations in Mathematical expressions Explaining and justifying the process and the product in calculations | Jan – Nov 2016 | Learners have shown improvement in tackling most Maths problems | Problem solving in the workbooks is seldom handled during lessons | Intensive use of workbooks and JICA material.

## Slide 11: INTERVENTIONS CONT……
PLANNED ACTIVITIES | TIME FRAME | PROGRESS | CHALLENGES | REMEDIAL ACTIONS | TIME FRAME
Designing a quality assessment task (Project & Investigation) | August - October 2016 | Provided an exemplars of quality project and advised of which content can be used to develop a project | Inability of teacher to set an authentic project and/or an investigation | Avail example of these to school as part of item bank | 3 hours
Infusing ICT in teaching and learning (Maths Lab) | April – Nov 2016 | Liaise with the EDSC manager s to assist in this regard as well as invite them to visit the centre when time allows | Failure of teachers to infuse ICT in teaching Not all schools have the Maths Labs | Use the schools that have Maths Lab as centres to train other teachers | 2 hours

## Slide 12: INTERVENTIONS CONT…..
PLANNED ACTIVITIES | TIME FRAME | PROGRESS | CHALLENGES | REMEDIAL ACTIONS | TIME FRAME
Using error analysis to enhance teaching & learning | September 2016 | Plan to train other SESs in the District. | Inability of teachers to detect reasons behind learner responses to questions | Use moderation feedback to assist teachers in a mini workshop | 2hours
Maths Olympiad & Maths Week competitions | April -Aug 2016 | Competitions are running at school level | Not all schools participate | Teachers to be encouraged to enter their learners | April – Aug 2016

## Slide 13: 4.PROGRESSED LEARNERS INTERVENTIONS
PLANNED ACTIVITIES | TIME FRAME | PROGRESS | CHALLENGES | REMEDIAL ACTIONS | TIME FRAME
Mental Maths Speed test | Every Friday from Jan - Nov | Implementation as planned | Not all schools are implementing | Strengthening monitoring | During school visits
Weekly test / topic test | Jan – Nov 2016 | Implementation as planned | Not all schools are implementing | Strengthening monitoring | During school visits
Effective use of workbooks | Jan – Nov 2016 | Implementation as planned | Shortages of workbooks | Strengthening monitoring | During school visits

## Slide 14: 5.1 + 4 Intervention Programme
PLANNED ACTIVITIES | TIME FRAME | PROGRESS | CHALLENGES | REMEDIAL ACTIONS | TIME FRAME
Implementation of 1 + 4 intervention programme | April - Nov 2016 | DBE lesson plans issued out to schools There is implementation | Attendance since teachers are teaching other grades and subjects | On-site support | Implementation of 1 + 4 intervention programme

## Slide 15: MATHS 1 + 4 PROJECT
In 2016 the 1+4 started with a block training of subject advisors and educators at Orion Hotel by DBE
Lesson plans were distributed to all schools
Subject advisors monitored the implementation at school level
Subject advisors then classified teachers according to identified challenges
Development sessions are conducted according to groups identified
School visits conducted to offer classroom support,
Learners books checked during school visits
Common quarterly tests written by grade 8 and 9 learners to check on the impact of the intervention
The NECT training material is also useful in the 1+4 session.
This 1+4 improvement strategy is benefiting most teachers who did not specialise in Mathematics

## Slide 16: 6. FURTHER INTERVENTIONS
NECT training of SES on the use of the Planner and Curriculum Coverage tracker
The Planner and Tracker were provided to grades 8 & 9 educators electronically
The NECT term 3 grade 8 and 9 Workshop Booklet were distributed to schools in a CD, on the 15 August 2016
The Curriculum Planner and Tracker was introduced and discussed with all teachers during PSF meetings

## Slide 17: FURTHER INTERVENTIONS
Since lesson planning is a challenge in these schools, a daily preparation note book was suggested in term one 2016.
The usage of the DBE work book is emphasised in all the PSFs and meetings.
The usage of the DBE work book is closely monitored during school visits and SBA moderation.
Grade 7 and 8 Maths teachers are meeting in clusters once per term to discuss challenging math topics in these grades.
Grade 8 Mathematics assessment plan is aligned to grade 9 provincial assessment plan 2016.
Adherence to these plans is advocated in our meetings and monitored during school visits.

## Slide 18: 7 LEARNER ATTAINMENT IMPROVEMENT STRATEGY
LAIP which comprises of 123 items remains our main focus for interventions at all levels Amongst others:
Item 4: Correct time tabling
Item 5: Setting clear targets
Item 7: Monitoring teaching, learning and assessment
Item 13: Reporting quarterly progress
Item 14: Career orientation
Item 35: English Across the Curriculum: Maths Language
Item 42: Remedial support for Learners with identified barriers

## Slide 19: CONCLUSSION
In support of the provincial mandate we are:
“REACHING FOR GOLD”
And as Bojanala District we:
“Aim for the Sky and Touch the Stars”

## Slide 20
BOJANALA DISTRICT
? ? ?

## Slide 21: THANK YOU!!!